## Slide 1: JMUX Replacement
Progress Current Period (past 2 weeks)- Milestones/Key Deliverables with Dates
DC power installed and operational at Northport by Hawkeye 03/18/2026
OTDR bad filter replaced; wavelength tested – green link light confirmed at Hicksville-Syosset 03/24/2026
BGP design reviewed and approved by Vikas Vohra on 03/16; peer review in progress 03/24/2026
Fiber termination to the NSP completed by Hawkeye 03/24/2026
New batch of IFRs received from Burns & McDonnell 03/24/2026
ILO configuration in progress at Hicksville and Melville by Rahiq and Brianna 03/24/2026
IFR received for 6S Kings Hwy 03/24/2026
IFR received for 7BH Bohemia 03/24/2026
 | Status* | Trends*
Schedule Health | Yellow | 
Financial Health | Green | 
Scope Health | Green | 
Risk Health | Green | 
Resource Health | Green | 
Status Date: 03/24/2026
IT/Cyber: IT
Director: Irving Landesbaum
GPM: Vikas Vohra
Program Manager Jay Gunaratne
Time Management
Proj Plan (Baseline) Start 03-01-2024
Proj Actual Start 04-18-2024
Go-Live/In Service/Next Sprint Release 01-01-2024
Proj Plan (Baseline) End 04-08-2027
Proj Actual Target End 07-08-2027
Project Financials / Budget
WBS Code: I.39424.1.x
LIPA approved total project budget: $6,600,000.00
URB approved funding to date: $6,600,000.00
Spend to date: $4,548,505.00
Estimate to complete: $2,051,495.00
Estimate at completion: $6,600,000.00
Over (+) / Under (-) LIPA approved budget: +/- $00.00
Benefit
Due to GE announcing End of Life for the GE Jungle Mux system as of EOY 2025, the benefits for project is to allow the Systems Integrator to select the most appropriate ‘Equipment Vendor’ via the RFP process to replace the GE JMUX equipment.
Scope (95%-Complete)
The purpose of this project is to install new Multiprotocol Label Switching (MPLS) nodes, remove existing GE Jungle MUX (JMUX) equipment, and design new circuits from the existing substation .
Major Steps (next 2 weeks): Milestones/Key Deliverables with Dates
BGP peer review and Change Review Board approval (Daniel/Hasib/Vikas) 03/31/2026
BGP execution at Hicksville and Melville (Lee + Rahiq/Brianna on-site) 04/01/2026 - 04/02/2026
Phase 2 staging and equipment discussion call 03/26/2026
Phase 2 staging and equipment discussion call 03/26/2026
IFR packages due — Green Acres and Berry Street (BMcD) 03/30/2026
Risk Management- Top 3 (in descending order of possible impact)
Vendor installation delays – inclement weather
Legacy JMUX equipment old and need to be very careful when doing cutovers.
Other projects and work being done at the substation simultaneously
Issue Management- Top 3 (in descending order of actual impact)
Accelerating phase 2 site surveys by getting them completed in Phase 1.
Working closely with vendors and tracking installation.
Equipment procurement and delays in SCM.
Scope/Change Management (most recent approved)
Adding 7 additional nodes to the original 25 Phase 1 nodes. The additional 7 nodes completes both ring 1 and ring 2 in this Phase 1 effort.
PRJ (ServiceNow): PRJ13797
Repository Link : JMUX Repository
Lifecycle Phase:
Execution
Current Period (past 2 weeks) Status Narrative:
DC power installed and operational at Northport on 03/18 — Router installation complete.
Hicksville-Syosset link active. OTDR trace files (bidirectional + raw) requested from splicers.
NSP Hicksville equipment wiring in progress; wire drops to equipment being completed this week.
BGP design approved by Vikas Vohra on 03/16. Peer review with Daniel Reyes and Hasib in progress; Change Review Board scheduled 03/31. BGP execution at Hicksville (4/1) and Melville (4/2). Brianna and Rahiq to be on-site to console into routers.
ILO configuration in progress at Hicksville and Melville by Rahiq and Brianna this week.
IFR approved by Lee Blackman for Kings Hwy and Bohemia; IFCs to follow 03/30.
Nokia training courses selected with Shelton (Nokia). Awaiting Glenn Leaming approval; dates to be confirmed by 03/27.
Phase 2 material review underway; Vinny reviewing MRR and material counts. Staging discussion call scheduled 03/26.
C37.94 card identified as needed for Northport Indoor — to be included with Phase 2 miscellaneous order.
Remediation (For Non-Green Statuses)
Schedule (Yellow): BGP execution scheduled 4/1-4/2 at Hicksville and Melville. ILO configuration in progress this week. Recovery on track to restore Green upon BGP completion.
Project Description
The Systems Integrator will create, facilitate, and execute the process for generating an RFP to select an ‘Equipment Vendor’ to replace the existing Private Network vendor – GE Jungle MUX. In parallel, the Systems Integrator will conduct ‘high-level’ design activities for the MPLS Private Network, including site surveys at 88 COMPANY substations to assess specific structural and infrastructure modifications required for the new equipment.
Dependency Management |  | 
Project | Deliverable | Date
NA |  | 
Overall Health This Period Last Period
Version 3.0