## Slide 1
JMUX Replacement Program
CIO Briefing | Phase 1 Complete · Phase 2 Underway · Path to Completion
PRJ13797 | Program Manager: Dhananjaya Gunaratne | March 12, 2026
PSEG Long Island | IT Infrastructure
CONFIDENTIAL

## Slide 2
Executive Summary
JMUX Replacement Program — Status as of March 12, 2026
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
✅ Phase 1 COMPLETE
31 substations cutover to MPLS All Wave 1 & Wave 2 cutovers done NSP installed at Melville & Hicksville SSP & CMDB documentation approved Minor close-outs in progress (Hicksville cabling, OTDR)
🟡 Phase 2 IN PROGRESS
36-site engineering design underway Site surveys completed during Phase 1 Burns & McDonnell issuing IFRs & IFCs Nokia Phase 2 equipment delivered 2/19 Schedule: Yellow (2.5-wk delay, recovering)
📋 CIO Actions REQUIRED
Awareness: Schedule is yellow, recovery plan in place Approval: Confirm Phase 2 vendor engagement continues Decision: Resource support for SSP/security reviews Support: Crown Castle fiber issue at Hicksville

## Slide 3
Phase 1 Accomplishments
31 Substations | Complete
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
KEY ACCOMPLISHMENTS
All 31 substation sites installed & commissioned
Wave 1 cutover (12/8–12/18/25) — non-tie sites complete
Wave 2 cutover (1/6–1/8/26) — tie sites complete
CWDM cutover complete at Hicksville & ACC
Nokia NSP racked & powered at Melville & Hicksville
Staging completed at Hawkeye Warehouse — 9/29/25
SSP documentation approved by security team
CMDB inventory updated & confirmed — 2/24/26
Phase 2 site surveys completed during Phase 1 (ahead of schedule)
7 additional nodes added to complete Ring 1 & Ring 2
PHASE 1 AT A GLANCE
31 / 31
Sites Complete
100%
Cutover Done
2
Network Rings Closed
Sept 2025
Staging Complete
Jan 2026
Final Cutover
$4.44M
Spent to Date

## Slide 4
Phase 2 Status
36 Sites | Engineering Design Underway | Burns & McDonnell SOW: $1.37M
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Site Surveys
COMPLETE
Nokia Equip. Delivery
COMPLETE
IFR Design (B&McD)
IN PROGRESS
IFC Design
IN PROGRESS
Construction
NOT STARTED
Cutover
NOT STARTED
Milestone
Contract Date
Status
Notes
Phase 1 Staging Support
8/22/2025
✅ Complete
$57,300 paid
Phase 1 Construction Coordinator
Aug 2025–Jan 2026
✅ Complete
$368,100 — monthly invoiced
Substation Site Surveys (Phase 2)
2/27/2026
✅ Complete
Completed during Phase 1 — ahead of schedule
MPLS Network Node Design — IFR
Wave 1: 2/23/26
🟡 In Progress
B&McD issuing IFRs; PSEG LI review 2-wk window
MPLS Network Node Design — IFC
Wave 1: 3/23/26
⏳ Upcoming
IFC follows PSEG LI review & comment
Construction & Installation
Aug–Dec 2026
⏳ Not Started
Pending IFC completion

## Slide 5
Schedule Status
Overall: 🟡 Yellow | Recovery Plan in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
SCHEDULE PERFORMANCE INDEX (SPI)
SPI: 0.75
🟡 YELLOW — Schedule delayed ~2.5 weeks
Root Causes:
• SSP documentation delays (security review queue)
• CMDB update coordination time
• Inclement weather affecting field work
• Crown Castle fiber issue at Hicksville (OTDR testing pending)
Recovery Actions:
All approvals received. Remaining Phase 1 close-out is remote configuration — no physical site access needed. Phase 2 IFR/IFC design on track.
PROGRAM TIMELINE
Apr 2024 — Project Start
Oct 2024 — RFP Award & SOW Executed
Jan 2025 — Phase 1 Detailed Design Start
Sep 2025 — Staging Complete (Hawkeye)
Oct 2025 — Phase 1 Construction Start
Dec 2025 – Jan 2026 — Wave 1 & 2 Cutovers Complete
Feb 2026 — Nokia Phase 2 Equipment Delivered
Mar 2026 — Phase 2 IFR Design in Progress ◀ NOW
Mar–Jul 2026 — Phase 2 IFC Design & Review
Aug–Dec 2026 — Phase 2 Construction
Jul 2027 — Program Completion (Target)

## Slide 6
Financial Status
Program Budget: $6,600,000 | Status: ON BUDGET ✅
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
$6,600,000
Total URB Approved Budget
$4,437,070
Spent To Date (67%)
$2,162,930
Estimate to Complete
$0
Over / Under Budget
Budget Utilization
67% Spent
33% Remaining
PO #
Supplier
PO Value
Invoiced
Remaining
Status
7000001429
Burns & McDonnell
$137,500
$49,500
$88,000
🟡 Active
7000001415
Burns & McDonnell
$869,235
$798,665
$70,570
🟡 Active
7000002099
Burns & McDonnell (Ph2)
$1,370,040
$388,740
$981,300
🟡 Active
7000001857
Nokia of America
$1,899,030
$532,525
$1,366,505
🟡 Active
7000002054
Elecnor Hawkeye
$402,793
$257,619
$145,174
🟡 Active
7000001175
Nokia of America
$190,575
$190,575
$0
✅ Paid in Full
7000001748
Presidio Networked Sol.
$40,955
$40,955
$0
✅ Paid in Full
7000001767
Graybar Electric
$24,759
$24,759
$0
✅ Paid in Full

## Slide 7
Risks & Issues
Active Risks | Mitigations in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
⚠ ACTIVE RISKS
🔧 ACTIVE ISSUES / IN RESOLUTION
HIGH
Legacy Equipment Fragility
JMUX equipment 25+ yrs old. Faulty connectors, brittle fiber panels. Potential for unplanned outage during cutover.
Mitigation: Careful cutover planning; dedicated B&McD on-site support. Phase 1 complete — risk reduced going into Ph2.
MEDIUM
Substation Access Delays
Weather, scheduling conflicts, or escort availability can delay field work.
Mitigation: Verify weekly before mobilizing. Adjust site plan if specific sites inaccessible.
MEDIUM
Phase 2 Schedule Slippage
IFR/IFC design cycle (4-wk IFR + 2-wk review + 2-wk IFC) leaves limited buffer.
Mitigation: Phase 2 surveys done early. B&McD running concurrent site designs. Weekly status calls tracking.
LOW
Crown Castle Fiber Issue (Hicksville)
Low dB levels on fiber — may be Crown Castle's network, not PSEG LI.
Mitigation: OTDR testing planned 3/3. If Crown Castle issue confirmed, escalate to vendor.
IN PROGRESS
Cat 6 Cabling — Hicksville NSP
Cables ordered; Hawkeye scheduled to complete 3/3/2026.
SCHEDULED
OTDR Testing — Hicksville
Low dB levels. OTDR test set confirmed for 1550 & 1310nm. Site visit 3/3–3/4/2026.
IN PROGRESS
Remote Access — Phase 2 Nodes
NSP at Hicksville & Melville. Remote access needed before router configuration can begin.
COMPLETE
Phase 2 SSP / Security Reviews
Architecture review, security assessment, compliance readiness all approved 2/10/2026.

## Slide 8
CIO Actions Required
3 Items for Decision or Awareness
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
1
AWARENESS
Schedule Recovery — Yellow Status
Context: Phase 1 experienced a 2.5-week delay due to SSP documentation processing and inclement weather. The SPI stands at 0.75 for February.
Detail: Recovery plan is in place. Remaining Phase 1 close-out items are remote (no site access required). Phase 2 engineering is running concurrently. Overall program target end date remains July 2027.
➤ No action required — for awareness only.
2
APPROVAL
Continue Phase 2 Vendor Engagement
Context: Burns & McDonnell Phase 2 SOW ($1.37M) is active. IFR design has commenced for 36 sites. Nokia equipment delivered to staging. Phase 2 is on track to hit IFC milestones per SOW schedule.
Detail: Confirm continued engagement of B&McD and Elecnor Hawkeye for Phase 2 construction support as design packages are issued.
➤ Approval requested to proceed with Phase 2 construction mobilization once IFC packages are complete (expected Q2 2026).
3
SUPPORT
Crown Castle Fiber Issue — Hicksville
Context: OTDR testing revealed low dB levels on fiber at Hicksville substation. This may be a Crown Castle infrastructure issue outside PSEG LI's control.
Detail: OTDR testing was scheduled for 3/3–3/4/2026. If confirmed as Crown Castle issue, formal escalation to Crown Castle will be required, which may impact Phase 2 schedule at that site.
➤ Request CIO support if vendor escalation to Crown Castle is needed to expedite resolution.

## Slide 9
Next Steps & Path to Completion
March 2026 — July 2027
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
IMMEDIATE (Next 30 Days)
Mar 3
Hawkeye completes Cat 6 cabling for NSP at Hicksville
Mar 3–4
OTDR testing at Hicksville — resolve Crown Castle fiber issue
Mar 2026
Remote router configuration begins (Layer 1-3 setup)
Mar 2026
B&McD continues Wave 1 IFR submissions (Far Rockaway, Valley Stream, Cedarhurst)
Mar 9
PSEG LI review window opens for Wave 1 IFR packages
Mar 23
Wave 1 IFC target completion
Ongoing
Weekly status calls with B&McD; monthly schedule updates
PATH TO COMPLETION
Q1 2026
Phase 1 close-out & Phase 2 IFR design
Q2 2026
Phase 2 IFC completion (all 36 sites)
Q2–Q3 2026
Phase 2 construction mobilization
Q3–Q4 2026
Phase 2 installations at all 36 sites
Q4 2026
Phase 2 cutovers — Waves 3 & 4
Q1 2027
As-built documentation complete
Jul 2027
🏁 Program Complete