## Slide 1: PRJ13797: JMUX Replacement Update Project Manager : Dhananjaya Gunaratne
March 2026

## Slide 2
JMUX Replacement: Private Field Area Network
Modernize PSEG LI’s substations communications by replacing legacy JMUX with MPLS nodes to deliver a reliable, scalable and future-ready network.
Objectives
  Engineering Services (Burns & McDonnell)
    Site surveys, rack elevations, power & cabling design
    Node Design – Produce IFR, IFC and As-Built documents
Procurement & Staging (Burns & McDonnell, Nokia, Graybar)
    Bill Of Material creation, MPLS Equipment order, Power and ancillary equipment(Patch panels, Fiber cables, mounting kits etc.)
Construction and Installation Support (Burns & McDonnell, Hawkeye)
    BMcD to provide on-site coordination with engineering team, technical support and commissioning oversight.
    Hawkeye to assist with shipment, racking, stacking and power during staging. Perform site surveys for construction support. Install all the equipment as per the approved IFC document
    Run Fiber or copper cabling as per the construction documents.
    Deployment and Application Migration (PSEG, Burns & McDonnell)
    Design and configure Layer 3 networks
    Pre-Stage the application connectivity
    Migrate production applications
SCOPE | SUBSTATIONS | MPLS SITES | DF RTU SITES | RADIO SHELTER SITES | NOKIA MPLS NODES
PHASE 1 | 49 | 26 | 17 | 6 | 31
PHASE 2 | 45 | 26 | 12 | 7 | 26
PHASE 3 | 35 | 22 | 7 | 6 | 22
TOTAL SCOPE | 129 | 74 | 36 | 19 | 79
Goal & Objectives

## Slide 3
.
Highlight Project Accomplishments
JMUX Replacement: Private Field Area Network

## Slide 5
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Survey | IFR | IFC | Construction | Deployment
1 | 7RM Bayport | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
2 | 7R Sayville | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/23/26
3 | 7XM Great River | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
4 | 7XM Great River Radio Shelter | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
5 | 6H Hauppauge | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
6 | 6H Hauppauge Tower | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
7 | 6S Kings Hwy | Complete | Fri 3/13/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
8 | Brentwood DO | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 9/2/26 | Fri 9/25/26
9 | 7H Babylon | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Mon 9/21/26
10 | 7H Babylon Radio Shelter | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Tue 9/22/26
11 | 7D West Babylon | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/12/26 | Mon 9/21/26
12 | 7D West Babylon Radio Shelter | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/19/26 | Mon 9/21/26
13 | 7W Berry St | Complete | Mon 3/30/26 | Tue 6/23/26 | Wed 8/19/26 | Mon 9/23/26
14 | 3J Whiteside | Complete | Mon 4/6/26 | Mon 5/4/26 | Wed 8/12/26 | Mon 9/14/26
15 | 2K Valley Stream | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
JMUX Replacement: Private Field Area Network

## Slide 6
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
16 | 2RB Green Acres | Complete | Mon 3/30/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
17 | Hewlett DO | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Fri 9/25/26
18 | 2ZB EF Barrett PS Inside | Complete | Mon 3/23/26 | Mon 4/20/26 | Wed 8/5/26 | Mon 9/14/26
19 | 2WB Barrett Outside | Complete | Mon 3/23/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
20 | 5HK Hicksville | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
21 | 2H Far Rockaway | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
22 | 2KB Cedarhurst | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
23 | 2R Hewlett | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
24 | 2R Hewlett Shelter | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
25 | 4M Baldwin | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
26 | 4M1 Baldwin Shelter | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
27 | 6K State School | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Fri 9/17/26
28 | 7BH Bohemia | Complete | Fri 3/13/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
29 | 7M MacArthur | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/22/26
JMUX Replacement: Private Field Area Network

## Slide 7
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
30 | 8AX Patchogue | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
31 | 8AX Patchogue Shelter | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
32 | 7Z Lindenhurst | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
33 | 7J Sterling | Complete | Mon 3/30/26 | Tue 6/9/26 | Wed 8/26/26 | Mon 9/22/26
34 | 7UM South Farmingdale | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
35 | ACC | Complete | Tue 6/9/26 | Wed 7/8/26 | Tue 9/8/26 | Mon 9/28/26
36 | 6U Ruland | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
JMUX Replacement: Private Field Area Network

## Slide 8
Schedule Status
Overall: 🟡 Yellow | Recovery Plan in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Root Causes:
• SSP documentation delays (security review queue)
• CMDB update coordination time
Recovery Actions:
SPI = 0.76 (Yellow).
Complete iLO port configuration without
Complete BGP Configuration at Hicksville and Melville
Remote access routers and complete configuration as per SSP doc.
SCHEDULE PERFORMANCE INDEX (SPI)
0.00
0.50
0.75
1.00
1.25
1.50
2.00
●
Below 0.70 — Critical
●
0.70–0.90 — Yellow
●
0.90–1.10 — On Track
●
Above 1.10 — Ahead
--- February 2026 : 0.75 (Orange)
╌╌ January 2026 : 1.00 (Gray)
--- March 2026 : 0.76 (Yellow ↓)
Week | Dates | Planned site (PV) | Actual Sites Completed (EV) | Weekly SPI | Culmative SPI | Key Notes
Northport Fuse issue | 2/26/2026 | 1 milestone (DC power complete) | 0 (DC power complete) | 1.00 | 0.75 | Northport fuse tripping — ILO work blocked. DC power issue resolved
OTDR Testing from Syosset to Hicksville, link now active | 3/9/2026 | 1 milestone (OTDR confirm) | 1 (OTDR complete ✅) | 1.00 | 0.75 | OTDR confirmed bad filter at Hicksville. Link now active. Crown Castle issue cleared. ✅
NSP cable run and terminated | 3/10/2026 | 1 milestone (NSP fiber term) | 1 (complete ✅) | 1.00 | 0.76 | Fiber run to NSP completed & terminated at Hicksville by Hawkeye. ✅
BGP design approved | 3/16/2026 | 1 milestone (BGP approval) | 1 (approved ✅) | 1.00 | 0.76 | BGP design formally approved. Lee to begin change docs for Hicksville & Melville. ✅
Moved all eqpt to new Hawkeye trailer for future staging . | 3/10/2026 | 0 (logistics task) | 0.5 (complete ✅) | N/A | 0.76 | Phase 2 Nokia equipment moved to new Hawkeye staging trailer. Not on critical path.
JMUX Replacement: Private Field Area Network

## Slide 9
Financials (2024-2026)
JMUX Replacement: Private Field Area Network

## Slide 10
Current Risk
  Legacy JMUX equipment old and delicate. Potential for Outage.
      Ran into faulty connectors that are over 25 years old and not readily available with vendors.
      Potential brittle fiber patch panels, Face plates, connectors and cables.
  Weather delay and delay in installing the equipment at sub-station (tracking weekly).
  Potential Schedule delays due to other major substation project conflicts.
Next Steps
iLO corporate connectivity interfaces turned up at Melville and Hicksville
BGP Configurations and integration with Corporate network in Melville & Hicksville
Remote access into Nokia routers to manage routers
Baseline network configurations and testing on Nokia Routers
JMUX Replacement: Private Field Area Network