## Slide 1
PAR Circuit Migration — Background & Discovery
PRJ13797: JMUX Replacement | PSEG Long Island | April 2026
📌 WHAT IS PAR CIRCUIT MIGRATION?
▸ 6 high-voltage substations require serial-to-IP conversion to connect legacy RTUs to the new Nokia MPLS network
▸ Sites: Northport · Hicksville (5HK) · Melville · Lindenhurst (7Z) · Far Rockaway (2H) · Hewlett (2R)
▸ NERC CIP compliance MANDATES an intermediary system — direct Nokia-to-RTU connection is not supported
▸ Solution selected: Iniven RC-30 — converts direct contact signals to C37.94 IP protocol
▸ No alternative solution exists — compliance is non-negotiable
❓ WHY WASN'T THIS FULLY SCOPED IN 2024?
▸ During 2024 kickoff meetings with Martin (Marty), PAR was acknowledged at a HIGH LEVEL ONLY
▸ General agreement reached: "C37.94 protocol should be okay" — no detailed design, cost, or schedule produced
▸ Marty indicated design cost would fall on the technical security team — no dollar figure was agreed upon
▸ PAR was a Phase 3 placeholder with a rough budget of ~$30K–$40K for general support only
▸ Consistent with project methodology — detailed requirements confirmed during each phase's site surveys
▸ Alex also discussed this briefly at the start — tentative rough plan only, no details captured
🔍 HOW WAS THE FULL SCOPE DISCOVERED?
▸ During Phase 2 detailed site surveys, the relay team was formally engaged for the first time
▸ Site-by-site review of existing RTU technology (SEL-2595 systems) revealed full technical & compliance scope
▸ 6 specific high-impact substations identified as requiring a dedicated intermediary solution
▸ True level of effort and cost first identified at this point — NOT a project management oversight
✅ WHAT WAS EVALUATED & DECIDED
▸ All available technology options reviewed at each of the 6 substations
▸ NERC CIP compliance requirements assessed for each site
▸ Only viable compliant solution confirmed: Iniven RC-30 intermediary device
▸ Chakrapani's T&D team engaged for engineering design
▸ PO placed for RC-30 equipment — 8-week lead time
▸ Proactively engaging ALL Phase 3 stakeholders now to prevent further scope gaps
PSEG Long Island | JMUX Replacement Program | PRJ13797 | Confidential | April 2026

## Slide 2
PAR Circuit Migration — Schedule & Financial Impact
PRJ13797: JMUX Replacement | PSEG Long Island | April 2026
💰 FINANCIAL IMPACT — ADDITIONAL UNBUDGETED FUNDING REQUIRED
Cost Component
Team Responsible
Est. Cost
Status
Iniven RC-30 Equipment (6 sites)
Iniven (Vendor)
~$60,000
PO Placed ✅
PAR Engineering Design
Chakrapani / T&D Team
TBD *
In Progress ⏳
Installation, Config & Cutover Labor
Relay Team — Johnny's Team
~$495,000 **
Not Started 🔴
TOTAL ADDITIONAL FUNDING REQUIRED
~$550,000+
* Engineering design cost TBD — to be confirmed once Chakrapani's team completes design scope
** Relay labor rate (~$1,100–$1,200/hr) and total hours per site being confirmed with Ethan & Chad
⚠ Chad's current Apr–Jun forecast = $120K (equipment + design only). $495K relay labor NOT YET included — to be spread across months once design is complete.
📅 SCHEDULE IMPACT
▸ Direct schedule impact: ~2–3 months
▸ PAR work running IN PARALLEL with Phase 2 construction — not on critical path
▸ Phase 3 site surveys & detail design accelerated into Phase 2 staging window (~Aug 2026)
▸ Ethan confirmed: Phase 3 engineering starts as soon as Phase 2 staging begins
▸ B&M Phase 3 design: estimated Jun–Dec 2026 (~$900K–$1.29M — to be confirmed)
▸ Projected full recovery: End of 2026
🔄 RECOVERY PLAN & ACTIONS TAKEN
✅ Iniven RC-30 PO placed — equipment on order, 8-week lead time
✅ Chakrapani's team engaged for PAR engineering design
✅ PAR migration parallelized — no impact to Phase 2 deployment critical path
✅ Phase 3 engineering accelerated — site surveys start at Phase 2 staging
✅ CIO (Greg) informed informally at All Hands — not a surprise
⏳ Formal budget Change Request to be submitted
⏳ Relay labor ($495K) to be spread across months once Chakrapani design complete
PSEG Long Island | JMUX Replacement Program | PRJ13797 | Confidential | April 2026