PRJ13797 — JMUX Replacement CIO Oral Talking Points · March 2026 Focus: February 2026 & Last Two Weeks (Mar 4–18, 2026) · Audience: CIO, SVP, Project Team

📌 SCOPE OF THIS DOCUMENT: Talking points cover only recent work — February 2026 and the last two weeks (Mar 4–18, 2026). No staging history. No CWDM cutover background. Present this as: 'Here is what we accomplished and where we stand right now.'

SLIDE 1 · OPENING ⏱ ~2 minutes

WHAT TO SAY:

"Good [morning/afternoon] everyone. I'm Jay Gunaratne, Program Manager for PRJ13797 — the JMUX Replacement program. Thank you for the time today."

"Today I want to walk you through what we accomplished in February and over the past two weeks — and where we stand right now on the critical path."

"I'll keep this focused on recent activity, current blockers, and the path forward. No history — just where we are and where we're going."

💡 DELIVERY TIP: Keep it short. One minute max. No backstory. Dive straight into the work.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 2 · GOALS & OBJECTIVES / PROGRAM SCOPE ⏱ ~3 minutes

WHAT TO SAY — focus on Phase 2 progress, not Phase 1 history:

"The program is 129 substations across three phases. Phase 1 — 31 sites — construction is complete. We are now in the configuration and cutover phase."

"In February, Nokia delivered all Phase 2 equipment on February 19th — ahead of schedule. That equipment is safely stored at the Hawkeye warehouse and ready for Phase 2 mobilization."

"Phase 2 site surveys — completed ahead of schedule. Phase 2 IFRs are being issued by Burns & McDonnell. Phase 2 IFCs are in progress."

"The OTDR testing from Hicksville to Syosset — that work is complete."

💡 DELIVERY TIP: Skip the program history. Lead with Nokia delivery and Phase 2 momentum. The CIO wants to hear forward progress.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 3 · PHASE 1 ACCOMPLISHMENTS — RECENT WORK ONLY ⏱ ~4 minutes

FEBRUARY 2026 ACCOMPLISHMENTS:

Nokia Phase 2 equipment delivered — February 19, 2026. ✅  All 26 nodes accounted for and stored at Hawkeye.

Phase 2 site surveys confirmed complete by end of February — no field surveys needed to start Phase 2 design.

LAST TWO WEEKS — March 4 through March 18, 2026:

Cat 6 cable run to NSP in Hicksville — completed by Hawkeye on March 4, 2026. ✅

OTDR testing from Hicksville to Syosset — completed March 9, 2026. ✅  Bad filter identified and replaced. Crown Castle fiber issue cleared — no escalation needed.

OTDR trace files sent to Burns & McDonnell. ✅

First batch of IFRs (3 sites: Far Rockaway, Valley Stream, Cedarhurst) — converted to IFC and uploaded to the shared drive. March 9, 2026. ✅

Fiber termination to the NSP completed by Hawkeye — March 13, 2026. ✅

New set of IFRs received from BMcD — March 13, 2026. ✅

BGP design approved — March 16, 2026. ✅  Lee Blackman to begin change documentation for Melville and Hicksville Nokia integration.

Northport DC power issue — FULLY RESOLVED. New cable run installed. Issue confirmed closed — March 18, 2026. ✅

💡 DELIVERY TIP: Walk through this list like a scorecard. Pause after each one. Let the wins land. The CIO and SVP want to see momentum.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 4 · PHASE 2 STATUS ⏱ ~4 minutes

WHAT TO SAY — February & current status:

"Phase 2 is tracking well. Let me walk you through where each workstream stands."

Site surveys — completed during Phase 1. No new surveys needed. We're ahead of the Phase 2 design start. ✅

Nokia Phase 2 equipment — delivered February 19th, stored at Hawkeye. ✅

IFR design (Burns & McDonnell): Wave 1 — Far Rockaway, Valley Stream, Cedarhurst — approved and converted to IFC. Uploaded to shared drive. ✅  Wave 2 currently in progress.

IFC design: Wave 1 complete and approved. Wave 2 follows the standard 4-week IFR + 2-week review cycle. On track.

Construction — targeted August through December 2026. Not started yet — that's correct and expected at this stage.

"The key message on Phase 2: the design engine is running while we close out Phase 1 configuration. We are not waiting."

💡 DELIVERY TIP: Phase 2 is a good news story. Keep your energy up here. This is momentum, not catch-up.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 5 · SCHEDULE STATUS ⏱ ~4 minutes

WHAT TO SAY — Own the yellow. Pivot fast to the plan:

"Our SPI is 0.76 — we're in the yellow band. February was 0.75 — we've stabilized but are not yet green."

"I want to name the blocker directly: ILO configuration. Bill from Burns & McDonnell is working with Rahiq to resolve a console cable and firmware issue. That is the gate. Everything downstream — BGP, remote access, cutovers — unlocks once ILO is done."

"The good news: four major items closed in the past two weeks. Cat 6 done March 4. OTDR done March 9. BGP approved March 16. Northport DC power — new cable run — fully resolved March 18."

Recovery sequence: ILO complete → BGP config at Hicksville & Melville (Lee Blackman) → Remote access all 31 routers → Application cutovers → RTU cutovers → Phase 1 close June 2026.

"February SPI was 0.75. March is 0.76. We are moving in the right direction. The recovery plan is detailed and owned."

💡 DELIVERY TIP: Speak slowly here. Don't rush past the yellow. Name it, own it, then pivot immediately to the 4 wins and the recovery chain. That's the credibility move.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 6 · CRITICAL PATH — NEXT 10 STEPS ⏱ ~5 minutes

WHAT TO SAY — Walk each step, name the owner:

Step 1 — ILO Console Cable & Firmware (Mar 19–20): Bill (B&M) + Rahiq. Cables being sourced. This is the #1 gate.

Step 2 — ILO Port Activation (Mar 21–24): Rahiq, Brianna, Bill. Configure ILO management ports at Hicksville & Melville.

Step 3 — Wire Drops (Mar 19–21, running in parallel): Jay + Hawkeye. LGX panel drops to equipment. SFPs and change order needed.

Step 4 — Nokia Training: March 19 at 3PM with Glenn from Nokia + PSEG LI team. ✅ Done.

Step 5 — Phase 2 BOM & Inventory (week of Mar 23): Jay + Vinny at Hawkeye. Reconcile Phase 2 Nokia equipment vs BOM.

Step 6 — BGP Configuration (Mar 24–28): Lee Blackman configures BGP at Hicksville & Melville once ILO complete.

Step 7 — IFR Submissions for Green Acres & Berry Street (Mar 30): Ethan Koch, BMcD. On track.

Step 8 — Remote Access Config (Apr 1–18): Lee Blackman configures all 31 routers remotely once BGP validated.

Step 9 — NSP Software Install & Layer 3 (Mid–Late April): Nokia + Lee. Starting at hub sites, rolling to all 31.

Step 10 — App & RTU Cutovers (May 2026): PSEG LI, BMcD, Hawkeye. Phase 1 close target: June 2026.

💡 DELIVERY TIP: This is your most important slide. Take your time. The CIO and SVP want to see a clear, owned, step-by-step plan. Don't rush through it.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 7–8 · PHASE 1 DETAIL & LAYER 1-3 CONFIG ⏱ ~3 minutes

WHAT TO SAY — Focus only on what's recent and relevant:

"I'll keep this brief. The construction accomplishments are behind us. What I want to highlight is where we are right now on the configuration side."

Cat 6 complete March 4. Fiber termination to NSP complete March 13. OTDR trace files with B&M. BGP approved March 16.

Layer 1 physical work — essentially done. Wire drops are the last item in progress.

Layer 2 and 3 — ILO, BGP, remote access — this is the active workstream. Owned by Bill, Rahiq, and Lee Blackman.

Once ILO is resolved, configuration work is fully remote. No more field mobilization needed for Phase 1.

💡 DELIVERY TIP: Don't dwell here. Slide through quickly. Acknowledge the work, move to the status report.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 9 · PROJECT STATUS REPORT — PMO FORMAT ⏱ ~4 minutes

FINANCIALS — Lead with the numbers. No surprises.

Total LIPA-approved budget: $6.6 million.

Spend to date: $4.44 million. Estimate to complete: $2.16 million. Estimate at completion: $6.6 million.

NO budget variance. We are tracking at budget.

Project scope: 65% complete as of this reporting period.

RECENT MILESTONES — Last 2 weeks:

Cat 6 cable run — completed March 4 by Hawkeye. ✅

OTDR testing — completed March 9. Bad filter found and replaced. ✅

Wave 1 IFRs (3 sites) — converted to IFC and uploaded to shared drive. March 9. ✅

Fiber termination to NSP — completed by Hawkeye, March 13. ✅

BGP design approved — March 16. Lee Blackman proceeding with change documentation. ✅

Northport DC power — new cable run installed, issue fully resolved, March 18. ✅

ACTIVE BLOCKER:

🔴 ILO configuration — Bill (B&M) coordinating with Rahiq. Console cable & firmware. #1 critical path blocker.

🔴 BGP config at Hicksville & Melville — pending ILO completion.

🔴 Remote access 31 routers — pending BGP completion.

REMEDIATION:

Complete remote config of all 31 routers and testing → bring SPI back to green by June 2026.

💡 DELIVERY TIP: Financials are clean. Let that land first. Then pivot to the milestone wins, then address the reds directly.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 10–12 · PHASE 1 SUBSTATION SCHEDULE ⏱ ~2 minutes

WHAT TO SAY — Brief:

"This is the Phase 1 substation schedule. All 31 sites complete on the construction side."

"Phase 2 site surveys — also shown here — complete. We knocked those out proactively during Phase 1."

"The remaining work is remote configuration — April through June. No field mobilization required."

💡 DELIVERY TIP: Spend 60–90 seconds per page max. Visual slides — let them read. Just narrate the headline.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 13 · CURRENT RISKS & NEXT STEPS ⏱ ~4 minutes

RECENT WINS — Lead with these:

Cat 6 ✅  OTDR ✅  OTDR trace files to B&M ✅  BGP approved ✅  Northport DC power — new cable run, FULLY RESOLVED ✅

ACTIVE RISKS:

Legacy equipment fragility — 25+ year-old JMUX. Mitigation: careful planning, B&McD on-site. Phase 1 construction done — risk reduced going into Phase 2.

Weather and access delays — medium risk, tracked weekly.

THREE REDS — all connected:

🔴 ILO: Bill is personally engaged with Rahiq. Console cable being sourced. Tracking daily.

🔴 BGP config: Lee Blackman ready to go the moment ILO is resolved.

🔴 Remote access 31 routers: follows BGP. Lee owns this end to end.

💡 DELIVERY TIP: Don't let the reds hang in the air. Name them, assign them, state the resolution date. Move on.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 14 · RISKS & ISSUES REGISTER ⏱ ~3 minutes

RESOLVED — Close these out confidently:

✅ Crown Castle fiber (Hicksville) — OTDR confirmed bad filter March 9. Closed. No escalation.

✅ Cat 6 cabling Hicksville NSP — confirmed by Vinny (Hawkeye) March 13. Closed.

✅ OTDR testing — complete March 9. Trace files sent to B&M. Closed.

✅ Northport DC power — new cable run, confirmed closed March 18. Closed.

✅ Phase 2 SSP / security reviews — all approved February 10, 2026. Closed.

ACTIVE:

🔴 Remote access Phase 2 nodes — BGP approved March 16. ILO is the gate. Bill/Rahiq resolving.

ACTIVE RISKS (open):

HIGH — Legacy equipment fragility. Mitigation in place. Risk level dropping as Phase 1 construction completes.

MEDIUM — Substation access delays. Tracked weekly.

MEDIUM — Phase 2 schedule slippage. Mitigated by concurrent B&McD design and early survey completion.

💡 DELIVERY TIP: Five resolved items is a strong story. Lead with the green. End on the one red with a clear owner and timeline.

───────────────────────────────────────────────────────────────────────────────────────────────

SLIDE 15 · NEXT STEPS & PATH TO COMPLETION — CLOSE ⏱ ~4 minutes

NEXT 30 DAYS:

ILO resolution — Bill & Rahiq. This week.

BGP configuration — Lee Blackman. March 24–28.

Phase 2 BOM & inventory reconciliation — Jay + Vinny at Hawkeye. Week of March 23.

IFR submissions for Green Acres & Berry Street — Ethan Koch, BMcD. March 30.

Wave 1 IFC complete — Far Rockaway, Valley Stream, Cedarhurst. Already done ✅. Wave 2 in progress.

Weekly status calls with B&McD continuing.

PATH TO COMPLETION:

Phase 1 Operational — June 2026

Phase 2 IFC completion — Q2 2026

Phase 2 construction — Q3–Q4 2026

Phase 2 cutovers — Q4 2026

Program Complete — July 2027 🏁

CLOSING STATEMENT:

"The last two weeks have been productive. Five items resolved. BGP approved. Phase 2 design running in parallel. One blocker on the critical path — actively being resolved, ownership is clear. I'm confident in the June 2026 Phase 1 close and the July 2027 program completion. Happy to take questions."

💡 DELIVERY TIP: End strong. Confident tone. The audience should leave knowing: things are being handled, the plan is real, and you are in control.

PRJ13797  ·  JMUX Replacement  ·  Jay Gunaratne  ·  March 2026  ·  PSEG Long Island  ·  CONFIDENTIAL