## Slide 1
Next Steps & Current Risks
PRJ13797: JMUX Replacement | PSEG Long Island | April 2026
📋 NEXT STEPS — Priority Order
1️⃣
Resolve DNS (.11→.15, .21→.25) — confirm NSP GUI access to ALL Nokia routers
Vic / Lee / Wayne
2️⃣
Execute RTU serial port test at Hicksville — validate pinout before Phase 2 construction
Ethan / John Ng / Jay
3️⃣
Relay RTU cutover to Nokia network — first production circuit migration
Lee / John Ng
4️⃣
Start PAR engineering design — Chakrapani team, concurrent with RC-30 delivery
BMcD / Jay
5️⃣
Northport C37.94 card — bundle order with Phase 2 equipment PO
Jay / BMcD
6️⃣
Hawkeye site surveys — cable & SFP inventory across all Phase 2 sites
Vinny / Hawkeye
7️⃣
Confirm Nokia training dates with Glenn — identify attendees & syllabus
Jay
8️⃣
Lindenhurst IFR submission — due Monday April 27 ⚠️ IMMINENT
Burns & McDonnell
9️⃣
Reconcile PAR relay labor ($495K) forecast with Chad — spread across months
Jay / Chad
⚠️ CURRENT RISKS
🟡
DNS Update
NSP installed 4/21, status being confirmed. DNS fix escalated to Vic.
🟡
Weather Delays
Substation closures possible at temps >90°F. Potential 2-week delay per event. Risk — not yet an issue. Monitor summer forecast. Schedule critical work in cooler windows.
🟡
RTU Serial Test Scheduling
DB9 cables delivered to John Ng ✅. Awaiting test date from relay team.
PSEG Long Island | JMUX Replacement Program | PRJ13797 | Confidential | April 2026