## Slide 1: PRJ13797: JMUX Replacement Update Project Manager : Dhananjaya Gunaratne
April 2026

## Slide 2
Modernize PSEG LI’s substation communications by replacing legacy JMUX with MPLS nodes to deliver a reliable, scalable and future-ready network.
Objectives
  Engineering Services (Burns & McDonnell)
    Site surveys, rack elevations, power & cabling design
    Node Design – Produce IFR, IFC and As-Built documents
Procurement & Staging (Burns & McDonnell, Nokia, Graybar)
    Bill Of Materials creation, MPLS Equipment order, Power and ancillary equipment(Patch panels, Fiber cables, mounting kits etc.)
Construction and Installation Support (Burns & McDonnell, Hawkeye)
    BMcD to provide on-site coordination with engineering team, technical support and commissioning oversight.
    Hawkeye to assist with shipment, racking, stacking and power during staging. Perform site surveys for construction support. Install all equipment per the approved IFC document
    Run Fiber or copper cabling as per the construction documents.
    Deployment and Application Migration (PSEG, Burns & McDonnell)
    Design and configure Layer 3 networks
    Pre-stage the application connectivity
    Migrate production applications
SCOPE | SUBSTATIONS | MPLS SITES | DF RTU SITES | RADIO SHELTER SITES | NOKIA MPLS NODES
PHASE 1 | 49 | 26 | 17 | 6 | 31
PHASE 2 | 45 | 26 | 12 | 7 | 26
PHASE 3 | 35 | 22 | 7 | 6 | 22
TOTAL SCOPE | 129 | 74 | 36 | 19 | 79
Goal & Objectives

## Slide 4
PAR Circuit Migration — Background & Discovery
PRJ13797: JMUX Replacement | PSEG Long Island | April 2026
📌 WHAT IS PAR CIRCUIT MIGRATION?
▸ 6 high-voltage substations require serial-to-IP conversion to connect legacy RTUs to the new Nokia MPLS network
▸ Sites: Northport(6F) ·Pilgrim(6DL) ·Barrett(2WB) ·E Garden City(3AF) ·Valley Steam(2K) ·Hicksville(5HK)
▸ NERC CIP compliance MANDATES an intermediary system — direct Nokia-to-RTU connection is not supported
▸ Solution selected: Iniven RC-30 — converts direct contact signals to C37.94 IP protocol
▸ No alternative solution exists — compliance is non-negotiable
❓ WHY WASN'T THIS FULLY SCOPED IN 2024?
▸ During 2024 requirement gathering , PAR was acknowledged at a HIGH LEVEL ONLY
  no detailed design, cost, or schedule produced
▸ PAR was a Phase 3 placeholder with a rough budget of ~$30K–$40K, included in the RTU migration.
🔍 HOW WAS THE FULL SCOPE DISCOVERED?
Consistent with project methodology — detailed requirements confirmed during each phase's site surveys
▸ During the site surveys, the engineering and relay team were engaged to capture detail requirements for the RTU planned for Phase 2.
▸ Site-by-site review of existing RTU technology (SEL-2595 systems) revealed full technical & compliance scope
▸ 6 specific high-impact substations identified as requiring a dedicated intermediary solution
▸ True level of effort and cost first identified at this point.
✅ WHAT WAS EVALUATED & DECIDED
▸ All available technology options reviewed at each of the 6 substations
▸ NERC CIP compliance requirements assessed for each site
▸ Only viable compliant solution confirmed: Iniven RC-30 intermediary device
▸ Relay protection engineering & implementation teams were engaged.
▸ PO placed for RC-30 equipment — 8-week lead time
▸ Proactively engaging ALL Phase 3 stakeholders now to prevent further scope gaps
PSEG Long Island | JMUX Replacement Program | PRJ13797 | Confidential | April 2026

## Slide 5
PAR Circuit Migration — Schedule & Financial Impact
PRJ13797: JMUX Replacement | PSEG Long Island | April 2026
💰 FINANCIAL IMPACT — ADDITIONAL UNBUDGETED FUNDING REQUIRED
Cost Component
Team Responsible
Est. Cost
Status
Iniven RC-30 Equipment (6 sites)
Iniven (Vendor)
~$59,500
PO Placed ✅
PAR Engineering Design
Chakrapani (Protection Engineering)
$240,000*
In Progress ⏳
Installation, Config & Cutover Labor
Relay Team — John Ng & Steven Bradley (Relay Team)
$230,000 **
Not Started 🔴
TOTAL ADDITIONAL FUNDING REQUIRED
~$529,500
* Engineering design cost estimated at 200/hours per site @200/hours = 200 X 6 sites X 200
** Relay team implementation and testing estimate 1000 hours @ $200/hour + material (cables, connectors)
PSEG Long Island | JMUX Replacement Program | PRJ13797 | Confidential | April 2026
📅 SCHEDULE IMPACT
▸ Potential overall project schedule impact due to PAR design and implementation: ~5 months
▸ PAR hardware order and receipt: 2 Months
▸ PAR engineering design/implementation : ~5 months
▸ PAR implementation & Testing : ~2 months (covered under original RTU cut-over)
▸ Net schedule impact – None (See Recovery Plan)
🔄 RECOVERY PLAN & ACTIONS TAKEN
✅ Material (Iniven RC-30) for PAR sites ordered—, 8-week lead time
✅ PAR engineering design work running “IN PARALLEL” with Phase 2 construction.
✅ PAR migration— no impact to Phase 2 deployment critical path
✅ Phase 3 engineering accelerated — site survey and MPLS design planned to start in Phase 2.
⏳ Formal budge change request to be submitted for the Phase 3 accelerated work (800K)
⏳ PAR engineering and implementation and Relay labor ($530K) to be requested in Phase 2.
⏳ Total funding to be requested for PAR and Phase 3 accelerated work in June - $1.2 M

## Slide 7
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Survey | IFR | IFC | Construction | Deployment
1 | 7RM Bayport | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
2 | 7R Sayville | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/23/26
3 | 7XM Great River | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
4 | 7XM Great River Radio Shelter | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
5 | 6H Hauppauge | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
6 | 6H Hauppauge Tower | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
7 | 6S Kings Hwy | Complete | Mon 3/31/26 | Mon 3/31/26 | Wed 8/12/26 | Fri 9/18/26
8 | Brentwood DO | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 9/2/26 | Fri 9/25/26
9 | 7H Babylon | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Mon 9/21/26
10 | 7H Babylon Radio Shelter | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Tue 9/22/26
11 | 7D West Babylon | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/12/26 | Mon 9/21/26
12 | 7D West Babylon Radio Shelter | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/19/26 | Mon 9/21/26
13 | 7W Berry St | Complete | Mon 3/31/26 | Tue 4/21/26 | Wed 8/19/26 | Mon 9/23/26
14 | 3J Whiteside | Complete | Mon 4/13/26 | Tue 4/21/26 | Wed 8/12/26 | Mon 9/14/26
15 | 2K Valley Stream | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
JMUX Replacement: Private Field Area Network

## Slide 8
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
16 | 2RB Green Acres | Complete | Mon 3/31/26 | Tue 4/21/26 | Wed 8/5/26 | Mon 9/14/26
17 | Hewlett DO | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Fri 9/25/26
18 | 2ZB EF Barrett PS Inside | Complete | Mon 5/23/26 | Mon 6/15/26 | Wed 8/5/26 | Mon 9/14/26
19 | 2WB Barrett Outside | Complete | Mon 5/23/26 | Mon 6/6/26 | Wed 8/5/26 | Mon 9/14/26
20 | 5HK Hicksville | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
21 | 2H Far Rockaway | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
22 | 2KB Cedarhurst | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
23 | 2R Hewlett | Complete | Mon 5/23/26 | Mon 6/23/26 | Wed 8/5/26 | Mon 9/14/26
24 | 2R Hewlett Shelter | Complete | Mon 5/23/26 | Mon 6/23/26 | Wed 8/5/26 | Mon 9/14/26
25 | 4M Baldwin | Complete | Mon 5/13/26 | Mon 6/11/26 | Wed 8/12/26 | Mon 9/14/26
26 | 4M1 Baldwin Shelter | Complete | Mon 5/13/26 | Mon 6/11/26 | Wed 8/12/26 | Mon 9/14/26
27 | 6K State School | Complete | Mon 5/20/26 | Mon 6/18/26 | Wed 8/12/26 | Fri 9/17/26
28 | 7BH Bohemia | Complete | Mon 3/31/26 | Tue 4/21/26 | Wed 8/12/26 | Fri 9/18/26
29 | 7M MacArthur | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/22/26
JMUX Replacement: Private Field Area Network

## Slide 9
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
30 | 8AX Patchogue | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
31 | 8AX Patchogue Shelter | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
32 | 7Z Lindenhurst | Complete | Tue 4/27/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
33 | 7J Sterling | Complete | Mon 3/31/26 | Tue 4/21/26 | Wed 8/26/26 | Mon 9/22/26
34 | 7UM South Farmingdale | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
35 | ACC | Complete | Tue 6/9/26 | Wed 7/8/26 | Tue 9/8/26 | Mon 9/28/26
36 | 6U Ruland | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
JMUX Replacement: Private Field Area Network

## Slide 10
Schedule Status
Overall: 🟡 Yellow | Recovery Plan in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Root Causes:
• SSP documentation delays (security review queue)
• CMDB update coordination time
Recovery Actions:
SPI = 0.78 (Orange).
Phase 1 is – 2.8 months behind.
Overall project is still on schedule since we have IFR/IFCs being completed for Phase 2 and we are working with Hawkeye to complete their site surveys as soon as we get the IFC.
Plan to get to 1.00 – Phase 1
  Complete the Node build in NMS for all nodes in Phase 1
  Complete RTU testing on provided test circuit.
  Work with B&M and confirm MOP for migrating production RTU and start migration.
SCHEDULE PERFORMANCE INDEX (SPI)
0.00
0.50
0.75
1.00
1.25
1.50
2.00
●
Below 0.70 — Critical
●
0.70–0.90 — Yellow
●
0.90–1.10 — On Track
●
Above 1.10 — Ahead
--- April 2026 : 0.77 (Orange)
--- March 2026 : 0.80 (Yellow ↓)
Week | Dates | Planned site (PV) | Actual Sites Completed (EV) | Weekly SPI | Culmative SPI | Key Notes
Work with B&M to access NOKIA NSP | 4/05/2026 | 1 milestone (BGP approval) | 1 (approved ✅) | .70 | 0.78 | Work with B&M and PSEG tech to access equipment
Build Phase 1 nodes into GUI Interface | 4/18/2026 | 1 milestone (BGP approval) | 1 (approved ✅) | 1.00 | 0.79 | All 31 nodes built into NMS GUI. Also tested and verified configuration as per SSP
9 IFCs sent to Hawkeye to start site surveys | 4/20/2026 | 1 milestone (BGP approval) | 1 (approved ✅) | 1.00 | 0.79 | Hawkeye will complete site survey and make a list of what will be required for installation for each site.
Test circuit to test RTU communication with the EMS at Hicksville | 4/18/2026 | 1 milestone (BGP approval) | 1 (approved ✅) | ** | ** | CNI will run test circuit, so we can verify RTU communication at Hicksville, before touching production RTU.
JMUX Replacement: Private Field Area Network

## Slide 11
Financials (2024-2026)
Category | 2024 Actuals | 2025 Actuals | 2026 Actuals | Program Total | % of Program
Internal Labor | $29,357.90 | $181,290.67 | $28,272.39 | $238,920.96 | ~4%
Materials | $601,379.80 | $371,819.58 | $46,040.04 | $1,019,239.42 | ~18%
Outside Services | $103,408.84 | $2,482,742.20 | $1,698,535.37 | $4,284,686.41 | ~76%
Assessments | $7,059.70 | $94,267.21 | $16,970.35 | $118,297.26 | ~2%
TOTAL | $741,206.24 | $3,130,319.66 | $1,789,818.15 | $5,661,344.05 | 100%

## Slide 12
Next Steps & Current Risks
PRJ13797: JMUX Replacement | PSEG Long Island | April 2026
📋 Next Steps
1
Work with B&M to test the RTU circuit that was run by CNI team.
Complete testing on test RTU and work with B&M to go over MOP to move production RTU.
2
3
Follow up with Hawkeye to make sure the site surveys are scheduled for Phase 2 sites. 9/36 IFCs sent to Hawkeye.
4
Track PAR control design and equipment ordered for 6 sites.
5
Keep tracking IFR/IFCs – 9/36 received to date.
⚠️ Current Risks
🟡
Legacy JMUX equipment is over 25 years old and brittle — faulty connectors, potential brittle fiber patch panels, face plates, connectors and cables. Potential for Outage.
🟡
Weather (Heat)
🟡
Potential Schedule delays due to other major substation project conflicts.
PSEG Long Island | JMUX Replacement Program | PRJ13797 | Confidential | April 2026