## URB Request
PRJ13797 — JMUX REPLACEMENT ¦ URB FUNDING REQUEST ¦ May 2026
98 Sites Total — Phase 1: 31 sites ✅ COMPLETE Phase 2: 36 sites 🔵 IN PROGRESS Phase 3: 31 sites ⭕ PENDING
| PHASE 1 | PHASE 2 | PHASE 3 | TOTAL
TOTAL PROJECT COST BY PHASE
Nokia Equipment (routers, SFPs, licenses) | 1412400 | 733293 | 1412400 | 3558093
Cables & Connectors | 241073 | 279956 | 241073 | 762102
Engineering — B&M (design, surveys, staging, CSC) | 1161245 | 1428428 | 1229914 | 3819587
Installation — Hawkeye (staging, install, go-live) | 402793 | 368841 | 744314 | 1515948
PM, Controls & Scheduler | 121360 | 649459 | 116600 | 887419
Internal Labor (PSEG + Cognizant) | 82421 | 436389 | 90000 | 608810
PQA, Assessments, NERC-CIP | 79228 | 142737 | 35000 | 256965
TOTAL PROJECT EAC | 3500520 | 4039103 | 3869301 | 11408924
LESS: APPROVED BUDGET (already authorized)
2024 Actuals (already spent — sunk cost) | 741206 | 0 | 0 | 741206
2025 Approved Capital Budget | 3250000 | 0 | 0 | 3250000
2026 Approved Capital Budget | 0 | 2600000 | 0 | 2600000
TOTAL APPROVED | 3991206 | 2600000 | 0 | 6591206
SCOPE OFFSETS — budget repositioned between phases (nets to $0)
As-Built Drawings deferred to Phase 3 | -79864 | 0 | 79864 | 0
Phase 3 Site Surveys pulled into Phase 2 | 0 | 86000 | -86000 | 0
NET OFFSET IMPACT | -79864 | 86000 | -6136 | 0
PLUS: NEW SCOPE ★ PCR REQUIRED
PAR — Equipment (Iniven RC-30 × 6 sites) | 0 | 52500 | 0 | 52500
PAR — Engineering (200 hrs × 6 × $200/hr) | 0 | 240000 | 0 | 240000
PAR — Installation (~1,298 hrs × $200/hr) | 0 | 259500 | 0 | 259500
PAR — Materials | 0 | 30000 | 0 | 30000
Phase 3 Design Acceleration into Phase 2 | 0 | 800000 | 0 | 800000
TOTAL NEW SCOPE | 0 | 1382000 | 0 | 1382000
★★ NET NEW FUNDING REQUIRED — URB ASK |  |  |  | 1400000