Burns & McDonnell EGS, P.C.

PRJXXXX – Systems Integrator

Statement of Work (SOW)

Tuesday, February-27th, 2024

V-0.03

PSEG and Supplier Confidential

This SOW Template has been approved by PSEG Legal, IT and Procurement.   Changes to the structure or content of this template except where expressly permitted may not be made without written PSEG IT Director approval.   Do not delete any sections.  If any sections are not applicable for the specific work scope, mark them as such, but do not delete them.

Italic blue text is used where you might insert wording about your project.

Italic red text is used for explanatory information that should be removed when the template is used.

Document Change History

| Version Rev | Change Date | Author | Remarks |
| --- | --- | --- | --- |
| .01 | 02/27/2024 | Martin C. Gately | Initial Draft |
| .02 | 3/4/2024 | Alexander R. Lenox | Scope of Work Updates |
| .03 | 3/15/2024 | Martin C. Gately | Updates – for Milestones, payments and closing requirements |

Table of Contents

Terms of the Engagement	4

1.	Overview of the Project and Services	4

1.1	Purpose and Objectives	4

1.2	Requirements and Scope	5

1.3	Dependencies and Constraints	5

1.4	Deliverables	6

1.5	Critical Performance Specification Milestones, Fees and Payments	8

1.6	Plan for escalation mechanism within the project	13

1.7	Risk Management Plan	13

1.8	Project Schedule	14

1.9	Sub-contracted work / Partner Relationships	14

1.10	Resource table	15

1.11	Team Coordination and Communications	16

2.	SOW Governance	16

2.1	Change management	16

2.2	Quality Assurance Plan	16

2.3	transition plan	17

2.4	Closeout Plan	17

2.5	Warranty	17

2.6	Secure coding standards	17

3.	Estimated Support Cost Increase	18

3.1	Estimated Annual Support Cost Increase (TCS SOWs only)	18

4.	Definitions and Acronyms	18

Appendices	18

Appendix A – Activities in scope of this sow – application development and Phase0 Services Waterfall	20

Appendix B – Activities in scope of this sow – Infrastructure Services	23

Appendix C – Activities in scope of this sow - Project Management Services	24

Approval and Authorization of this SOW	25

# Terms of the Engagement

This Statement of Work (“SOW”) entered into by and between COMPANY  Long Island Electric Utility Servco LLC, as agent of and acting on behalf of the Long Island Lighting Company d/b/a LIPA and Burns & McDonnell EGS, P.C. (“SUPPLIER”) as of February, 27th, 2024 (“Effective Date”), is issued pursuant to and governed by the terms and conditions of the MA00007834: Contract for Consulting Services  between Company and Supplier, dated June-1st, 2023 (the “Agreement”). This SOW incorporates the terms of the Agreement herein, as if the terms of the Agreement are set forth below at length.  In the event of a conflict between the terms and conditions of the Agreement and the terms and conditions of this SOW, the terms and conditions of the Agreement shall control.  Capitalized terms used but not defined herein shall have the meanings ascribed to them in the Agreement.

| Customer |  |  |
| --- | --- | --- |
| ### Name | ### Title | ### Contact Details |
| Vikas Vohra | Group Product Manager – IT Infrastructure | Vikas.Vohra@pseg.com |

# Overview of the Project and Services

Please select the work scope type that this template is being used for:

Work Scope Type (select one):

[  ] Application Development Waterfall

[  ] Application Development Phase 0

[  ] Infrastructure Services

[  ] Project Management Services

[  ] Other:

This statement of work between the two parties indicated above is to create a contractual agreement whereby the said vendor – Supplier will abide by the Purpose (Scope) and Objectives below to hire an ‘Equipment Vendor’ via a RFP process and project manage said vendor to replace the current COMPANY private network equipment vendor.

## Purpose and Objectives

- Provide Project Management and Implementation Services to select a Telecommunications equipment network provider to replace the existing private Network we utilize today – GE Jungle Mux (JMUX)

## Requirements and Scope

The Systems Integrator will create, facilitate and execute the process for generating a RFP to then select an ‘Equipment vendor’ who will be used to replace the existing Private Network vendor – GE JungleMUX.  In addition, the Systems Integrator will perform ‘high level’ design activities for the ~ 105 COMPANY substations via ‘site surveys’ to assess what types of specific structural work that is required to accommodate the new equipment.

After the selection of the ‘Equipment Vendor’ the Systems Integrator will then Project Manage and facilitate the implementation process with the newly selected equipment.

Project Requirements and activities In Scope of this SOW

- Conduct COMPANY Site Surveys for the 113 (max) substations to assess possible needs for additional space for new network equipment at each site - Supplier will gather data related to available rack space, wall space, or other locations within each substation control enclosure where the new communication network equipment may be installed. - Supplier will perform visual inspections at each building indoors at floor level. - Digital photos and video will be collected for reference when creating the site survey forms that will be submitted to COMPANY. - Supplier will populate a survey form detailing the rack space, wall space, or equipment location data gathered at each substation. - COMPANY and Supplier will review survey form used to gather substation data prior to substation surveys kick-off. - COMPANY will sign-off on survey form and data being captured. - Supplier will submit the site survey form, at substation survey completion, to COMPANY as final. - COMPANY will provide site escorts to provide site access to the Supplier and partnering persons performing the site surveys. - If panels need to be opened, COMPANY will provide a qualified worker to open the panels. - COMPANY will provide updated building floor plans for substation control buildings that Burns & McDonell will redline as part of the site deliverable. - Perform specific RFP activities to select an ‘Equipment Vendor’ that abides by the COMPANY RFP processes. - Supplier will conduct up to seven (7) 1-hour interviews with the COMPANY telecommunications stakeholders. COMPANY Stakeholders are able to provide information needed for network vendor requirements provided by COMPANY. - Supplier will create a requirements-based network equipment specification with sufficient detail for a qualified vendor to provide a proposal for network equipment. - Produce a ‘high-level’ network design that includes the following preliminary information. - ‘High-level’ network design will include network topology based on the existing network physical topology; including the proposed core network and encompassing all known substations. - Estimated node counts. - Interface counts for application connections. - Network protocol requirements and services. - Network service topologies for point-to-point and multipoint services. - Estimated network capacity requirements per application. - Supplier will submit the draft requirements specification to COMPANY for review and comments. - COMPANY will provide Supplier with review comments within three (3) weeks of the date of submission. - Supplier will host a meeting to review comments or questions from COMPANY. - Supplier will incorporate review feedback and submit the final Network Requirements within two (2) weeks of the conference call. - Supplier will create RFP specifications, RFP to be issued by COMPANY, on PSEG’s PowerAdvocate platform. - Supplier will draft Vendor Scope requirements for COMPANY Review. - COMPANY will provide comment within two (2) weeks of the date of submission. - Supplier will review feedback and submit a final Vendor Sope requirements within two (2) weeks of COMPANY feedback receipt. - Supplier will issue a bid schedule and finalize the schedule based on COMPANY comments. - COMPANY will provide terms and conditions, commercial documents, and any other required COMPANY forms, spreadsheets, etc. as required by COMPANY procurement rules. - Supplier will receive one round of questions from bidders, via COMPANY, and provide answers to the bidders. If any questions require COMPANY input, Supplier will solicit answers from COMPANY and provide responses to COMPANY to be posted in PowerAdvocate. - Supplier will provide a weighted scoring matrix for COMPANY to review and adjust the scoring weights based on feature importance to COMPANY. The scoring categories will be determined by the final equipment specification and ‘high-level’ design. - Supplier will evaluate the final RFP responses and submit a written recommendation to COMPANY indicating which vendor scored the highest based on the weighted score matrix, as well as any additional information based on Supplier experience working with the vendor and/or product. - Equipment vendor selection will be capable of providing MPLS capable hardware for the transport network.

- Project Management work efforts will abide by the COMPANY CMMI project deliverables. - Supplier and COMPANY will complete the equipment vendor RFP process and COMPANY will contract with the network equipment vendor or reseller. - Supplier will host a weekly meeting with the COMPANY selected vendor or reseller to understand status on pre-construction deliverables including low-level design documents, and staging test plan and staging test. - Supplier will be recording meeting minutes during the calls and submitting them for COMPANY review. - Supplier will update the project schedule monthly and submit the updated schedule for COMPANY review. - Supplier will create and maintain a project contact list that includes key stakeholders for both the vendor and COMPANY.

Project Requirements and activities Out of Scope of this SOW

- Any fiber additions/replacements will not be required

- Assumed the low level design for the implementation with the existing fiber will be conducted with the assistance of the newly selected ‘equipment vendor’

## Dependencies and Constraints

| Dependencies |  |  |
| --- | --- | --- |
| Dependency Description | Explanation / Basis for Dependency | Comments or Plan Impact |
| <describe the Dependency items> |  | <describe the impact> |

| Constraints |  |  |
| --- | --- | --- |
| Constraint Description | Explanation / Basis for Constraint | Comments or Plan Impact |
| Company capacity to review and issue RFP in PowerAdvocate | These items are on the critical path and rely on Company to execute | Will delay the project schedule |
| Company capacity to allow site access (escorts) | Personnel with site access needed for site entry for site surveys | Will delay the project schedule if not available prior to going to site. Will have schedule and cost impacts if Contractor arrives on site and arranged escort is unavailable (late cancellation). |

## Deliverables

Deliverables:

The key deliverables developed by the Supplier must be reviewed and accepted by Company with an objective of detecting potential issues early in the project execution process, in order to prevent adverse effects to the project (including, but not limited to, adverse effects to the project schedule and cost of the project).

| Deliverables | Planned Delivery Date | Acceptance Criteria (These deliverables shall have a documented peer review and be reviewed & approved by Company prior to the referenced CPS Milestone. | Company Approver | CPS Reference (1) |
| --- | --- | --- | --- | --- |
| Documentation of the solutions, their configuration and constraints. | 06/04/2024 | Services and substance submitted to Company. | Martin C. Gately/Vikas Vohra | 1 “Network Equipment Requirements and Vendor Scope Specifications to Company” |
| Vendor scope, specifications, and scoring matrix (pre-RFP). | 6/11/2024 | Deliverable submitted to Company as a final version after Company review and comment of Draft. | Martin C. Gately/Vikas Vohra/Ken Buchbinder | 1 “Network Equipment Requirements and Vendor Scope Specifications to Company” |
| Vendor recommendation and scoring matrix documents (post-RFP). | 09/04/2024 | Final deliverable submitted to Company. | Martin C. Gately/Vikas Vohra/Ken Buchbinder | 2 “Vendor Request for Proposal Recommendation to Company” |
| Site survey data submitted to Company | 06/11/2024 | Deliverable submitted to Company. The milestone date is when all survey data has been submitted to Company. | Martin C. Gately/Vikas Vohra | 3 “Substation Site Surveys Complete” |

- All deliverables must be linked to a CPS milestone (Section 1.5.) This means they must complete before or at the related CPS milestone date before the milestone compliance is measured and the subsequent invoice paid.

## Critical Performance Specification Milestones, Fees and Payments

The project will commence on April 1, 2024 with a targeted completion date of December 31, 2026.  The total fixed price for the project is  $306,300.00

Fees must be broken down into the identified CPS milestones and associated acceptance criteria. This includes all deliverables noted in section 1.4 that are linked to the CPS milestones.  Company will NOT pay in advance for services or deliverables or pay fees upon execution of an SOW.  Company will pay for services or deliverables that have been received and approved in accordance with the terms of the Agreement and this SOW. In general, invoicing of travel and business related expenses are not permitted by Company and Supplier must include any such costs in the fixed price for the project.  Company will only reimburse Supplier for its actual and reasonable expense for travel and incidentals that have been preapproved by Company in writing.

SOW Costs - Milestone Payment Allocation for Application Development, Infrastructure Services, and PM Services

Unless specifically approved by the applicable Company Delivery Manager (“Company DM”), all Fixed Fee IT waterfall project SOWs shall follow this milestone payment structure:

| Milestone | Milestone Name |
| --- | --- |
| 1 | Network Equipment Requirements and Vendor Scope Specifications to Company |
| 2 | Construction of the RFP for the ‘Equipment vendor’ |
| 3 | Vendor Request for Proposal Recommendation to Company |
| 4 | Substation Site Surveys Complete |

Company DM may adjust the allocation proportions across the milestones. A minimum of 10% of the total SOW price for the project must be allocated to the Post Warranty payment.

Milestone payment structures for Phase 0 and other IT services SOWs will be determined by Company PM/DM.

Critical Performance Specifications - Milestone Allocation

Company’s Project Manager (“Company PM”) will measure Supplier’s work performance and deliverables against the performance specifications, description of the services/deliverables, performance measurements and acceptance criteria identified in the table below entitled “Critical Performance Specifications Milestones and Dates.” Company’s PM and/or DM, as applicable, shall determine whether the services and deliverables have met performance measurements and acceptance criteria. The table shall have entries for each planned milestone payment. Each and every payment must have a CPS measurement and acceptance criteria defined. The initial setup of the table below is for the minimum CPS criteria (Milestones 1-4). Additional CPS criteria may be added to facilitate interim payments, however all payments must be linked to a CPS measurement with measurement criteria defined by Company.

At the completion of the services and deliverables subject to the applicable milestones and prior to each milestone payment invoice, the Supplier shall request from Company a performance measurement against the specified measurements and acceptance criteria.

Once the request for performance measurement is received, the Company PM shall measure Supplier’s performance to determine if Supplier’s services and deliverables have met the applicable performance measurements and acceptance criteria.

  - If the services and deliverables meet the performance measurements and acceptance criteria, as determined by Company, the Company DM shall notify the Supplier to submit the invoice for the full value.

  - If the services or deliverables do not meet the specified performance measurements or acceptance criteria, the Company DM shall notify the Supplier that the services or deliverables, as applicable, must be corrected or re-performed as necessary and the corresponding invoice shall be reduced by the applicable service credit amount.

SUPPLIER SERVICE CREDITS FOR FAILURE TO MEET MILESTONE COMMITMENT DATES

Supplier agrees and acknowledges that Supplier’s timely performance of the services, provision of the deliverables and completion of each project milestone by the applicable CSP milestone commitment date (as set forth in the table below) is of critical importance to Company and the success of the project contemplated by this SOW.   Supplier further agrees and acknowledges that if Supplier fails to meet a CSP milestone commitment date, Company shall incur certain costs and damages.  In the event Supplier fails to meet a CSP milestone commitment due to a delay caused solely by Supplier, Supplier shall pay to Company the applicable service credit amount set forth in the table below.

Company shall deduct any service credits amounts from payments due to Supplier hereunder.  Any service credits provided hereunder shall constitute Company’s sole and exclusive remedy for delays in completion of each Milestone.

| CRITICAL PERFORMANCE SPECIFICATION MILESTONES AND DATES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Milestone / Payment # | Performance Specification | Description of Services/Deliverables to be Provided and Performance Measurements | Acceptance Criteria | Milestone Commitment Date (1) | Service Credits | Milestone Payment Amount |
| 1 | Network Equipment Specifications and Vendor Scope Requirements | Supplier will create a requirements-based network equipment specification document based on the data gathered from the stakeholder interviews. This will be a technical specification with sufficient detail for a qualified vendor to provide a proposal for network equipment. | Document completed in form and substance submitted to Company by the Milestone Commitment Date | 6/11/2024 | 5% of milestone payment for delay > 5 business days | $36,250.00 |
| 2 | Vendor Request for Proposal – Vendor Recommendation | Supplier will issue a Request for Proposal (‘RFP’) event to up to four (4) potential vendors that meet the vendor scope requirements and network equipment specifications. The RFP will be issued out of PowerAdvocate (by Company) and Supplier will issue a weighted scoring matrix and written recommendation to the Company based on the final technical requirements. The Mile | Document and services completed in form and substance submitted to Company by the Milestone Commitment Date | 9/4/2024 | 5% of milestone payment for delay > 5 business days | $16,250.00 |
| 3 | Substation Site Surveys | Supplier will gather data related to available rack space, wall space, or other locations within each substation control enclosure where the new communication network equipment may be installed. Sites will be submitted in batches, however the milestone shall be based on submittal to Company of all site survey data. | Final deliverable submitted to Company by the Milestone Commitment Date | 6/14/2024 | 5% of milestone payment for delay > 5 business days | $99,800.00 |
| 4 | Project Management Services | Supplier will host meetings, record meeting minutes, and maintain the project schedule for the Company’s selected vendor. Supplier will report vendor milestone progress, as agreed upon between Vendor and Company, in accordance to Company defined deliverable process. Assumption: Company’s selected vendor will adhere to coordinated project schedule. - Project Status Report (100%) | PM performance must measure (average) A or B. See note 3 below | 9/01/2024-12/31/2026 | N/A | $5,500 a month for 28 months. Total: $154,000.00 |
| Notes and Definitions: 1: Includes date changes as updated per approved Project Change Request (PCR) provided the PCR change is approved prior to the currently approved milestone date 2: Severity Level 1: Errors that (i) cause the services or deliverables to cease operating or cease operating in any material respect, as determined by Company; (ii) affecting essential functions for which no workaround exists, as determined by Company; or (iii) cause a loss or data or permit unauthorized access to data, as determined by Company. Example: Unsuccessful installation, complete failure of a feature. Severity Level 2: Errors that (i) disable essential functions but for which a workaround exist (provided that the workaround is obvious and does not require significant time or effort to implement), as determined by Company; (ii) violate material specifications or adversely affect material functions applicable to the services or deliverables, as determined by Company; or (iii) result in inconsistencies in reported data, as determined by Company. Example: A feature is not functional from one module but the task is doable if other complicated or time consuming indirect steps are followed in another module/s. Severity Level 3: Non-critical errors that disable only nonessential functions identified in the applicable specifications or documentation, as determined by Company. 3. The rating scale for PM performance, as calculated by Company, is: Rating Range (% Compliant) A 85% - 100% B 75% - 84% C 65% - 74% N 0% - 64% Company shall determine the project measurements and project measurement criteria applicable to each project. Company may determine that not all 7 categories referenced above apply to a particular project. The PM score will be based upon the number of compliant categories (from the 4, as determined by Company) divided by the number of categories measured by Company over the applicable milestone period. The milestone period is the period between the start of the milestone and the milestone completion date, as determined by Company. For example, if Company determines that the milestone phase of design (CPS 1) for a project is 3 months and during these three months that PM will be measured on 3 items in month 1, 4 items in month 2 and 3 items in month 3, the PM will be measured on 10 items in total. Of the 10 items, if the PM was non-compliant, as determined by Company, in 3 categories, the PM would receive a 70% compliant rating (determined by dividing 7 by 10, for an average rating of 70% complaint). The PM would receive a “C” rating of for this project, causing the PM to miss the required A or B rating and resulting in a service credit being owed by the PM to Company, as set forth in the table above. 4. For SOWs with total cost less the $20,000, the minimum credit for this milestone payment is $5,000 5. For SOWs with total cost less the $20,000, the minimum credit for this milestone payment is $10,000 |  |  |  |  | Total | $306,300.00 |

## Plan for escalation mechanism within the project

The following escalation procedure will be followed if the Company determines that resolution is required for a project schedule delay that arises during the performance of this SOW or other issues pertaining to Supplier’s performance. When a delay or issue arises, Supplier and Company’s project team members shall strive to resolve the problem or defect causing the delay or other project-related issues. The following steps would be followed in the event the defect, delay or issue is not resolved with 2 days following the occurrence of any such defect, delay or issue:

- Level 1 Escalation: If the project team cannot resolve the delay or issue within two (2) business days, Supplier’s  Project Manager/PM Supervisor  (Alex Lenox, Project Coordinator, alenox@burnsmcd.com, (636) 248-0351 and Dan Bayouth, Project Advisor, dbayouth@burnsmcd.com, (865) 229-6884) and Company PM/DM will meet to discuss the delay or issue and resolution steps. Company’s PM and DM (Martin C. Gately, Senior Principal Technology Consultant , Martin.Gately@pseg.com, 516-353-3991/Group Product Manager, Vikas Vohra, Vikas.Vohra@pseg.com, 917-587-7373) will engage the right resource to help resolve the issue.

- Level 2 Escalation: If the delay or issue is not resolved within three (3) business days after the Level 1 Escalation, Supplier’s Executive Sponsor (Director or higher) (Andrew Jarvis, President, ajarvis@burnsmcd.com, (913) 558-0376) will meet with the Company Director (Irving Landesbaum, Director Infrastructure Project Office, Irving Landesbaum@pseg.com, 516-207-3412) to address the issue and discuss steps taken and a resolution plan.

- Level 3 Escalation: If the delay or issue is not resolved within three (3) business days after the Level 2 Escalation, Supplier’s Senior Vice President (Andrew Jarvis, President, ajarvis@burnsmcd.com, (913) 558-0376) will meet with the PSEG CIO (Greg Filiplowski, Mgr Director & CIO, Gregory.Filipkowski@pseg.com, 614-715-6104) to address the issue and discuss steps taken and a resolution plan.

## Risk Management Plan

Describe the risks to the deliverables, the probability, potential impacts and how these may be mitigated. Risk factors that should be considered when identifying the specific project risks include contractual risks, organization-related risks, technological risks, risks due to size and complexity of the project, risks in personnel acquisition and retention, risks in achieving Company acceptance of the product, and others specific to the context of the project.

| Risk | Probability | Impact | Mitigation Actions |
| --- | --- | --- | --- |
| Delayed comments from COMPANY on design documents | Low | Time | Expedite revision if possible |
| Delayed reviews of the RFP specifications | Low | Time | Expedite revision if possible |
| Delayed issue of the RFP issuance | Low | Time | Expedite revision if possible |
| Denied entry into substations due to weather, construction, lack of escort, or other conditions | Medium | Time and cost | Verify before mobilizing for the week, change site plan if specific sites are inaccessible |

## Project Schedule

Project Schedule durations are noted in business days. The Project Schedule shall incorporate all COMPANY and Supplier Holidays. COMPANY to provide holidays to be incorporated.

| Task Name | Duration | Start | Finish |
| --- | --- | --- | --- |
| PSEG Long Island System Integrator | 719 days | Mon 4/1/24 | Thu 12/31/26 |
| Project Kickoff | 0 days | Mon 4/1/24 | Mon 4/1/24 |
| System Integrator | 719 days | Mon 4/1/24 | Thu 12/31/26 |
| Site Surveys | 52 days | Mon 4/1/24 | Tue 6/11/24 |
| Supplier and COMPANY Review Substation Survey Data Form | 5 days | Mon 4/1/24 | Fri 4/5/24 |
| COMPANY Accepts Final Survey Data Form | 2 days | Mon 4/8/24 | Tue 4/9/24 |
| Site Surveys | 35 days | Wed 4/10/24 | Tue 5/28/24 |
| Supplier Submits Final Survey Data Forms | 10 days | Wed 5/29/24 | Tue 6/11/24 |
| Vendor Selection - RFP | 714 days | Mon 4/8/24 | Thu 12/31/26 |
| Network Requirements | 42 days | Mon 4/8/24 | Tue 6/4/24 |
| Stakeholder Interviews | 2 days | Mon 4/8/24 | Tue 4/9/24 |
| Issue draft Network Requirements Specification for COMPANY review | 15 days | Wed 4/10/24 | Tue 4/30/24 |
| COMPANY provides review comments for draft Network Requirements Specification | 15 days | Wed 5/1/24 | Tue 5/21/24 |
| Supplier Issues final Network Requirements Specification to COMPANY | 10 days | Wed 5/22/24 | Tue 6/4/24 |
| Vendor Scope Requirements | 35 days | Wed 4/24/24 | Tue 6/11/24 |
| Supplier Issues draft Vendor Scope Requirements for COMPANY review | 15 days | Wed 4/24/24 | Tue 5/14/24 |
| COMPANY review comments for draft Vendor Scope Requirements | 10 days | Wed 5/15/24 | Tue 5/28/24 |
| Issue final Vendor Scope Requirements to COMPANY | 10 days | Wed 5/29/24 | Tue 6/11/24 |
| Vendor RFP | 76 days | Wed 6/12/24 | Wed 9/25/24 |
| Supplier Develops and Executes Vendor RFP | 12 wks | Wed 6/12/24 | Tue 9/3/24 |
| Supplier Provides Recommended Vendor for COMPANY | 1 day | Wed 9/4/24 | Wed 9/4/24 |
| COMPANY selects Vendor | 3 wks | Thu 9/5/24 | Wed 9/25/24 |
| Vendor Project Management | 601 days | Thu 9/12/24 | Thu 12/31/26 |
| Vendor Project Management | 601 days | Thu 9/12/24 | Thu 12/31/26 |

## Sub-contracted work / Partner Relationships

Supplier shall engage no contractors, subcontractors or agents to perform the services or deliverables without Company’s prior written consent.

Description of approved subcontracted services/deliverables and name of applicable subcontractors:

Supplier will be subcontracting a portion of the station survey work, as detailed in section 1.2, to Global One Partners, LLC, a WMBE. Global One Partners, LLC will be accompanying Supplier personnel on up to 125 station surveys. The work, as detailed in section 1.2, will include gathering data related to available rack space, wall space, or other locations within each substation control enclosure where the new communication network equipment may be installed.

Global One Partners, LLC will report to the Supplier Project Coordinator.

## Resource table

Supplier Resource Table

| Resource Name | Resource Title | Job Description | Start Date | End Date | Effort In Hrs. | Hourly Rate | Cost (Rate*Hrs.) | Work Location |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Andrew Jarvis, PE | President | Executive Sponsor, Escalation Contact | 4/1/2024 | 12/31/2026 |  | N/Av | N/A | Kansas City, Missouri |
| Dan Bayouth | Project Advisor | Advisor for scope defined in section 1.2 | 4/1/2024 | 12/31/2026 |  | N/A | N/A | Kansas City, Missouri |
| Alex Lenox | Project Coordinator | Project coordinator managing the scope, schedule, forecasting, communication and project delivery. | 4/1/2024 | 12/31/2026 |  | N/A | N/A | Kansas City, Missouri |
| Ethan Koch, PE | Network Engineer | Network Engineer executing on site surveys, network requirements development, vendor specification development, and vendor recommendation. | 4/1/2024 | 12/31/2026 |  | N/A | N/A | Kansas City, Missouri |
| Dustin Williams | Network Designer | Network designer providing technical oversight and quality management to the Network Engineer on network topology, high-level design, and vendor low-level design review. | 4/1/2024 | 12/31/2026 |  | N/A | N/A | Kansas City, Missouri |
| Total Cost |  |  |  |  |  |  |  |  |

Note : For TCS AD SOWs Job Description and Hourly Rate should be from the AD&S App J Rate Card, or  Infrastructure Management Service Schedule 5 rate card.

Note : For Project Management Services, Supplier shall provide a Project Manager (PM) to Company in a managed services resource model, typically managing  multiple projects. The individual should be on-boarded by Supplier and have completed all required training.

Company Resource Table

Identify the Company resources required to support this SOW.

| Company Resource Title | Job Description | Start Date | End Date |
| --- | --- | --- | --- |
| Martin C. Gately | Infrastructure Principal Project Manager | April-1st-2024 |  |
| Vikas Vohra | Infrastructure Group Product Manager | April-1st-2024 |  |
| Irving Landesbaum | Infrastructure Group Director | April-1st-2024 |  |
|  | <definition in the context of this SOW> |  |  |
|  | <definition in the context of this SOW> |  |  |

## Team Coordination and Communications

Describe the methods to be used for regular coordination and collaboration.  Include information as appropriate on items such as standard team meetings, decision-making processes, and team member status reporting.

Supplier will host weekly meetings with Company and/or future Vendor via Microsoft Teams or Zoom calls. Supplier will record meetings minutes during the call, including detailed action items, and will submit to Company in a designated document sharing platform. Document sharing platform and process will be defined by Company.

Supplier will update project schedule monthly and submit the updated schedule to Company for review. Supplier will create and maintain a project contact list that includes key stakeholders for Company, Supplier, and Vendor.

# SOW Governance

## Change management

Changes to this SOW will be handled in accordance with change management or change order requirements set forth in the Agreement.

## Quality Assurance Plan

Supplier will follow Supplier’s established, ISO 9001:2015 certified quality management system. This includes the deliverable review process:

Q3 – Deliverable Review

The Q3 is a design assessment of deliverables (such as drawings, specifications, and models) for

compliance with project requirements and is performed at distinct milestones of the life of the project.

For multi-discipline projects, Q3 Reviewers may also include team members from other disciplines.

Multiple Q3 Reviews are typically completed on projects, one for each distinct design output type.

Q4 – Independent Deliverable Review

Performed by either a reviewer independent from the development of the output or the sealing

licensed professional, Q4 Reviews are verification that design output is complete, accurate, consistent

with project requirements and ready for use. Multiple Q4 Reviews are typically completed on projects,

one for each distinct design output type.

Once a Q4 Review is performed, feedback resulting from the review will be returned to the project

team to address comments and make updates as required. This allows the project team to understand

discrepancies and fosters continual learning and improvement.

### Process Compliance Reviews

Process Compliance Reviews of a project are randomly performed by Company Quality Assurance team. The services deliverables in this Statement of Work are subject to Company process compliance reviews. Supplier shall follow all Company processes while producing the services and deliverables, as applicable.

### Peer Reviews

Key deliverables developed by the Supplier / Vendor shall be peer reviewed by the vendor with an objective of detecting issues early in the execution of the contract, in order to prevent their ill effects/ adverse effects on the project.

## transition plan

Describe the deliverables/tools to be transitioned to Company or the support vendor.  Identify the relevant stakeholders (such as business, IT, vendor, and support vendor) who will be responsible for performing the transition and how it will be done (e.g. training sessions, knowledge transfer sessions, etc.).

| Deliverables / Tools to be transitioned | Transition From | Transition To | Transition Method | Criteria for Completion |
| --- | --- | --- | --- | --- |
| <identify the deliverables and tools that need to be transitioned> | <who will provide the transition> | <who will receive the transition> | <how will the transition be provided i.e. meetings, trainings> | <what is the criteria for completion of transition> |

## Closeout Plan

Ensure that all of the milestones above are successfully completed and approved by PSEGLI.

| Closeout Activities | Performed By Whom |
| --- | --- |
| Network Equipment Requirements and Vendor Scope Specifications to Company | PSEGLI |
| Construction of the RFP for the ‘Equipment vendor’ | PSEGLI |
| Vendor Request for Proposal Recommendation to Company | PSEGLI |
| Substation Site Surveys Complete | PSEGLI |

## Warranty

For the purposes of this SOW, the warranty period  for all deliverables provided hereunder shall commence on the day immediately following the date on which the last deliverable provided by Supplier to Company and continue for ninety (90) days from such date (the “Warranty Period”).  Supplier project resources utilized to complete the services outlined in this SOW will be available to assist in the resolution of defects and issues during the Warranty Period as may be further specified in the Agreement.

## Secure coding standards

# Estimated Support Cost Increase

# Definitions and Acronyms

Define all terms and acronyms required to properly interpret this plan.

| Term | Definition |
| --- | --- |

| Acronym | Meaning |
| --- | --- |
| PPQA |  |
| CMMI |  |
| RFP | Request for Proposal |

# Appendices

| Appendix | Title | Location or Link |
| --- | --- | --- |
| A | Activities in Scope of this SOW - Application Development Waterfall | Below |
| B | Activities in Scope of this SOW -Infrastructure Hardware Services | Below |
| C | Activities in Scope of this SOW -Project Management Services | Below |
| D | Substation Survey List | Below |
| E | <<title>> | <<where is it located>> |

# Appendix A – Activities in scope of this sow – application development and Phase0 Services Waterfall

The following activities as noted “Y” are within the Supplier work scope of this SOW.  For a Phase 0 SOW, the first 8 tasks are typically applicable.

All templates should be taken from Company’s Document Repository, and all testing information should be in Company’s test management application.

.

| In Scope (Yes/No) | Work Task Description |  |
| --- | --- | --- |
| Y | Document business rules / requirements |
| Y | Develop and document detailed functional and technical requirements |
| Y | Conduct Joint Application Design Sessions to determine / validate functional and technical requirements |
| Y | Complete Requirements and Testing documents |
| Y | Conduct assessments of functional requirements and generate an impact analysis, including affected systems, alternative design scenarios, etc. |
|  | Develop application test strategy (e.g. unit, functional, integration, stress, regression, performance, and user acceptance test as applicable) |
|  | Complete/update Estimation Worksheet |
|  | Provide high level logical data model |
|  | Develop prototype to demonstrate support of requirements |
|  | Create the detailed design document from the Business, Functional and Technical Requirements and high-level design that specifies all components, program modules, data stores, interfaces, interface components and associated operations procedures for the application |
|  | Create design to contain security features in compliance with Company policies, including external and Company role based security models |
|  | Complete Functional Design Specification document |
|  | Document technical design, logical and physical data models and complete the Technical Specification Document |
|  | Define implementation and deployment procedures and project schedules to meet deployment and delivery requirements |
|  | Ensure compliance with all technical standards/design standards (e.g. naming, script, etc.) |
|  | Track design changes and make updates until final design approval |
|  | Perform all necessary technical design, programming, development, unit and string testing, scripting, configuring or customizing of application modules as required to develop and implement the design plans and specifications |
|  | Recommend modifications and performance-enhancement adjustments to Company system software and utilities |
|  | Manage all programming and development efforts using industry-standard project management tools and methodologies |
|  | Develop and execute unit test cases for programming and development efforts |
|  | Provide Supplier’s unit test results with Company |
|  | Upload unit test results to Company’s Quality Center (if Supplier does not have access to the tool, this can be done by Company) |
|  | Develop the test plan & strategy for UAT testing |
|  | Develop the test plan & strategy for System Integration Testing (SIT) testing |
|  | Develop the test plan & strategy for Performance / Load testing |
|  | Providing the strategy(s) / plan(s) for review and approval by the project team and key business stakeholders |
|  | Ensure all requirements are entered and maintained in company application |
|  | Ensure all test cases are entered and maintained in company application |
|  | Ensure all UAT test labs/test suites (One for Supplier Execution, and one for Business UAT) for testing execution of the test strategy are entered and maintained in company application |
|  | Creation of SIT test labs/test suites for testing execution of the SIT test strategy in company application |
|  | Creation of Performance / Load test labs/test suites for testing execution of the Performance / Load test strategy in company application |
|  | Execution of one full UAT test lab/test suite including defect closeout prior to sending the solution to the business for business testing (UAT) in company application |
|  | Facilitation of business testing (UAT) and approval by the business |
|  | Execution of <X> System Integration Test (SIT) cycles & associated test lab including defect closeout per project testing strategy & schedule |
|  | Execution of <X> Performance / Load Test cycles & associated test lab including defect closeout per project testing strategy & schedule |
|  | Resolution of associated test defects documented in company application |
|  | Manage the functional, integration, and regression test environments and associated test data including creation and maintenance during the testing period |
|  | Review testing results for compliance with policies, procedures, plans, and test criteria and metrics (e.g. defect rates, progress against schedule, etc.) |
|  | Analyze test results (testing, defects) and identify improvements |
|  | Provide <X> automated test scripts for future regressions tests |
|  | Execute <X> automated test scripts |
|  | Stage systems before implementation where applicable |
|  | Develop migration strategy |
|  | Perform data migration from existing systems to new systems, by electronic methods |
|  | Deliver user policies and procedures documentation |
|  | Conduct pre-installation site surveys |
|  | Implement local adaptations to technical architecture or services provided |
|  | Install new or enhanced hardware items, components, peripherals, or configuration and system management tools to operate with the support application environment |
|  | Conduct pre-installation site surveys, including validation of site-specific functionality as defined in the Requirements Document(s) |
|  | Production Acceptance and Change Management Activities |
|  | Assist in support, implementation and deployment of the application |
|  | Coordinate deployment and support activities |
|  | Perform data migration from existing systems to new systems |
|  | Support post implementation user acceptance |
|  | Provide system and user documentation |
|  | Create detailed “technical go-live” plan |
|  | Create “go/no-go” checklist including test results and conduct the “go/no-go” meetings |
|  | Deploy system |
|  | Participate in environment setup & decommissioning for new and changed environments |
|  | Correct defects during warranty period |
|  | Develop and maintain a configuration management plan |
|  | Perform configuration management activities throughout the development life cycle |
|  | Develop training and knowledge transfer plan in the project plan |
|  | Provide technical training assistance and knowledge transfer |
|  | Provide End-User training content for Company applications |
|  | Provide Help desk agent training, including developing dialogue scripts |
|  | Develop / update Runbook |
|  | Provide operational processing flow |
|  | Provide system installation, support, configuration and tuning manuals |
|  | Provide application hardware and system software requirements documentation |
|  | Provide system and application security procedures |
|  | Provide standard operating procedures |
|  | Provide documented application disaster recovery process |
|  | All other application development activities required by the Company PDLC process, excluding project management |
|  | <list the Project Activities in scope> |
|  | <list the Project Activities in scope> |

# Appendix B – Activities in scope of this sow – Infrastructure Services

The following activities as noted “Y” are within the Supplier work scope of this SOW.   All templates should be taken from Company’s Document Repository, and all testing information should be in Company’s test management application.

.

| In Scope (Yes/No) | Work Task Description |  |
| --- | --- | --- |
|  | Project Plan/ Schedule creation (for Supplier managed deliveries) |
| Y | Weekly status reporting |
|  | Issues Log |
|  | Provide inputs to Project Management Plan / Schedule for Supplier managed deliverables |
|  | Perform project estimation |
|  | Identify possible product and software tool enhancement opportunities for improved performance, stability, and potential cost savings |
| Y | Perform site walk-through for space, racks, power, cabling, Verizon escorting, etc. |
|  | Define localization, deployment criteria and delivery requirements (i.e. laws/regulations) |
|  | Document detailed technical requirements |
|  | Develop overall project/program cost and schedule estimate |
|  | Create the detailed design document from the Business, Functional and Technical Requirements and high-level design |
|  | Attend Infrastructure Design Review and obtain approval |
|  | Develop Infrastructure Production Acceptance |
|  | Create Change Management tickets |
|  | Perform Peer Reviews |
|  | Attend Change Management meeting to obtain approval on change ticket |
|  | Coordinate outage with site contact and IT |
|  | Contact Electric Division Office(s) and schedule Travelling Operator(s) |
|  | Complete Fossil Work Form and obtain outage approval from Electric Systems Operations Center (ESOC) and Energy Resources and Trading (ER&T) |
|  | Contact ESOC prior to the outage |
|  | Obtain access to the site |
|  | Install cabling, router, switches, wireless devices, etc. |
|  | Escort Verizon for circuit installation, activation, etc. |
|  | Coordinate deployment and support activities with Company’s parties as directed by the Company project manager |
|  | Review and approve implementation, deployment procedures, schedules and deployment staffing levels |
|  | <list the Project Activities in scope> |
|  | <list the Project Activities in scope> |

# Appendix C – Activities in scope of this sow - Project Management Services

The following activities as noted “Y” are within the Supplier work scope of this SOW.  All templates should be taken from Company’s Document Repository, and all testing information should be in Company’s test management application.

| In Scope (Yes/No) | Work Task Description |  |
| --- | --- | --- |
| Y | Manage projects in accordance with Company PDLC processes. |
|  | Ensure projects are delivered on time, on budget, with near zero production defects and with high client satisfaction. |
|  | Ensure all project deliverables are developed, reviewed, peer reviewed, verified, approved and stored per applicable procedures |
|  | Project Tailoring Matrices |
|  | Project Estimates |
|  | Project Work Plans (Schedules) and WBS structure |
|  | Monthly project budget forecasting and variance analysis |
|  | Risks and Issues Management |
|  | Funding Release(s) |
|  | Project Change Request(s) - if needed |
| Y | RFP(s) / RFQ(s) |
|  | Purchase requisitions and Service entries |
|  | Product and Project Quality Assurance requirements, audits and compliance |
|  | Production Acceptance Activities and Approvals |
| Y | Meeting minutes for all key meetings |
|  | Maintaining all project data in Company project/portfolio management application |
|  | Ensuring all testing activities/results in Company test management application |
|  | Ensuring knowledge transfer from development to support |
|  | Conduct/support checkpoints (Plan/Analysis, Application Design Review, Test Readiness, Production Acceptance, Post Implementation, etc.). |
|  | Conduct and Track Risks |
|  | Establish and Track Issues |
| Y | Manage all activities. |
|  | Prepare required documentation for obtaining SAP Transport Approval Request and Change Committee Approvals. Obtain mentioned approvals. |
|  | Manage implementation |
|  | Manage resolution of post implementation defects |
|  | Conduct Lessons Learned sessions by project phase. |
|  | Provide weekly status report to DM. |
|  | Steering Committee presentations. |
|  | All other required PDLC project management activities and deliverables. |
|  | <list the Project Activities in scope> |
|  | <list the Project Activities in scope> |

# Approval and Authorization of this SOW

| Company Check the applicable box: [ ] PSEG Service Corporation [ ] Long Island Electric Utility Servco LLC as agent of and acting on behalf of the Long Island Lighting Company D/B/A LIPA |  | Supplier Burns and McDonnell EGS, P.C. |
| --- | --- | --- |
| Signature |  | Signature |
| Full Name |  | Full Name |
| Title |  | Title |
| Date |  | Date |
| Purchase Order Number |  |  |

Unless specifically approved by the PSEG DM, all SOWs shall be fixed priced.  If this project will involve a different pricing structure (e.g. time and materials), this section must be revised.

Escalation contacts will be conformed to reflect Supplier’s corporate structure.