## Slide 1: PRJ13797: JMUX Replacement Update Project Manager : Dhananjaya Gunaratne
April 2026

## Slide 2
JMUX Replacement: Private Field Area Network
Modernize PSEG LI’s substation communications by replacing legacy JMUX with MPLS nodes to deliver a reliable, scalable and future-ready network.
Objectives
  Engineering Services (Burns & McDonnell)
    Site surveys, rack elevations, power & cabling design
    Node Design – Produce IFR, IFC and As-Built documents
Procurement & Staging (Burns & McDonnell, Nokia, Graybar)
    Bill of Materials creation, MPLS Equipment order, Power and ancillary equipment(Patch panels, Fiber cables, mounting kits, etc.)
Construction and Installation Support (Burns & McDonnell, Hawkeye)
    BMcD to provide on-site coordination with engineering team, technical support and commissioning oversight.
    Hawkeye to assist with shipment, racking, stacking, and power during staging. Perform site surveys for construction support. Install all equipment per the approved IFC documents
    Install fiber and copper cabling per the construction documents.
    Deployment and Application Migration (PSEG, Burns & McDonnell)
    Design and configure Layer 3 networks
    Pre-stage the application connectivity
    Migrate production applications
SCOPE | SUBSTATIONS | MPLS SITES | DF RTU SITES | RADIO SHELTER SITES | NOKIA MPLS NODES
PHASE 1 | 49 | 26 | 17 | 6 | 31
PHASE 2 | 45 | 26 | 12 | 7 | 26
PHASE 3 | 35 | 22 | 7 | 6 | 22
TOTAL SCOPE | 129 | 74 | 36 | 19 | 79
Goal & Objectives

## Slide 3
✅ Phase 1 — BGP Configuration Complete
BGP design approved by Vikas Vohra (3/16). Change implemented at Hicksville and Melville (4/1–4/2).
✅ NSP Installation at Hicksville — Complete
Fiber cabling pulled, terminated, and wired. NSP appliance stood up 4/10.
✅ Remote Connectivity Established — Complete
Corporate integration of Nokia MPLS at Hicksville and Melville completed 4/7.
✅ Phase 2 Site Surveys — 100% Complete
All 36 Phase 2 substation site surveys completed. IFR/IFC schedule confirmed.
✅ Northport DC Power — Complete
DC power installed and operational at Northport (3/18). Router fully operational.
✅ Phase 2 Equipment Staged
All Phase 2 Nokia equipment moved to new Hawkeye staging trailer. Material delivery per order form confirmed complete.
✅ OTDR Testing — Complete
Hicksville–Syosset link confirmed active. Bad CWDM filter replaced. Crown Castle issue resolved.
✅ Phase 2 IFR Packages — In Progress
First packages (Far Rockaway, Valley Stream, Cedarhurst) IFR/IFC complete. Next batch: Sterling & Whiteside — IFR due 4/13.
Highlight Project Accomplishments
JMUX Replacement: Private Field Area Network

## Slide 4
Phase 2 Engineering Schedule — 36 Sites
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Survey | IFR | IFC | Construction | Deployment
1 | 7RM Bayport | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
2 | 7R Sayville | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/23/26
3 | 7XM Great River | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
4 | 7XM Great River Radio Shelter | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
5 | 6H Hauppauge | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
6 | 6H Hauppauge Tower | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
7 | 6S Kings Hwy | Complete | Mon 3/31/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
8 | Brentwood DO | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 9/2/26 | Fri 9/25/26
9 | 7H Babylon | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Mon 9/21/26
10 | 7H Babylon Radio Shelter | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Tue 9/22/26
11 | 7D West Babylon | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/12/26 | Mon 9/21/26
12 | 7D West Babylon Radio Shelter | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/19/26 | Mon 9/21/26
13 | 7W Berry St | Complete | Mon 3/31/26 | Tue 6/23/26 | Wed 8/19/26 | Mon 9/23/26
14 | 3J Whiteside | Complete | Mon 4/13/26 | Mon 5/4/26 | Wed 8/12/26 | Mon 9/14/26
15 | 2K Valley Stream | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
JMUX Replacement: Private Field Area Network

## Slide 5
Phase 2 Engineering Schedule — 36 Sites
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
16 | 2RB Green Acres | Complete | Mon 3/31/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
17 | Hewlett DO | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Fri 9/25/26
18 | 2ZB EF Barrett PS Inside | Complete | Mon 3/23/26 | Mon 4/20/26 | Wed 8/5/26 | Mon 9/14/26
19 | 2WB Barrett Outside | Complete | Mon 3/23/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
20 | 5HK Hicksville | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
21 | 2H Far Rockaway | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
22 | 2KB Cedarhurst | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
23 | 2R Hewlett | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
24 | 2R Hewlett Shelter | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
25 | 4M Baldwin | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
26 | 4M1 Baldwin Shelter | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
27 | 6K State School | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Fri 9/17/26
28 | 7BH Bohemia | Complete | Mon 3/31/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
29 | 7M MacArthur | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/22/26
JMUX Replacement: Private Field Area Network

## Slide 6
Phase 2 Engineering Schedule — 36 Sites
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
30 | 8AX Patchogue | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
31 | 8AX Patchogue Shelter | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
32 | 7Z Lindenhurst | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
33 | 7J Sterling | Complete | Mon 3/31/26 | Tue 6/9/26 | Wed 8/26/26 | Mon 9/22/26
34 | 7UM South Farmingdale | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
35 | ACC | Complete | Tue 6/9/26 | Wed 7/8/26 | Tue 9/8/26 | Mon 9/28/26
36 | 6U Ruland | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
JMUX Replacement: Private Field Area Network

## Slide 7
Schedule Status
Overall: 🟡 Yellow | Recovery Plan in Place
PSEG Long Island | JMUX Replacement Program | Confidential | April 2026
Root Causes:
• SSP documentation delays (security review queue)
• CMDB update coordination time
Recovery Actions:
SPI = 0.80 (Yellow) — Recovery Plan Active
✅ BGP configuration complete at Hicksville & Melville
✅ Remote connectivity established (4/7)
✅ NSP stood up at Hicksville (4/10)
🔄 Nokia Training — dates to be confirmed with Glenn/Nokia
🔄 RTU Serial Testing at Hicksville QA — to be scheduled
🔄 Phase 2 IFR packages in progress (next: Sterling & Whiteside — 4/13)
SCHEDULE PERFORMANCE INDEX (SPI)
0.00
0.50
0.75
1.00
1.25
1.50
2.00
●
Below 0.70 — Critical
●
0.70–0.90 — Yellow
●
0.90–1.10 — On Track
●
Above 1.10 — Ahead
--- February 2026 : 0.75 (Orange)
╌╌ January 2026 : 1.00 (Gray)
--- March 2026 : 0.80 (Yellow ↓)
Week | Dates | Planned site (PV) | Actual Sites Completed (EV) | Weekly SPI | Cumulative SPI | Key Notes
iLO corporate connectivity interfaces turned up at Melville and Hicksville | 2/26/2026 | 1 milestone (DC power complete) | 1 (DC power complete) | 1.00 | 0.76 | Northport fuse tripping — ILO work blocked. DC power issue resolved
Layer 3 (BGP) network design and configurations | 3/9/2026 | 1 milestone (OTDR confirm) | 1 (OTDR complete ✅) | 1.00 | 0.77 | OTDR confirmed bad filter at Hicksville. Link now active. Crown Castle issue cleared. ✅
Remote access to NSP for Nokia Network Configurations & Management | 3/10/2026 | 1 milestone (NSP fiber term) | 1 (complete ✅) | 1.00 | 0.78 | Fiber run to NSP completed & terminated at Hicksville by Hawkeye. ✅
BGP design approved | 3/16/2026 | 1 milestone (BGP approval) | 1 (approved ✅) | 1.00 | 0.80 | BGP design formally approved. Lee to begin change docs for Hicksville & Melville. ✅
Moved all equipment to new Hawkeye trailer for future staging . | 3/10/2026 | 0 (logistics task) | 1 (complete ✅) | 1.00 | 0.80 | Phase 2 Nokia equipment moved to new Hawkeye staging trailer. Not on critical path.
JMUX Replacement: Private Field Area Network

## Slide 8
Financials (2024-2026)
JMUX Replacement: Private Field Area Network
PROJECT FINANCIAL SUMMARY — As of March 11, 2026
Total Capital Budget: $6,600,000 | Spend to Date: $4,722,381 | Remaining Budget: $1,877,619
Estimate to Complete: $2,545,728 | Estimate at Completion: $7,268,109
⚠️ Projected Total Variance: -$668,109 (-10.1%)
⚠️ Projected 2026 Capital Variance: -$796,783 (-31%)
2026 APPROVED CAPITAL BUDGET: $2,600,000
2026 Spend to Date: $851,055 | 2026 Remaining: $1,748,945
2026 ETC: $2,545,728
2026 VENDOR FORECAST
Nokia (2026 Order — Brian Basarath): $951,773 | Nokia Credits (NSP License cancellations): ~$218,480
Burns & McDonnell (PO 7000002099 — remaining): $1,222,710
Elecnor Hawkeye (PO 7000002054 — remaining): $205,276
NOTE: Budget variance driven by unplanned PAR migration scope (Iniven RC-30 devices, 6 sites) and extended engineering/labor.
Formal Change Request to be submitted to capture additional 2026 capital requirements.

## Slide 9
CURRENT RISKS
🔴 Legacy JMUX equipment is aging and fragile — risk of outage during migration window.
🔴 Faulty connectors (25+ years old) identified; replacements not readily available from vendors.
🟡 Potential brittle fiber patch panels, face plates, connectors, and cables at substation sites.
🟡 Weather delays and substation access constraints impacting installation schedule (tracked weekly).
🟡 Schedule conflicts with other major substation projects at PSEG Long Island.
🟡 PAR migration (Iniven RC-30) — 8-week equipment lead time; PO not yet placed. Risk to JMUX retirement timeline.
🟡 Melville and 6DL Pilgrim IFR/IFC dates still TBD — potential downstream schedule impact.
NEXT STEPS
🔄 Nokia Training — Confirm dates with Glenn/Nokia; identify attendees (Owner: Jay — Due: ASAP)
🔄 RTU Serial Testing at Hicksville QA — Schedule with John Ng's team; 2 temp cables to be installed (Owner: Ethan — TBD)
🔄 Phase 2 IFR Packages — Sterling & Whiteside IFR due 4/13; Hewlett IFR due 4/20 (Owner: Burns & McDonnell)
🔄 NSP Configuration — Ethan to work with Lee/Rahiq/Brianna to configure NSP appliance (stood up 4/10)
🔄 PAR Migration — Place PO for Iniven RC-30 devices (8-week lead time); coordinate with John Ng (Owner: Jay)
🔄 2-Way Radio migration — Start Layer 3 service migration per Lee's direction (Owner: Lee/BMcD)
🔄 JMUX Decommissioning — Earliest consideration April 2026; confirm readiness criteria (Owner: Jay/Team)
JMUX Replacement: Private Field Area Network