## Slide 1: PRJ13797: JMUX Replacement Update Project Manager : Dhananjaya Gunaratne
April 2026

## Slide 2
JMUX Replacement: Private Field Area Network
Modernize PSEG LI’s substation communications by replacing legacy JMUX with MPLS nodes to deliver a reliable, scalable and future-ready network.
Objectives
  Engineering Services (Burns & McDonnell)
    Site surveys, rack elevations, power & cabling design
    Node Design – Produce IFR, IFC and As-Built documents
Procurement & Staging (Burns & McDonnell, Nokia, Graybar)
    Bill of Materials creation, MPLS Equipment order, Power and ancillary equipment(Patch panels, Fiber cables, mounting kits, etc.)
Construction and Installation Support (Burns & McDonnell, Hawkeye)
    BMcD to provide on-site coordination with engineering team, technical support and commissioning oversight.
    Hawkeye to assist with shipment, racking, stacking, and power during staging. Perform site surveys for construction support. Install all equipment per the approved IFC documents
    Install fiber and copper cabling per the construction documents.
    Deployment and Application Migration (PSEG, Burns & McDonnell)
    Design and configure Layer 3 networks
    Pre-stage the application connectivity
    Migrate production applications
SCOPE | SUBSTATIONS | MPLS SITES | DF RTU SITES | RADIO SHELTER SITES | NOKIA MPLS NODES
PHASE 1 | 49 | 26 | 17 | 6 | 31
PHASE 2 | 45 | 26 | 12 | 7 | 26
PHASE 3 | 35 | 22 | 7 | 6 | 22
TOTAL SCOPE | 129 | 74 | 36 | 19 | 79
Goal & Objectives

## Slide 3
PHASE 1 — Completed Milestones
✅ Remote Connectivity — Hicksville & Melville — COMPLETE
Corporate Nokia MPLS integration established. BGP executed 4/1–4/2.
✅ iLO Corporate Connectivity — Hicksville & Melville — COMPLETE
iLO interfaces turned up and confirmed operational.
✅ Layer 3 BGP Network Design & Configuration — COMPLETE
BGP approved by Vikas Vohra 3/16. Fully executed 4/1–4/2.
✅ NSP Installation & Stand-Up — Hicksville — COMPLETE
Fiber cabled, terminated, NSP appliance stood up 4/10.
✅ Northport DC Power & OTDR Testing — COMPLETE
DC power live 3/18. Bad CWDM filter replaced. Link active.
PHASE 2 — Running In Parallel — ON TRACK 🟢
✅ IFR/IFC Packages — Lindenhurst due 4/27. Hewlett IFR with Lee for review 4/21.
✅ Equipment Staged — All Nokia Phase 2 equipment at Hawkeye staging trailer.
🔄 NMS Buildout — 13 of 31 Phase 1 Nokia routers added to NFMP by Lee. Rahiq & Brianna completing remaining 18 nodes. 🔄 Site Surveys — Hawkeye field crews dispatched this week. Collecting cable,
SFP, and equipment inventory at all Phase 2 sites.
🔄 Nokia NSP — Installed 4/21. Confirming full status. DNS update escalated to Vic.
Highlight Project Accomplishments
JMUX Replacement: Private Field Area Network

## Slide 4
Phase 2 Engineering Schedule — 36 Sites
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Survey | IFR | IFC | Construction | Deployment
1 | 7RM Bayport | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
2 | 7R Sayville | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/23/26
3 | 7XM Great River | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
4 | 7XM Great River Radio Shelter | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
5 | 6H Hauppauge | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
6 | 6H Hauppauge Tower | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
7 | 6S Kings Hwy | Complete | Mon 3/31/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
8 | Brentwood DO | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 9/2/26 | Fri 9/25/26
9 | 7H Babylon | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Mon 9/21/26
10 | 7H Babylon Radio Shelter | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Tue 9/22/26
11 | 7D West Babylon | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/12/26 | Mon 9/21/26
12 | 7D West Babylon Radio Shelter | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/19/26 | Mon 9/21/26
13 | 7W Berry St | Complete | Mon 3/31/26 | Tue 6/23/26 | Wed 8/19/26 | Mon 9/23/26
14 | 3J Whiteside | Complete | Mon 4/13/26 | Mon 5/4/26 | Wed 8/12/26 | Mon 9/14/26
15 | 2K Valley Stream | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
JMUX Replacement: Private Field Area Network

## Slide 5
Phase 2 Engineering Schedule — 36 Sites
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
16 | 2RB Green Acres | Complete | Mon 3/31/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
17 | Hewlett DO | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Fri 9/25/26
18 | 2ZB EF Barrett PS Inside | Complete | Mon 3/23/26 | Mon 4/20/26 | Wed 8/5/26 | Mon 9/14/26
19 | 2WB Barrett Outside | Complete | Mon 3/23/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
20 | 5HK Hicksville | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
21 | 2H Far Rockaway | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
22 | 2KB Cedarhurst | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
23 | 2R Hewlett | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
24 | 2R Hewlett Shelter | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
25 | 4M Baldwin | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
26 | 4M1 Baldwin Shelter | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
27 | 6K State School | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Fri 9/17/26
28 | 7BH Bohemia | Complete | Mon 3/31/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
29 | 7M MacArthur | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/22/26
JMUX Replacement: Private Field Area Network

## Slide 6
Phase 2 Engineering Schedule — 36 Sites
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
30 | 8AX Patchogue | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
31 | 8AX Patchogue Shelter | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
32 | 7Z Lindenhurst | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
33 | 7J Sterling | Complete | Mon 3/31/26 | Tue 6/9/26 | Wed 8/26/26 | Mon 9/22/26
34 | 7UM South Farmingdale | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
35 | ACC | Complete | Tue 6/9/26 | Wed 7/8/26 | Tue 9/8/26 | Mon 9/28/26
36 | 6U Ruland | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
JMUX Replacement: Private Field Area Network

## Slide 7
Schedule Status
Overall: 🟡 YELLOW — Trending ⬆️ TOWARD GREEN
PSEG Long Island | JMUX Replacement Program | Confidential | April 2026
Important Clarification — Phase 1 vs. Overall Project:
• SSP documentation delays (security review queue)
• CMDB update coordination time
Recovery Actions:
⚠️ The ~3 month delay applies ONLY to Phase 1 remaining activities — NOT the entire project.
Phase 1 — Delayed (Recovering):
• Nokia NSP finalization — 90% done, DNS update escalated to Vic this week
• RTU serial port test at Hicksville — cables sourced from Hawkeye, scheduling in progress
• Relay RTU cutover to Nokia — pending RTU test
• Layer 3 / 2-Way Radio migration — pending NSP completion
Phase 2 — ON TRACK 🟢 (Running in Parallel):
• IFR/IFC engineering packages — on schedule. Hewlett submitted 4/20. Lindenhurst due 4/27.
• Hawkeye field crews dispatched for site surveys — capturing cables, SFPs, equipment needs
• All Nokia Phase 2 equipment staged at Hawkeye trailer ✅
Recovery Actions:
• DNS escalated to Vic — one-line fix, expected resolution this week
• Vinny (Hawkeye) dispatched for DB9 cable sourcing today — unblocks RTU test
• Additional resources applied to close Phase 1 gap
• Phase 3 stakeholders already engaged proactively to prevent scope surprises
SCHEDULE PERFORMANCE INDEX (SPI)
0.00
0.50
0.75
1.00
1.25
1.50
2.00
●
Below 0.70 — Critical
●
0.70–0.90 — Yellow
●
0.90–1.10 — On Track
●
Above 1.10 — Ahead
--- February 2026 : 0.75 (Orange)
╌╌ January 2026 : 1.00 (Gray)
--- March 2026 : 0.80 (Yellow ↓)
Week | Dates | Planned site (PV) | Actual Sites Completed (EV) | Weekly SPI | Cumulative SPI | Key Notes
iLO corporate connectivity interfaces turned up at Melville and Hicksville | 2/26/2026 | 1 milestone (DC power complete) | 1 (DC power complete) | 1.00 | 0.76 | Northport fuse tripping — ILO work blocked. DC power issue resolved
Layer 3 (BGP) network design and configurations | 3/9/2026 | 1 milestone (OTDR confirm) | 1 (OTDR complete ✅) | 1.00 | 0.77 | OTDR confirmed bad filter at Hicksville. Link now active. Crown Castle issue cleared. ✅
Remote access to NSP for Nokia Network Configurations & Management | 3/10/2026 | 1 milestone (NSP fiber term) | 1 (complete ✅) | 1.00 | 0.78 | Fiber run to NSP completed & terminated at Hicksville by Hawkeye. ✅
BGP design approved | 3/16/2026 | 1 milestone (BGP approval) | 1 (approved ✅) | 1.00 | 0.80 | BGP design formally approved. Lee to begin change docs for Hicksville & Melville. ✅
Moved all equipment to new Hawkeye trailer for future staging . | 3/10/2026 | 0 (logistics task) | 1 (complete ✅) | 1.00 | 0.80 | Phase 2 Nokia equipment moved to new Hawkeye staging trailer. Not on critical path.
JMUX Replacement: Private Field Area Network

## Slide 8
Financials (2024-2026)
JMUX Replacement: Private Field Area Network
PROJECT FINANCIAL SUMMARY — As of March 11, 2026
Total Capital Budget: $6,600,000 | Spend to Date: $4,722,381 | Remaining Budget: $1,877,619
Estimate to Complete: $2,545,728 | Estimate at Completion: $7,268,109
⚠️ Projected Total Variance: -$668,109 (-10.1%)
⚠️ Projected 2026 Capital Variance: -$796,783 (-31%)
2026 APPROVED CAPITAL BUDGET: $2,600,000
2026 Spend to Date: $851,055 | 2026 Remaining: $1,748,945
2026 ETC: $2,545,728
2026 VENDOR FORECAST
Nokia (2026 Order — Brian Basarath): $951,773 | Nokia Credits (NSP License cancellations): ~$218,480
Burns & McDonnell (PO 7000002099 — remaining): $1,222,710
Elecnor Hawkeye (PO 7000002054 — remaining): $205,276
NOTE: Budget variance driven by unplanned PAR migration scope (Iniven RC-30 devices, 6 sites) and extended engineering/labor.
Formal Change Request to be submitted to capture additional 2026 capital requirements.

## Slide 9
CURRENT RISKS
🔴 PAR Serial-to-IP Equipment (Iniven RC-30) — 8-week lead time. PO not yet placed. CRITICAL PATH.
🟡 DNS update — NSP installed 4/21, status being confirmed. DNS fix escalated to Vic.
🟡 Weather delays — substation closures possible at temps >90°F. Potential 2-week delay per event.
(Risk — not yet an issue. Monitor summer forecast. Schedule critical work in cooler windows.)
🟡 RTU serial test scheduling — DB9 cables delivered to John Ng ✅. Awaiting test date from relay team.
🟡 Melville & 6DL Pilgrim IFR/IFC — dates still TBD. Monitoring for schedule impact.
NEXT STEPS — Priority Order
1️⃣ Resolve DNS (.11→.15, .21→.25) — confirm NSP GUI access to ALL Nokia routers [Vic / Lee / Wayne]
2️⃣ Execute RTU serial port test at Hicksville — validate pinout before Phase 2 construction [Ethan / John Ng / Jay]
3️⃣ Relay RTU cutover to Nokia network — first production circuit migration [Lee / John Ng]
4️⃣ ⚠️ Place PO — Iniven RC-30 (6 PAR sites) — 8-WEEK LEAD TIME — ORDER IMMEDIATELY [Jay]
5️⃣ ⚠️ Start PAR engineering design concurrently with PO placement [BMcD / Jay]
6️⃣ Northport C37.94 card — bundle order with Phase 2 equipment [Jay / BMcD] 7️⃣ PAR pilot connectivity test — confirm wiring at Northport [BMcD / Hawkeye] 8️⃣ Hawkeye site surveys — cable & SFP inventory across all Phase 2 sites [Vinny / Hawkeye]
9️⃣ Confirm Nokia training dates with Glenn — identify attendees [Jay]
🔟 Lindenhurst IFR submission — due Monday April 27 ⚠️ IMMINENT [Burns & McDonnell]
JMUX Replacement: Private Field Area Network