## Slide 1: PRJ13797: JMUX Replacement Update Project Manager : Dhananjaya Gunaratne
February 2026

## Slide 2
JMUX Replacement: Private Field Area Network
Modernize PSEG LI’s substations communications by replacing legacy JMUX with MPLS nodes to deliver a reliable, scalable and future-ready network.
Objectives
  Engineering Services
    Detailed site surveys, rack elevations, power design, supplemental documents and as-builts
    Each of the substations are fully aligned with PSEG LI standards and stakeholder buy-off
    Phase 1 – As- Built – BMcD is working on completing the As –Built for Phase 1
    Phase 2 site surveys completed in Phase 1. BMcD is working on
      Issuing (IFRs)
      Issuing for Construction (IFC) – In Progress
Procurement & Staging
    All equipment purchased by PSEGLI and shipped to Hawkeye’s staging facility, date of delivery – Delivered
Construction and Installation Support
    BMcD to provide on-site coordination with engineering team, technical support and commissioning oversight.
    SSP document gathering for Phase 2 needs to be filled out for SSP team
    Working on remote connectivity to the nodes.
SCOPE | SUBSTATIONS | MPLS SITES | DF RTU SITES | RADIO SHELTER SITES | NOKIA MPLS NODES
PHASE 1 | 49 | 26 | 17 | 6 | 31
PHASE 2 | 45 | 26 | 12 | 7 | 26
PHASE 3 | 35 | 22 | 7 | 6 | 22
TOTAL SCOPE | 129 | 74 | 36 | 19 | 79
Goal & Objectives

## Slide 3
Phase-1
Engineering Services
Procurement and Staging
  Staging completed at Hawkeye Warehouse - 9/29/2025
Construction and Installation Support
  Installing equipment at substations. – 31/31 sites completed
  ACC cabling and fiber panel installed – 1/7/26
  Throwover from Hicksville to ACC will happen - 1/13/2026
    J-mux eqpt. Will be moved on the primary & secondary cabinet to
    make room for the MPLS routers. – 1/13/26 - Work Completed
    Complete CWDM cutover at Hicksville and ACC - Work completed
    Install routers in the primary & secondary cabinet – Work Completed
    NSP installed racked & powered up in Melville and Hicksville – Work Completed
    CMDB document updated and added to CMDB database – Work Completed
    Cat 6 cables need to be ordered and run to NSP in Hicksville – Scheduled for 03/03
Deployment & Cutover
  Cutover of CWDM started at Bagatelle, Melville, Pilgrim -11/19- 11/20/2025 – we ran into fiber panel issues. - Work Completed
  Wave 1 - 12/8/2025 – 12/18/2025 (non-tie sites) – Decided to start with the no tie sites. – Work Completed
  WAVE 2 - 01/06/2026 – 1/08/2026 (tie-in-sites) – with experience cutting over the tie sites, we felt comfortable to complete the tie sites. – Work Completed
.
Burns & Mac - Phase 1 | Total | Completed
IFR - Issued for review design | 31 | 31
IFC - Issued for construction | 31 | 31
Highlight Project Accomplishments
Total Phase 1 scope | 
Initiation & Planning | 100%
Site Surveys | 100%
Test Plan | 100%
HLD | 100%
IFR/IFC | 100%
Procurement | 100%
Staging | 100%
Field Installation | 100%
Deployment - CWDM | 100%
Pre-Deployment Deployment - Security & Radio | 5%
Deployment - Relay/RTU Cutover | not started

## Slide 4
Progress Current Period (past 2 weeks)- Milestones/Key Deliverables with Dates
Nokia equipment for Phase 2 – delivered to Hawkeye warehouse 02/19/2026
Nokia NSP equipment installed racked and powered up at Melville and Hicksville . 02/11/2026
SSP documents filled out and sent to SSP team 02/10/2026
CMDB inventory spreadsheet filled out and sent to added into database. 02/06/2026
Project Health | Status | Trends
Schedule Health | Green | 
Financial Health | Green | 
Scope Health | Green | 
Risk Health | Green | 
Resource Health | Green | 
Status Date: 02/25/2026
IT/Cyber: IT
Director: Irving Landesbaum
GPM: Vikas Vohra
Program Manager Jay Gunaratne
Time Management
Proj Actual Start 04-18-2024
RFP Award and SOW 10-04-2024
Phase 1 Detailed Design Start 01-13-2025
Construction Start 10-06-2025
Project Plan (Baseline) End 04-08-2027
Proj Actual Target End 07-08-2027
Financials–Total URB Approved Prgm Budget
Master WBS Code: I.39424.1.x URB Approved budget: $6,600,000.00
Spend to date: $4,437,070.00
Estimate to complete: $2,162,930.00
Estimate at complete: $6,600,000.00
Over (+) / Under (-) budget: $00.00
Under budget
Benefit
Due to GE announcing End of Life for the GE Jungle Mux system as of EOY 2025, the benefits for project is to allow the Systems Integrator to select the most appropriate ‘Equipment Vendor’ via the RFP process to replace the GE JMUX equipment.
Designing and implementing a private MPLS network to replace the aging Jungle Mux system enhances reliability, scalability, and security while ensuring seamless communication and future-proofing critical infrastructure. This upgrade reduces maintenance costs, simplifies network management, and mitigates risks associated with end-of-life equipment, ensuring long-term operational stability.
Scope (95%-Complete)
(Update the % above accordingly. The % of work that has been completed to deliver a product, service, or result with the specified features and functions. It is conceivable to leverage the description from each of the underlying project PJD’s)
Major Steps (next 2 weeks): Milestones/Key Deliverables with Dates
Cabling for NSP in Hicksville will be completed (Cables ordered) 03/03/2026
OTDR testing at Hicksville since the DB level is low. 03/03/2026
Nokia Equipment for Phase 2 delivered all at once to Hawkeye warehouse. 02/19/2026
Risk Management- Top 3 (in order of possible impact)
Safety delay at substation – Vendor not reporting safety issue.
Vendor installation delays – inclement weather
Legacy JMUX equipment old and need to be very careful when doing cutovers.
Issue Management- Top 3 (in order of actual impact)
Accelerating phase 2 site surveys by getting them completed in Phase 1.
Working closely with vendors and tracking installation.
Scope/Change Management (most recent approved)
Adding 7 additional nodes to the original 25 Phase 1 nodes. The additional 7 nodes completes both ring 1 and ring 2 in this Phase 1 effort.
Current Period (past 2 weeks) Status Narrative:
CMDB inventory database updated and confirmed. – 2/24
SSP documentation, security assessments, architecture reviews and compliance readiness for radio/security have been approved .
Nokia NSP installed at Hicksville & Melville. Setting up a change ticket for 03/03, to revisit Hicksville to complete cabling that was ordered.
Nokia equipment has been delivered to Hawkey warehouse and safely stored – 02/19
OTDR testing is planned for 03/04. Hawkeye will visit the Hicksville site to plan. The wavelength will be tested to make sure the filter is working properly. If the filter is working properly, it can be a Crown Castle issue.
Verified with OTDR tester that their test set can test 1550 and 1310 wavelengths.
Project Description
The Systems Integrator will create, facilitate, and execute the process for generating an RFP to select an ‘Equipment Vendor’ to replace the existing Private Network vendor – GE Jungle MUX. In parallel, the Systems Integrator will conduct ‘high-level’ design activities for the MPLS Private Network, including site surveys at 88 COMPANY substations to assess specific structural and infrastructure modifications required for the new equipment.
PRJ (ServiceNow): PRJ13797
Repository Link: JMUX Repository
Overall Health
This Period Last Period
PROGRAM: JMUX Replacement - Phase 1

## Slide 5
Phase 1 – Layer 1-3 configuration – Next steps

## Slide 6
2025 Phase-1 Substation Schedule 31 Sites (1 of 2)
Project Accomplishments
# | Substation | IFR | IFC | Construction | Deployment
1 | 6BR: Bagatelle Rd | Completed | Completed | Sept-9th Oct 10th | Nov-19th 2/10/26
2 | 6P: Pulaski Rd. | Completed | Completed | Sept-12th Oct 10th | Dec-11th 2/12/26
3 | 6P1: Pulaski Rd. Shelter | Completed | Completed | Sept-12th Oct 10th | Dec-11th 2/13/26
4 | Melville | Completed | Completed | Sept-11th Oct 10th | Nov-25th 1/5/26
5 | 6DL: Pilgrim | Completed | Completed | Sept-11th Oct 10th | Dec-2nd 2/11/26
6 | 5K: Syosset | Completed | Completed | Aug-12th Oct 24th | Sept-19th 1/2/26
7 | 5K1: Syosset Shelter | Completed | Completed | Aug-12th Oct 24th | Sept-19th 1/3/26
8 | 6U: Ruland Rd. | Completed | Completed | Sept-9th Oct 17th | Nov-21st 2/10/26
9 | 6Fo: Northport (outdoor) | Completed | Completed | Sept-3rd Oct 31st | Oct-23rd 2/3/26
10 | 6Fi: Northport (outdoor) | Completed | Completed | Sept-3rd Oct 31st | Oct-24th 2/4/26
11 | 6RL: Elwood | Completed | Completed | Sept-3rd Oct 10th | Oct-31st 2/4/26
12 | 6UL: Greenlawn | Completed | Completed | Sept-5rd Oct 17th | Nov-5th 2/5/26
13 | 6UL1: Greenlawn Shelter | Completed | Completed | Sept-5th Oct 17th | Nov-7th 2/6/26
14 | 6Q: Oakwood | Completed | Completed | Sept-5th Oct 10th | Nov-13th 2/9/26
15 | 5M: Newbridge | Completed | Completed | Aug-19th Oct 17th | Oct-9th 1/16/26
16 | 4XH: Glenwood | Completed | Completed | Aug-12th Nov 6th | Sept-23rd 2/11/26

## Slide 7
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Project Accomplishments
# | Substation | IFR | IFC | Construction | Deployment
17 | 5HK: Hicksville (primary) | Completed | Completed | Aug-19th Oct 17th | Oct-8th 1/12/26
18 | 5HK: Hicksville (secondary) | Completed | Completed | Aug-19th Oct 17th | Oct-9th 1/12/26
19 | 5MK: Jericho | Completed | Completed | Aug-19th Nov 6th | Oct-9th 1/14/26
20 | ACC | Completed | Completed | Aug-26th Oct 24th | Oct-21st 1/27/26
21 | 4G: Shore Rd. | Completed | Completed | Aug-12th Nov 6th | Sept-25th 1/6/26
22 | 4GH: Glen Head | Completed | Completed | Aug-14th Nov 6th | Sept-25th 1/6/26
23 | 4B: Roslyn | Completed | Completed | Aug-14th Nov 6th | Sept-29th 1/7/26
24 | 3AF: Lake Success | Completed | Completed | Aug-14th Oct 10th | Sept-29th 1/7/26
25 | 3AF1: Lake Success Shelter | Completed | Completed | Aug-14th Oct 10th | Sept-30th 1/8/26
26 | 3KG: Herrick's | Completed | Completed | Aug-19th Oct 31st | Oct-13th 1/16/26
27 | 4AH: Carle Place | Completed | Completed | Aug-28th Oct 31st | Oct-20th 1/30/26
28 | 4MG: Mitchell Gardens | Completed | Completed | Aug-28th Oct 31st | Oct-20th 2/2/26
29 | 4H: East Garden City | Completed | Completed | Aug-19th Oct 24th | Oct-13th 1/19/26
30 | 3D: Manhasset | Completed | Completed | Aug-14th Oct 31st | Oct-1st 1/9/26
31 | 3D1: Manhasset Shelter | Completed | Completed | Aug-15th Oct 31st | Oct-2nd 1/9/26

## Slide 8
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 surveys being done during Phase 1
# | Substation | Site Survey | IFR | IFC | Construction | Deployment
1 | 7RM Bayport | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
2 | 7R Sayville | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/23/26
3 | 7XM Great River | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
4 | 7XM Great River Radio Shelter | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
5 | 6H Hauppauge | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
6 | 6H Hauppauge Tower | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
7 | 6S Kings Hwy | Complete | Mon 4/27/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
8 | Brentwood DO | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 9/2/26 | Fri 9/25/26
9 | 7H Babylon | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Mon 9/21/26
10 | 7H Babylon Radio Shelter | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Tue 9/22/26
11 | 7D West Babylon | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/12/26 | Mon 9/21/26
12 | 7D West Babylon Radio Shelter | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/19/26 | Mon 9/21/26
13 | 7W Berry St | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/19/26 | Mon 9/23/26
14 | 3J Whiteside | Complete | Mon 4/6/26 | Mon 5/4/26 | Wed 8/12/26 | Mon 9/14/26
15 | 2K Valley Stream | Complete | Tue 2/23/26 | Mon 3/2/26 | Wed 8/5/26 | Mon 9/14/26

## Slide 9
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 surveys being done during Phase 1
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
16 | 2RB Green Acres | Complete | Mon 3/9/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
17 | Hewlett DO | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Fri 9/25/26
18 | 2ZB EF Barrett PS Inside | Complete | Mon 3/23/26 | Mon 4/20/26 | Wed 8/5/26 | Mon 9/14/26
19 | 2WB Barrett Outside | Complete | Mon 3/23/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
20 | 5HK Hicksville | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
21 | 2H Far Rockaway | Complete | Tue 2/23/26 | Mon 3/2/26 | Wed 8/5/26 | Mon 9/14/26
22 | 2KB Cedarhurst | Complete | Tue 2/23/26 | Mon 3/2/26 | Wed 8/5/26 | Mon 9/14/26
23 | 2R Hewlett | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
24 | 2R Hewlett Shelter | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
25 | 4M Baldwin | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
26 | 4M1 Baldwin Shelter | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
27 | 6K State School | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Fri 9/17/26
28 | 7BH Bohemia | Complete | Mon 4/27/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
29 | 7M MacArthur | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/22/26

## Slide 10
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 surveys being done during Phase 1
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
30 | 8AX Patchogue | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
31 | 8AX Patchogue Shelter | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
32 | 7Z Lindenhurst | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
33 | 7J Sterling | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/26/26 | Mon 9/22/26
34 | 7UM South Farmingdale | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
35 | ACC | Complete | Tue 6/9/26 | Wed 7/8/26 | Tue 9/8/26 | Mon 9/28/26
36 | 6U Ruland | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26

## Slide 11
JMUX Replacement: Private Field Area Network
JMUX Schedule Performance Index – Phase 1
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr | 5 | 6 | 7 | 8 | 9 | 10
Project SPI Current | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 50
.5
1.0
.9
1.1
1.2
1.4
1.3
Result
February - .75
Delay in SSP document and CMDB doc with also inclement weather caused 2.5-week delay on the project. The schedule is currently yellow.
We have all the approvals to move forward with configuring the routers. This is not physical work, but remote work, which will be done as soon as we confirm the NSP equipment is cabled up and we have remote access.
.9
Week | Scheduled work | Planned site (PV) | Actual Sites Completed (EV) | Weekly SPI | Culmative SPI | Key Notes
February 1- February 7 | CMDB inventory filled out on share point | 20 | 12 | .60 | .60 | Inventory database was updated
February 8 – February 14 | NSP equipment installed @ Melville and Hicksville | 20 | 16 | .80 | .70 | .80 shows we are trending upward. Eqpt was installed without alarms.
February 15 – February 21 | Phase 2 – Nokia Eqpt delivered to warehouse | 20 | 20 | 1.00 | .80 | Phase 2 – eqpt from NOKIA delivered and safely stored
February 22 – February 28 | CMDB database updated | 20 | 24 | 1.20 | .90 | SPI of 1.20 shows catch-up week and drives cumulative SPI toward recovery.
March 1- March 7th | OTDR testing and cabling to be completed at Hicksville | NA | NA | NA | NA | EV/SPI will be updated once testing is completed and remote access is confirmed.

## Slide 12
Financials (2024-2026)

## Slide 13
Current Risk
  Legacy JMUX equipment old and delicate. Potential for Outage.
      Ran into faulty connectors that are over25 years old and not readily available with vendors.
      Potential brittle fiber patch panels, Face plates, connectors and cables.
  Weather delay and delay in installing the equipment at sub-station (tracking weekly).
  Other major substation project conflicts.
Next Steps
Hawkeye will complete Cat 6 cabling needed for Nokia NSP in Hicksville.
They will also complete the OTDR testing since the level is low. If there is no issue on our equipment, it might be a Crown Castle issue. Testing will confirm where the fault lies.
Router configuration on the routers that are powered up on Ring 1 and Ring 6 will commence.
Verifying Remote access after NSP is wired and OTDR issue is rectified.
I can bring the project back on Schedule when the routers are provisioned after the OTDR and cabling is completed via remote access.

## Slide 14
Hicksville Cat6 cabling completion for NSP (change ticket planned 03/03).
OTDR testing at Hicksville (planned 03/04) to confirm whether the low DB level is internal vs carrier-side (Crown Castle); validate filter/wavelength behavior.
Confirm stable remote access after cabling/OTDR so we can shift to “remote-first” execution.
Start router configuration on the powered routers for Ring 1 and Ring 6 (remote workstream), with standard config + validation.
Continue closeout: finalize CMDB/As-Builts updates and close the remaining documentation gate (this is key to moving Yellow → Green).