## Phase 1 Cost Summary
JMUX Replacement Phase 1 Cost Breakdown
Deliverable | Payment Amount | 2024 | 2025 | 2026
Substation Site Surveys | 78870 | 29875 | 48995
MPLS Network Node Template | 18950 | 18950
Communications Enclosure Estimate
Low Level Design | 51250 |  | 51250
Network Test Plan | 14750 |  | 14750
Lab Testing
Procurement and Construction Bids | 12750 |  | 12750
MPLS Network Node Design | 787050 |  | 787050
Phase 1 Staging Support (2 weeks, 2 people) | 57300 |  | 57300
Phase 1 Construction/Commissioning Support (8 months) | 490800 |  | 384125 | 106675
Phase 1 Reduced Construction Support (6 months) | 368100 |  | 164625 | 203475
Phase 1 Total | 1511720 | 48825 | 1356220 | 106675
Phase 1 Reduced Total | 1389020 | 48825 | 1136720 | 203475
MPLS Network Node Design Site List and Cost Breakdown
Site Code | Site Name | Total Cost | IFR Cost | IFC Cost | As-Built Cost
5HK | Hicksville Primary Room | 23850 | 16695 | 5963 | 1192
5HK | Hicksville Secondary Room | 23850 | 16695 | 5963 | 1192
5M | Newbridge | 23850 | 16695 | 5963 | 1192
ACC | ACC | 23850 | 16695 | 5963 | 1192
6U | Ruland | 23850 | 16695 | 5963 | 1192
MEL | Melville | 23850 | 16695 | 5963 | 1192
6BR | Bagatelle | 23850 | 16695 | 5963 | 1192
6DL | Pilgrim | 23850 | 16695 | 5963 | 1192
6P | Pulaski | 23850 | 16695 | 5963 | 1192
6P1 | Pulaski Radio Shelter | 23850 | 16695 | 5963 | 1192
6Fo | Northport Outdoor | 23850 | 16695 | 5963 | 1192
6Fi | Northport Indoor | 23850 | 16695 | 5963 | 1192
6RL | Elwood | 23850 | 16695 | 5963 | 1192
6UL | Greenlawn | 23850 | 16695 | 5963 | 1192
6UL1 | Greenlawn Radio Shelter | 23850 | 16695 | 5963 | 1192
6Q | Oakwood | 23850 | 16695 | 5963 | 1192
5K | Syosset | 23850 | 16695 | 5963 | 1192
5K1 | Syosset Radio Shelter | 23850 | 16695 | 5963 | 1192
5SK | Plainview | 23850 | 16695 | 5963 | 1192
4F | Freeport (Intertie) | 23850 | 16695 | 5963 | 1192
5BK | Brooklyne Ave | 23850 | 16695 | 5963 | 1192
5RK | North Bellmore | 23850 | 16695 | 5963 | 1192
5R | Bellmore | 23850 | 16695 | 5963 | 1192
5RS | Round Swamp | 23850 | 16695 | 5963 | 1192
6M | Deposit | 23850 | 16695 | 5963 | 1192
MPLS Network Node Design Total |  | 596250 | 417375 | 149075 | 29800
CR1
Site Code | Site Name | Total Cost | IFR Cost | IFC Cost | As-Built Cost
3AF | Lake Success | 23850 | 16695 | 5963 | 1192
3AF1 | Lake Success - Shelter | 23850 | 16695 | 5963 | 1192
3KG | Herricks | 23850 | 16695 | 5963 | 1192
4AH | Carle Place | 23850 | 16695 | 5963 | 1192
4MG | Mitchell Gardens | 23850 | 16695 | 5963 | 1192
4H | E. Garden City | 23850 | 16695 | 5963 | 1192
3D | Manhasset | 23850 | 16695 | 5963 | 1192
3D | Manhasset Shelter | 23850 | 16695 | 5963 | 1192
MPLS Network Node Design CR1 Total |  | 190800 | 133560 | 47704 | 9536

## Phase 2 Cost Breakdown
JMUX Replacement Phase 2 Cost Breakdown
Scope | Total Cost | 2025 | 2026
Phase 2 Substation Site Surveys | 86040 | 57360 | 28680
Phase 2 Staging Support (2 weeks, 2 people) | 57300 |  | 57300
Phase 2 Construction/Commissioning Support (8 months) | 490800 |  | 490800
Phase 2 Reduced Construction Support (6months) | 368100 |  | 368100
Phase 2 MPLS Network Node Design | 858600 | 453160 | 405440
Phase 2 Total | 1492740 | 510520 | 982220
Phase 2 Reduced Total | 1370040 | 510520 | 859520
MPLS Network Node Design Site List and Cost Breakdown |  |  | Site Count: | 36
Site Code | Site Name | Total Cost | IFR Cost | IFC Cost | As-Built Cost
1 | Site 1 | 23850 | 16695 | 5963 | 1192
2 | Site 2 | 23850 | 16695 | 5963 | 1192
3 | Site 3 | 23850 | 16695 | 5963 | 1192
4 | Site 4 | 23850 | 16695 | 5963 | 1192
5 | Site 5 | 23850 | 16695 | 5963 | 1192
6 | Site 6 | 23850 | 16695 | 5963 | 1192
7 | Site 7 | 23850 | 16695 | 5963 | 1192
8 | Site 8 | 23850 | 16695 | 5963 | 1192
9 | Site 9 | 23850 | 16695 | 5963 | 1192
10 | Site 10 | 23850 | 16695 | 5963 | 1192
11 | Site 11 | 23850 | 16695 | 5963 | 1192
12 | Site 12 | 23850 | 16695 | 5963 | 1192
13 | Site 13 | 23850 | 16695 | 5963 | 1192
14 | Site 14 | 23850 | 16695 | 5963 | 1192
15 | Site 15 | 23850 | 16695 | 5963 | 1192
16 | Site 16 | 23850 | 16695 | 5963 | 1192
17 | Site 17 | 23850 | 16695 | 5963 | 1192
18 | Site 18 | 23850 | 16695 | 5963 | 1192
19 | Site 19 | 23850 | 16695 | 5963 | 1192
20 | Site 20 | 23850 | 16695 | 5963 | 1192
21 | Site 21 | 23850 | 16695 | 5963 | 1192
22 | Site 22 | 23850 | 16695 | 5963 | 1192
23 | Site 23 | 23850 | 16695 | 5963 | 1192
24 | Site 24 | 23850 | 16695 | 5963 | 1192
25 | Site 25 | 23850 | 16695 | 5963 | 1192
26 | Site 26 | 23850 | 16695 | 5963 | 1192
27 | Site 27 | 23850 | 16695 | 5963 | 1192
28 | Site 28 | 23850 | 16695 | 5963 | 1192
29 | Site 29 | 23850 | 16695 | 5963 | 1192
30 | Site 30 | 23850 | 16695 | 5963 | 1192
31 | Site 31 | 23850 | 16695 | 5963 | 1192
32 | Site 32 | 23850 | 16695 | 5963 | 1192
33 | Site 33 | 23850 | 16695 | 5963 | 1192
34 | Site 34 | 23850 | 16695 | 5963 | 1192
35 | Site 35 | 23850 | 16695 | 5963 | 1192
36 | Site 36 | 23850 | 16695 | 5963 | 1192
37 | Site 37 | 23850 | 16695 | 5963 | 1192
38 | Site 38 | 23850 | 16695 | 5963 | 1192
MPLS Network Node Design Total |  | 906300 | 634410 | 226594 | 45296

## Phase 3 Cost Breakdown
JMUX Replacement Phase 3 Cost Breakdown
Scope | Total Cost | 2026 | 2027
Phase 3 Substation Site Surveys | 89481.6 | 44740.8 | 44740.8
Phase 3 Staging Support (2 weeks, 2 people) | 59592 | 59592
Phase 3 Construction/Commissioning Support (8 months) | 510432 |  | 510432
Phase 3 MPLS Network Node Design | 967356 | 483678 | 483678
Phase 3 Total | 1626861.6 | 588010.8 | 1038850.8
MPLS Network Node Design Site List and Cost Breakdown |  |  | Site Count: | 39
Site Code | Site Name | Total Cost | IFR Cost | IFC Cost | As-Built Cost
1 | Site 1 | 24804 | 17362.8 | 6201 | 1240.2
2 | Site 2 | 24804 | 17362.8 | 6201 | 1240.2
3 | Site 3 | 24804 | 17362.8 | 6201 | 1240.2
4 | Site 4 | 24804 | 17362.8 | 6201 | 1240.2
5 | Site 5 | 24804 | 17362.8 | 6201 | 1240.2
6 | Site 6 | 24804 | 17362.8 | 6201 | 1240.2
7 | Site 7 | 24804 | 17362.8 | 6201 | 1240.2
8 | Site 8 | 24804 | 17362.8 | 6201 | 1240.2
9 | Site 9 | 24804 | 17362.8 | 6201 | 1240.2
10 | Site 10 | 24804 | 17362.8 | 6201 | 1240.2
11 | Site 11 | 24804 | 17362.8 | 6201 | 1240.2
12 | Site 12 | 24804 | 17362.8 | 6201 | 1240.2
13 | Site 13 | 24804 | 17362.8 | 6201 | 1240.2
14 | Site 14 | 24804 | 17362.8 | 6201 | 1240.2
15 | Site 15 | 24804 | 17362.8 | 6201 | 1240.2
16 | Site 16 | 24804 | 17362.8 | 6201 | 1240.2
17 | Site 17 | 24804 | 17362.8 | 6201 | 1240.2
18 | Site 18 | 24804 | 17362.8 | 6201 | 1240.2
19 | Site 19 | 24804 | 17362.8 | 6201 | 1240.2
20 | Site 20 | 24804 | 17362.8 | 6201 | 1240.2
21 | Site 21 | 24804 | 17362.8 | 6201 | 1240.2
22 | Site 22 | 24804 | 17362.8 | 6201 | 1240.2
23 | Site 23 | 24804 | 17362.8 | 6201 | 1240.2
24 | Site 24 | 24804 | 17362.8 | 6201 | 1240.2
25 | Site 25 | 24804 | 17362.8 | 6201 | 1240.2
26 | Site 26 | 24804 | 17362.8 | 6201 | 1240.2
27 | Site 27 | 24804 | 17362.8 | 6201 | 1240.2
28 | Site 28 | 24804 | 17362.8 | 6201 | 1240.2
29 | Site 29 | 24804 | 17362.8 | 6201 | 1240.2
30 | Site 30 | 24804 | 17362.8 | 6201 | 1240.2
31 | Site 31 | 24804 | 17362.8 | 6201 | 1240.2
32 | Site 32 | 24804 | 17362.8 | 6201 | 1240.2
33 | Site 33 | 24804 | 17362.8 | 6201 | 1240.2
34 | Site 34 | 24804 | 17362.8 | 6201 | 1240.2
35 | Site 35 | 24804 | 17362.8 | 6201 | 1240.2
36 | Site 36 | 24804 | 17362.8 | 6201 | 1240.2
37 | Site 37 | 24804 | 17362.8 | 6201 | 1240.2
38 | Site 38 | 24804 | 17362.8 | 6201 | 1240.2
39 | Site 39 | 24804 | 17362.8 | 6201 | 1240.2
MPLS Network Node Design Total |  | 967356 | 677149.2 | 241839 | 48367.8