## Phase 1 — Steps & Cost
PRJ13797 – JMUX Replacement ¦ PHASE 1 — WHAT REMAINS TO BE DONE ¦ As of May 18 2026
Phase 1 target completion: Jun 23 2026 ¦ 33 sites (Hawkeye) ¦ 31 MPLS nodes (Nokia)
SECTION A — TECHNICAL / OPERATIONAL STEPS TO COMPLETE PHASE 1
# | Workstream | Step / Action Required | Owner | Target Date | Status | % Done | Blocker? | Notes
1 | RTU Migration | Complete RTU serial test at Hicksville (beta cable RJ45→DB25 installed — test circuit with EMS) | John Ng / B&M / Lee Blackman | May 18–19 2026 | OVERDUE | 55% | NO | Beta cable delivered. QAS 6U RTU + Digi confirmed ready by George. CAT6 from QAS Digi at patch panel. Once test passes → confirm pinout → order 8 patch panel cables.
2 | RTU Migration | Order 8× patch panel cables (RJ45→DB25) 7 production + 1 spare — confirm pinout transmit/receive crossover | Jay / Procurement | May 22 2026 | Not Started | 0% | Depends on Step 1 | Cables Unlimited is supplier. Cannot order until Hicksville serial test confirms correct pinout. 7 Phase 1 sites + 1 spare = 8 units.
3 | RTU Migration | Develop MOP — Production RTU Migration (5K SIOS pilot cutover procedure) | Ethan Koch (B&M) | May 16 2026 | OVERDUE | 10% | NO | MOP must cover: substation location, Hicksville control room, ACC. Personnel: relay tech at substation, control room tech at Hicksville, JVOX at ACC, Rahiq/Brianna on site. Change mgmt ticket required.
4 | NMS / NSP | Remote Node Verification — All 31 Phase 1 Sites (Login via NSP GUI, verify configs, confirm connectivity) | Lee Blackman / Rahiq / Brianna | May 9 2026 | OVERDUE | 0% | NO | OVERDUE — planned May 9. Must complete before production cutover scheduling can begin. 31 nodes in NSP GUI already built.
5 | RTU Migration | Production RTU Circuit Cutovers — All Phase 1 Sites (all JMUX-supported RTU circuits migrated to Nokia MPLS) EXCEPTION: 5DA Duffy Ave + 5R Bellmore (4W→RS-232 conversion first) | John's relay team / Jay | Jun 23 2026 | Not Started | 0% | Depends on Steps 1–4 | Cannot start until: serial test ✓, MOP approved ✓, node verification ✓. 5DA Duffy Ave and 5R Bellmore: wait until 4W→RS-232 conversion complete before cutting over to MPLS.
6 | RTU Migration | DRD RTU Cutovers — Both Sites (only 2 DRD sites exist — both in Phase 1) | John's relay team / Jay | Jun 23 2026 | Not Started | 0% | Depends on Step 5 | Only 2 DRD RTU sites exist in the entire project. Both must be completed in Phase 1. No Phase 2/3 deferral possible.
7 | PAR | PAR — Chakrapani (Chok) Team: Confirm design status all 6 sites: Northport, 5HK, Melville, 7Z, 2H, 2R | Jay → Chakrapani | URGENT — this week | In Progress | 25% | NO | CRITICAL OPEN ITEM: Chok has NOT confirmed (1) whether he's tracking the RC-30 PO or (2) where design stands for any of 6 sites. Must get monthly forecast before next CIO touchpoint. Meeting being set with Chok + Locke + Samir.
8 | PAR | PAR — Iniven RC-30 Equipment Delivery (6 units, EO#7000002695, 8-week lead time) | Chakrapani / Procurement | ~Jun 2026 (8 wk lead) | In Progress | 25% | NO | PO confirmed ($52,500). Not a programmable device — no NERC CIP issue. Delivery timing drives Steven Bradley's installation schedule.
9 | Network | Two-Way Radio Pilot Cutover Headends: Hicksville + Melville ¦ Pilot site: Syosset | B&M / Jay | Jun 23 2026 | Not Started | 0% | Depends on Steps 4–5 | Remaining sites deferred to Phase 2/3. Only 1 pilot site in Phase 1. Headend configuration at Hicksville and Melville required first.
10 | Network | FEMA-DA Pilot Cutover Headends: Hicksville + Melville ¦ Pilot site: Syosset | B&M / Jay | Jun 23 2026 | Not Started | 0% | Depends on Steps 4–5 | Remaining sites deferred to Phase 2/3. 1 pilot site in Phase 1.
11 | Network | PTT Protection Pilot — Phase 1 Sites | B&M / Jay / Relay team | Jun 23 2026 | Not Started | 0% | Depends on Steps 4–5 | Pilot scope to be confirmed per site survey. Some Phase 1 sites may need Phase 2/3 revisit.
12 | Network | Substation Security Pilot Headends: Hicksville + Melville ¦ Pilot site: Ruland Road | B&M / Jay | Jun 23 2026 | Not Started | 0% | Depends on Steps 4–5 | Remaining sites deferred to Phase 2/3. 1 pilot site (Ruland Road) in Phase 1.
13 | PAR | PAR — Steven Bradley / Johnny team Installation & testing at 6 PAR sites | Steven Bradley / Johnny team | Aug–Dec 2026 | Not Started | 0% | Depends on Steps 7–8 | Cannot start until Chok design complete + RC-30 equipment delivered. REVISED cost: 1,056 hrs × ~$185/hr = $195,600 (down from $494K original). Separate from RTU relay cutovers.
14 | Engineering | B&M Phase 1 Construction Support Coordinator (B&M on-site through Jan 2026 — COMPLETE) Phase 2 CSC starts Aug 2026 | Ethan Koch / Alex Lenox (B&M) | COMPLETE | Complete | 100% | N/A | Phase 1 B&M construction support coordinator Aug 2025–Jan 2026 complete. Phase 2 CSC starts Aug 2026 (new milestone on Phase 2 SOW).
SECTION B — PHASE 1 ENGINEERING PACKAGES (31 Sites) ¦ ALL IFR & IFC = ISSUED ¦ As-Builts → Phase 3
✅ ALL 31 Phase 1 IFRs ISSUED ¦ ✅ ALL 31 Phase 1 IFCs ISSUED ¦ ★ As-Builts (31 sites × $1,192 = $36,952) DEFERRED to Phase 3 ¦ B&M Phase 1 Construction Support Coordinator: COMPLETE (Aug 2025–Jan 2026)
SECTION C — PHASE 1 COST BREAKDOWN
# | Vendor | Service / Milestone | SOW Ref | Contract Value | Status | 2025 Spend | 2026 Spend | Notes
1 | Hawkeye | Phase 1 SOW — Base Contract All 5 invoiceable milestones (Ph0+M1+M2+M4+M6) 33 sites | MA#8447 / PSEG Bid#231567 | 333900 | Mostly Paid | 267120 | 66780 | 6 milestones × $66,780 = $400,680. Milestone 6 (Decommission, $66,780) = Phase 3. Milestones Ph0+1+2+4 = $267,120 (2025). M6 deferred to Phase 3 ($66,780).
2 | Hawkeye | Addendum 1 — Work Directives 1,2,3,4,5 & 9 Racks, antennas, subpanel, fiber jumpers, inner duct (WD1-5: Oct 2025 = $49,361 ¦ WD9: Nov 2025 = $19,532) | Addendum 1 — Dec 15 2025 | 68893 | Paid | 68893 |  | WD1: Racks $13,075 WD2: Antennas $5,053 WD3: Subpanel $11,942 WD4: Fiber jumpers $4,890 WD5: Melville/Oakwood OT support $14,402 WD9: Inner duct at 9 sites $19,532. All paid 2025.
3 | Hawkeye | Revised Phase 1 Total (Base + Addendum 1) [EXCLUDING Milestone 6 Decommission → Phase 3] |  | 335993 | Mostly Paid | 336013 | 66780 | Base $333,900 + Addendum $68,893 = $402,793 total. Less M6 decommission ($66,780) = $335,993 Phase 1 operational spend.
4 | B&M | Phase 1 Staging Support (Milestone 1) Card slotting, SFP install, staging test plan, network connectivity/firmware/control plane validation | B&M SOW v03 — Milestone 1 | 57300 | Paid | 57300 |  | Completed Aug 22 2025. $57,300 fixed. Included staging test plan: BGP, SyncE, QoS, BFD, VPRN, Epipe, Cpipe tests.
5 | B&M | Phase 1 Construction Support Coordinator (Milestone 2) On-site Aug 2025–Jan 2026, up to 45 hrs/wk Ethan Koch field coordination, RFI management, daily reports | B&M SOW v03 — Milestone 2 | 368100 | Paid | 368100 |  | $61,350/month × 6 months (Aug–Jan). COMPLETE. Ethan Koch on-site daily during Phase 1 construction.
6 | B&M | Phase 1 PM Service (Alex Lenox) $5,500/month project coordination | B&M SOW v03 — PM | 66000 | In Progress | 33000 | 33000 | $5,500/mo × 12 months. Jan–Jun 2026 portion = $33,000 still running.
7 | Nokia | Phase 1 Equipment 31 Nokia 7705 SAR-8 nodes + cards + SFPs [DELIVERED & PAID — all in 2025] | PO7000001811 / PO7000001841 | 733293 | PAID/DELIVERED | 733293 |  | ALL Phase 1 AND Phase 2 equipment on same master PO $1,899,000. Phase 1+2 delivery = $733,293 paid.
8 | PAR | Iniven RC-30 Equipment — 6 PAR sites [PO EO#7000002695 — CONFIRMED] | EO#7000002695 | 52500 | Ordered |  | 52500 | $52,500. PO placed by Chakrapani. 8-week lead time. Delivery ~Jun 2026.
9 | PAR | PAR Engineering — Chakrapani (Chok) team Design + procurement + test (6 sites) ⚠ FORECAST INFLATED | Internal — Chok team | 240000 | In Progress | 5000 | 235000 | FORECAST: 1,200 hrs × $200 = $240K. ACTUAL TO DATE: ~$5K only. Meeting being set to get real monthly forecast. Expect MAJOR reduction.
10 | PAR | PAR Installation — Steven Bradley / Johnny team 6 sites — install + test Iniven RC-30 [REVISED from $494K → $195,600] | Internal — Steven's team | 195600 | Not Started |  | 195600 | REVISED: 144 hrs × 5 sites + supervision = 1,056 hrs × ~$185/hr = $195,600. Cannot start until Chok design done + RC-30 delivered (~Aug 2026).
11 | Internal | Relay Team — RTU Circuit Cutovers Phase 1 John's team — all Phase 1 sites | Internal PSEG | 150000 | Not Started |  | 150000 | Estimate for Phase 1 relay team cutovers only (separate from PAR). Actuals TBD per site.
PHASE 1 TOTAL (ALL VENDORS + PAR + RELAY) |  |  |  | 2265586 |  | 1532706 | 732880 | ⚠ Chok PAR $240K inflated — actual ~$5K. Real cost to be confirmed this week.

## Phase 2 — Steps & Cost
PRJ13797 – JMUX Replacement ¦ PHASE 2 — WHAT NEEDS TO BE DONE ¦ 36 Sites ¦ Aug–Sep 2026
Construction Start: Aug 5 2026 ¦ Deployment Complete: Sep 28 2026 ¦ All IFRs due: Jun 29 2026 ¦ All IFCs due: Jul 13 2026
SECTION A — PHASE 2 STEPS IN SEQUENCE
# | Workstream | Step / Action Required | Owner | Target Date | Status | % Done | Blocker? | Notes
1 | Engineering | Complete all remaining Phase 2 IFRs 36 sites total — rolling schedule Jan–Jun 2026 FINAL DEADLINE: Jun 29 2026 | B&M (Ethan Koch) | Jun 29 2026 | In Progress | 40% | NO | IFRs completed so far: 2H, 2K, 2KB, 2R, 2R1, 2RB, 2WB, 2ZB, 3J, 7BH, 7J, 7W, 7XM, 7J, Sterling, Bohemia, Berry St, Kings Hwy + several others. Still outstanding per dashboard: 5HK Hicksville, 4M Baldwin (In Review), 4M1 Baldwin Shelter (In Review), 6K State School (Submitted), 6U Ruland, 7M MacArthur, 7UM South Farmingdale, 8AX Patchogue, 8AX1 Patchogue Shelter, 7H Babylon, 7H1 Babylon Shelter, 7D West Babylon, 7D1 W.Babylon Shelter, 7RM Bayport, 7R Sayville, DO Brentwood, DO Hewlett HQ, 6H Hauppauge, 6H1 Hauppauge Shelter, 7Z Lindenhurst, 6S Kings Hwy, ACC, 6H State School + others.
2 | Engineering | Complete all Phase 2 IFCs (sealed by NY PE) 36 sites — FINAL DEADLINE: Jul 13 2026 | B&M (Ethan Koch) | Jul 13 2026 | In Progress | 25% | Depends on Step 1 | IFC follows IFR by ~2 weeks per site. IFCs issued so far: 2H, 2K, 2KB, 2R, 2R1, 2RB, 2WB, 2ZB, 3J, 7BH, 7J, 7W, 7XM, Sterling, Bohemia, Berry St, Kings Hwy. Remaining IFCs to track per B&M schedule in SOW Section 2.2.
3 | Construction | Hawkeye Site Surveys — Phase 2 (pre-construction) On-site: cable types, power verification, rack space per IFC | Hawkeye (Vinny Montano) | May–Jul 2026 | In Progress | 30% | Needs IFC per site | Vinny started site surveys week of May 18 2026. Surveys running in parallel with IFC completion. Must be done before installation mobilization. 3 mobilisations planned per site.
4 | Procurement | Confirm Phase 2 equipment BOM with Ethan/Tim (CWDM cards, Eltek PSUs, accessories from Presidio) | Jay / Ethan Koch | Jun 2026 | Not Started | 0% | NO | Nokia Phase 2 equipment delivered and paid ($733,293). Remaining accessories: ~8-10 CWDM cards (~$15K) + Eltek PSUs (~$10K) from Presidio. Confirm exact count once first IFC packages reviewed.
5 | Construction | Hawkeye Staging & Assembly (Milestone Ph0) Receive all Phase 2 Nokia nodes, rack, card-install, load firmware, burn-in & test at Hawkeye lab | Hawkeye (Robert Kenney / Joel Velez) | Jun–Aug 2026 | Not Started | 0% | Needs all equipment on hand | Hawkeye SOW Ph2 Milestone Ph0 = $100,170. All 36 nodes assembled and tested in lab before shipping to substations. B&M provides: card slotting requirements, fiber connectivity details, chassis labelling.
6 | Construction | Hawkeye Installation — All 36 Phase 2 Sites (Milestone 2: Nokia SAR-8, CWDM, Eltek PSU, RS-232 patch panel, fiber, CAT6, 4-wire VF) CONSTRUCTION START: Aug 5 2026 | Hawkeye (Vinny Montano / field teams) | Aug–Sep 2026 | Not Started | 0% | Needs: IFCs ✓, staging ✓, site surveys ✓ | Hawkeye SOW Ph2 Milestone 2 = $80,136. 3 mobilisations per site. Install per IFC: power up, basic checklist, notify PSEG Relay site ready for migration. Construction start Aug 5 2026, target completion Sep 28 2026.
7 | Network | B&M Phase 2 Construction Support Coordinator (On-site Aug–Dec 2026, up to 45 hrs/wk) Field coordination, RFI response, daily reports | B&M (Ethan Koch / field rep) | Aug–Dec 2026 | Not Started | 0% | Needs construction to start | B&M SOW Ph2 Milestone 2 (Phase 2) = $382,824 (~$61,350/mo × ~6 months). On-site coordinator responds to Hawkeye field questions, tracks construction vs IFC, submits daily reports.
8 | RTU Migration | PSEG Relay Team — Phase 2 RTU Circuit Cutovers (migrate all Phase 2 JMUX circuits to Nokia MPLS) Separate from PAR | John's relay team / Jay | Aug–Sep 2026 | Not Started | 0% | Needs installation complete per site | After Hawkeye installs and tests each site, relay team migrates circuits. Cannot retire JMUX until ALL phases complete. Phase 2 relay team estimate: ~$200-250K (actuals TBD per site).
9 | Network | Two-Way Radio, FEMA-DA, Substation Security, PTT — remaining Phase 2 sites (after Phase 1 pilots) | B&M / PSEG / Relay team | Sep 2026 | Not Started | 0% | Depends on Phase 1 pilots first | Phase 1 pilots (Steps 9-12 in Phase 1) establish the template. Phase 2 rolls out at scale across all 36 sites.
10 | NMS / NSP | Build Phase 2 Nodes into NSP GUI (36 Phase 2 Nokia nodes configured in Nokia NSP management system) | Lee Blackman / Rahiq / Brianna | Jul–Aug 2026 | Not Started | 0% | Needs IFCs complete | Lee/Rahiq/Brianna built all 31 Phase 1 nodes by Apr 23. Same process for Phase 2. Can start as soon as IFC packages are finalized — no need to wait for physical installation.
11 | Engineering | Sign off on Phase 2 Go-Live (Hawkeye Milestone 4) (all 36 sites installed, tested, relay migration complete) | Vic Vohra / Jay / Ahsan | Sep–Oct 2026 | Not Started | 0% | Depends on Steps 6–9 | Hawkeye SOW Ph2 Milestone 4 = $80,136. Formal go-live acceptance by PSEG. After sign-off, Hawkeye can invoice Milestone 4 and B&M can invoice final construction support.
SECTION B — PHASE 2 ENGINEERING PACKAGES (36 Sites) ¦ IFR/IFC Status from Live Dashboard
# | Site Code | Site Name | Phase | IFR Status | IFR Date | IFC Status | IFC Date | Notes
1 | 2H | Far Rockaway | Phase 2 | IFR Issued | Feb 23 | IFC Issued | Mar 9 | Complete
2 | 2K | Valley Stream | Phase 2 | IFR Issued | Feb 23 | IFC Issued | Mar 9 | Complete
3 | 2KB | Cedarhurst | Phase 2 | IFR Issued | Feb 23 | IFC Issued | Mar 9 | Complete
4 | 2R | Hewlett | Phase 2 | IFR Issued | Feb 23 | IFC Issued | Mar 23 | Complete
5 | 2R1 | Hewlett Shelter | Phase 2 | IFR Issued | Feb 23 | IFC Issued | Mar 23 | Complete
6 | 2RB | Green Acres | Phase 2 | IFR Issued | Apr 21 | IFC Issued | Apr 21 | Complete
7 | 2WB | Barrett Power Plant | Phase 2 | IFR Issued | Apr 6 | IFC Issued | Apr 6 | Complete
8 | 2ZB | Barrett PS (EF Barrett) | Phase 2 | IFR Issued | Apr 20 | IFC Issued | Apr 20 | Complete
9 | 3J | Whiteside | Phase 2 | IFR Issued | Apr 27 | IFC Issued | — | IFC pending
10 | 4M | Baldwin | Phase 2 | In Review | — | Not Started | — | ⚠ OVERDUE — due May 4
11 | 4M1 | Baldwin Shelter | Phase 2 | In Review | — | Not Started | — | ⚠ OVERDUE — due May 4
12 | 6H | Hauppauge | Phase 2 | IFR Issued | Apr 20 | Not Started | — | IFC due Jun 9
13 | 6H1 | Hauppauge Tower Shelter | Phase 2 | IFR Issued | Apr 20 | Not Started | — | IFC due Jun 9
14 | 6K | State School | Phase 2 | Submitted | — | Not Started | — | IFR in review
15 | 6S | Kings Hwy | Phase 2 | IFR Issued | Mar 31 | IFC Issued | Mar 31 | Complete
16 | 6U | Ruland Road | Phase 2 | Not Started | — | Not Started | — | Due Jun 23
17 | 7BH | Bohemia | Phase 2 | IFR Issued | Apr 21 | IFC Issued | Apr 21 | Complete
18 | 7D | West Babylon | Phase 2 | Not Started | — | Not Started | — | Due Jun 23
19 | 7D1 | West Babylon Shelter | Phase 2 | Not Started | — | Not Started | — | Due Jun 23
20 | 7H | Babylon | Phase 2 | Not Started | — | Not Started | — | Due Jun 30
21 | 7H1 | Babylon Shelter | Phase 2 | Not Started | — | Not Started | — | Due Jun 30
22 | 7J | Sterling | Phase 2 | IFR Issued | Apr 21 | IFC Issued | Apr 21 | Complete
23 | 7M | MacArthur | Phase 2 | Not Started | — | Not Started | — | Due Jul 8
24 | 7R | Sayville | Phase 2 | Not Started | — | Not Started | — | Due Jul 8
25 | 7RM | Bayport | Phase 2 | Not Started | — | Not Started | — | Due Jul 8
26 | 7UM | South Farmingdale | Phase 2 | Not Started | — | Not Started | — | Due Jul 8
27 | 7W | Berry St. | Phase 2 | IFR Issued | Apr 21 | IFC Issued | Apr 21 | Complete
28 | 7XM | Great River | Phase 2 | IFR Issued | — | Not Started | — | IFC pending
29 | 7XM1 | Great River Shelter | Phase 2 | IFR Issued | — | Not Started | — | IFC pending
30 | 7Z | Lindenhurst | Phase 2 | In Progress | — | Not Started | — | ⚠ OVERDUE — due Apr 27
31 | 8AX | Patchogue | Phase 2 | Not Started | — | Not Started | — | Due Jul 8
32 | 8AX1 | Patchogue Shelter | Phase 2 | Not Started | — | Not Started | — | Due Jul 8
33 | 5HK | Hicksville Primary | Phase 2 | Not Started | — | Not Started | — | Due Jul 22
34 | D.O. | Brentwood D.O. | Phase 2 | Not Started | — | Not Started | — | Due Jul 22
35 | D.O. | Hewlett Headquarters | Phase 2 | Not Started | — | Not Started | — | Due Jul 22
36 | ACC | ACC | Phase 2 | Not Started | — | Not Started | — | Due Jul 29
ENGINEERING SUMMARY: IFR Complete: 0/36 ¦ IFC Complete: 0/36 ¦ Remaining IFRs: 36 ¦ Remaining IFCs: 36 ¦ As-Builts (all 36 × $1,192 = $42,912) → PHASE 3
SECTION C — PHASE 2 COST BREAKDOWN ¦ All costs 2026 except noted
# | Vendor | Service / Milestone | SOW / PO Ref | SOW Total | Status | 2026 ($) | 2027 ($) | Notes
1 | B&M | Site Surveys — 36 Phase 2 sites (Milestone 3: $86,040 fixed) | B&M SOW v03 M3 | 86040 | Complete | 86040 |  | Completed Feb 27 2026. Fixed fee $86,040. Visual inspections + photos/video at all 36 sites.
2 | B&M | Node Design — IFR (36 sites × $16,695 = $601,020) Rolling Jan–Jun 2026 per SOW schedule | B&M SOW v03 M4 / App.D | 601020 | In Progress | 601020 |  | IFRs issued: 0/36 complete. Rolling submissions. ALL due by Jun 29 2026.
3 | B&M | Node Design — IFC (36 sites × $5,963 = $214,668) Rolling Mar–Jul 2026 per SOW schedule | B&M SOW v03 M4 / App.D | 214668 | In Progress | 214668 |  | IFCs issued: 0/36 complete. ALL due by Jul 13 2026. Sealed by NY PE.
4 | B&M | PM Service (Alex Lenox) — Phase 2 portion $5,500/mo Jul–Dec 2026 | B&M SOW v03 PM | 33000 | Not Started | 33000 |  | $5,500/mo × 6 months Jul–Dec 2026 = $33,000. Jan–Jun already in Phase 1 cost.
5 | B&M | Phase 2 Construction Support Coordinator (Milestone 2 Phase 2 — on-site Aug–Dec 2026) up to 45 hrs/wk | B&M SOW v03 M2-Ph2 | 382824 | Not Started | 382824 |  | ~$61,350/month × ~6 months. Invoiced monthly. Aug 5 2026 start. On-site daily field coordination, RFI tracking, daily reports to Jay.
6 | Hawkeye | Staging & Assembly (Milestone Ph0) All 36 Phase 2 Nokia nodes — lab burn-in & test | Hawkeye Ph2 SOW M-Ph0 | 100170 | Not Started | 100170 |  | $100,170 (25% of $400,680). Jun–Aug 2026. B&M provides card slotting + connectivity reqs.
7 | Hawkeye | Site Surveys pre-construction (Milestone 1) On-site survey: cable types, power, rack space per IFC | Hawkeye Ph2 SOW M1 | 100170 | In Progress | 100170 |  | $100,170 (25%). Vinny started May 18 2026. Running in parallel with IFC completion.
8 | Hawkeye | Installation — All 36 Phase 2 Sites (Milestone 2) Nokia SAR-8, CWDM, Eltek, RS-232 panel, fiber, CAT6, 4-wire VF | Hawkeye Ph2 SOW M2 | 80136 | Not Started | 80136 |  | $80,136 (20%). Construction start Aug 5 2026. Target Sep 28 2026. 3 mobilisations per site. Energize and basic test. Notify relay team when ready.
9 | Hawkeye | Project Ready for Go-Live (Milestone 4) All 36 sites installed + relay migration complete | Hawkeye Ph2 SOW M4 | 80136 | Not Started | 80136 |  | $80,136 (20%). Go-live sign-off by Vic/PSEG. Target Sep–Oct 2026.
10 | Nokia / Presidio | CWDM Cards + Accessories (~8-10 additional cards + Eltek PSUs) | TBD — Presidio PO | 25000 | Not Started | 25000 |  | Graybar closed. Presidio source. ~$1,500-2,000/card. BOM to be confirmed with Ethan once Phase 2 IFC reviews complete.
11 | Internal / PSEG Relay | RTU Circuit Cutovers — Phase 2 sites (John's relay team — separate from PAR) | Internal PSEG | 250000 | Not Started | 250000 |  | After Hawkeye installs each site, relay team migrates circuits. Cannot retire JMUX until all phases complete but can run parallel. Actuals TBD per site.
PHASE 2 TOTAL (B&M + HAWKEYE + RELAY + EQUIPMENT) |  |  |  | 1953164 |  | 1953164 | 0 | NOTE: As-Builts (36 × $1,192 = $42,912) and Hawkeye Decommissioning ($40,068) EXCLUDED — both in Phase 3.