## Slide 1: PRJ13797: JMUX Replacement Update Project Manager : Dhananjaya Gunaratne
March 2026

## Slide 2
JMUX Replacement: Private Field Area Network
Modernize PSEG LI’s substations communications by replacing legacy JMUX with MPLS nodes to deliver a reliable, scalable and future-ready network.
Objectives
  Engineering Services
    Detailed site surveys, rack elevations, power design, supplemental documents and as-builts
    Each of the substations are fully aligned with PSEG LI standards and stakeholder buy-off
    Phase 1 – All “As –Builts” for all Phases will be provided after the JMUX is decommissioned and removed from the network.
    Phase 2 site surveys completed in Phase 1. BMcD is working on
      Issuing (IFRs) – In Progress
      Issuing for Construction (IFC) – In Progress
Procurement & Staging
    All equipment purchased by PSEGLI and shipped to Hawkeye’s staging facility, date of delivery – Delivered
Construction and Installation Support
    BMcD to provide on-site coordination with engineering team, technical support and commissioning oversight.
    SSP document gathering for Phase 2 needs to be filled out for SSP team
    Working on remote connectivity to the nodes.
SCOPE | SUBSTATIONS | MPLS SITES | DF RTU SITES | RADIO SHELTER SITES | NOKIA MPLS NODES
PHASE 1 | 49 | 26 | 17 | 6 | 31
PHASE 2 | 45 | 26 | 12 | 7 | 26
PHASE 3 | 35 | 22 | 7 | 6 | 22
TOTAL SCOPE | 129 | 74 | 36 | 19 | 79
Goal & Objectives

## Slide 3
Phase-1
Engineering Services
Procurement and Staging
  Nokia equipment for Phase 2 has been delivered – Work Completed - 2/19/2026
  Equipment moved to new Staging location – Work Completed – 3/05/2026
  Call setup with B&M to go over equipment list for Phase 2 – 3/30/2026
Construction and Installation Support
    Cat 6 cables needs to be run to NSP in Hicksville – Work Completed
    OTDR testing from Hicksville to Syosset – Work Completed
    iLO corporate connectivity interfaces turned up at Melville and Hicksville – Work in Progress
    BGP design approved 3/16 — Lee Blackman to proceed with Melville & Hicksville
    as soon as iLO connectivity is completed – Work in Progress
    Remote access into routers (31) to configure routers as per the SSP docs – Work in Progress
    Verification of remote access to NSP from Melville and Hicksville. – Work in Progress
.
Burns & Mac - Phase 1 | Total | Completed
IFR - Issued for review design | 31 | 31
IFC - Issued for construction | 31 | 31
Highlight Project Accomplishments
Total Phase 1 scope | 
Initiation & Planning | 100%
Site Surveys | 100%
Test Plan | 100%
HLD | 100%
IFR/IFC | 100%
Procurement | 100%
Staging | 100%
Field Installation | 100%
Deployment - CWDM | 100%
Pre-Deployment Deployment - Security & Radio | 5%
Deployment - Relay/RTU Cutover | not started

## Slide 4
Phase 1 – Layer 1-3 configuration – Next steps
Mobilization | Description | Responsible Stakeholder | Present On Site | Estimated Duration/Site
Initial Installation | • Install power feeds - Completed • Power MPLS router - Completed • Install new communication cables - Completed | Hawkeye | Hawkeye, BMcD, PSEGLI | 5 days
Fiber Integration | • JMUX OC-48 Circuits & Nokia MPLS over CWDM filters - Completed • Establish new MPLS parallel links - Completed • Establish Nokia parallel network & connectivity - Completed | PSEGLI | BMcD, PSEGLI | 1 Week
Layer 3 Connect | • Establish Ethernet circuits with Nokia MPLS in paralled with JMUX where possible • Security • FEMA DA • Two-way Radio • DSCADA • MicroPAQ | BMcD, PSEGLI | BMcD | 5 days
Layer 1 | • Cutover of relay and RTU circuits from JMUX to MPLS • Cutover any other circuits (PAR, DRD, etc.) as possble • Only RTUs/Circuits with no dependency on other JMUX rings | PSEGLI (Relay) | BMcD, PSEGLI | 5 days

## Slide 6
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Survey | IFR | IFC | Construction | Deployment
1 | 7RM Bayport | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
2 | 7R Sayville | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/23/26
3 | 7XM Great River | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
4 | 7XM Great River Radio Shelter | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
5 | 6H Hauppauge | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
6 | 6H Hauppauge Tower | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
7 | 6S Kings Hwy | Complete | Fri 3/13/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
8 | Brentwood DO | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 9/2/26 | Fri 9/25/26
9 | 7H Babylon | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Mon 9/21/26
10 | 7H Babylon Radio Shelter | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Tue 9/22/26
11 | 7D West Babylon | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/12/26 | Mon 9/21/26
12 | 7D West Babylon Radio Shelter | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/19/26 | Mon 9/21/26
13 | 7W Berry St | Complete | Mon 3/30/26 | Tue 6/23/26 | Wed 8/19/26 | Mon 9/23/26
14 | 3J Whiteside | Complete | Mon 4/6/26 | Mon 5/4/26 | Wed 8/12/26 | Mon 9/14/26
15 | 2K Valley Stream | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26

## Slide 7
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
16 | 2RB Green Acres | Complete | Mon 3/30/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
17 | Hewlett DO | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Fri 9/25/26
18 | 2ZB EF Barrett PS Inside | Complete | Mon 3/23/26 | Mon 4/20/26 | Wed 8/5/26 | Mon 9/14/26
19 | 2WB Barrett Outside | Complete | Mon 3/23/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
20 | 5HK Hicksville | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
21 | 2H Far Rockaway | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
22 | 2KB Cedarhurst | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
23 | 2R Hewlett | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
24 | 2R Hewlett Shelter | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
25 | 4M Baldwin | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
26 | 4M1 Baldwin Shelter | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
27 | 6K State School | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Fri 9/17/26
28 | 7BH Bohemia | Complete | Fri 3/13/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
29 | 7M MacArthur | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/22/26

## Slide 8
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
30 | 8AX Patchogue | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
31 | 8AX Patchogue Shelter | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
32 | 7Z Lindenhurst | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
33 | 7J Sterling | Complete | Mon 3/30/26 | Tue 6/9/26 | Wed 8/26/26 | Mon 9/22/26
34 | 7UM South Farmingdale | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
35 | ACC | Complete | Tue 6/9/26 | Wed 7/8/26 | Tue 9/8/26 | Mon 9/28/26
36 | 6U Ruland | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26

## Slide 9
Schedule Status
Overall: 🟡 Yellow | Recovery Plan in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Root Causes:
• SSP documentation delays (security review queue)
• CMDB update coordination time
Recovery Actions:
BGP design approved 3/16 ✅ → Lee Blackman change docs for Melville & Hicksville → NSP install (critical path, Nokia) → remote BGP config 31 sites → App cutovers → RTU cutovers → Phase 1 close Jun 2026
"Review the initial project plan vs new plan to determine the SPI." — Vik SPI = 0.76 (Yellow). NSP is sole remaining blocker. Phase 1 construction 100% done; deployment micro-phase ~5%. June 2026 revised target.
Phase 2 IFR/IFC design on track.
SCHEDULE PERFORMANCE INDEX (SPI)
0.00
0.50
0.75
1.00
1.25
1.50
2.00
●
Below 0.70 — Critical
●
0.70–0.90 — Yellow
●
0.90–1.10 — On Track
●
Above 1.10 — Ahead
--- February 2026 : 0.75 (Orange)
╌╌ January 2026 : 1.00 (Gray)
--- March 2026 : 0.76 (Yellow ↓)
Week | Dates | Planned site (PV) | Actual Sites Completed (EV) | Weekly SPI | Culmative SPI | Key Notes
Northport Fuse issue | 2/26/2026 |  |  |  |  | 
OTDR Testing from Syosset to Hicksville, link now active | 3/9/2026 |  |  |  |  | 
NSP cable run and terminated | 3/10/2026 |  |  |  |  | 
BGP design approved | 3/16/2026 |  |  |  |  | 
Moved all eqpt to new Hawkeye trailer for future staging . | 3/10/2026 |  |  |  |  | 

## Slide 10
Financials (2024-2026)

## Slide 11
Current Risk
  Legacy JMUX equipment old and delicate. Potential for Outage.
      Ran into faulty connectors that are over25 years old and not readily available with vendors.
      Potential brittle fiber patch panels, Face plates, connectors and cables.
  Weather delay and delay in installing the equipment at sub-station (tracking weekly).
  Other major substation project conflicts.
Next Steps
Confirm stable remote access after cabling/OTDR so we can shift to “remote-first” execution.
Start router configuration on the powered routers for Ring 1 and Ring 6 (remote workstream), with standard config + validation.