## Slide 1
Next Steps & Current Risks
PRJ13797: JMUX Replacement | PSEG Long Island | April 2026
📋 Next Steps
1
Work with B&M to test the RTU circuit that was run by CNI team.
2
Make sure all Phase 1 nodes are built into the network GUI and can be accessed remotely. Also need to check that all routers are configured as per SSP.
3
Complete testing on test RTU and work with B&M to go over MOP to move production RTU.
4
Follow up with Hawkeye to make sure the site surveys are scheduled for Phase 2 sites. 9/36 IFCs sent to Hawkeye.
5
Track PAR control design and equipment ordered for 6 sites.
6
Keep tracking IFR/IFCs – 9/36 received to date.
⚠️ Current Risks
🟡
Legacy JMUX equipment old and delicate. Potential for Outage.
🟡
Ran into faulty connectors that are over 25 years old and not readily available with vendors.
🟡
Potential brittle fiber patch panels, face plates, connectors and cables.
🟡
Weather delay and delay in installing the equipment at sub-station (tracking weekly).
🟡
Potential Schedule delays due to other major substation project conflicts.
PSEG Long Island | JMUX Replacement Program | PRJ13797 | Confidential | April 2026