## Monthly Cost Breakdown
PRJ13797 — JMUX REPLACEMENT PROJECT
Cost Actuals & Forecast — Monthly Breakdown ¦ As of May 12, 2026 ¦ CONFIDENTIAL
Cost Category / Line Item | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | TOTAL 2026 | 2027 (est) | GRAND TOTAL
A. PAR CIRCUIT MIGRATION — Phase 2 (Unbudgeted New Scope)
RC-30 Equipment — Iniven (6 units @ ~$10K ea) |  | 30000 | 30000 | [5 empty] | 60000 |  | 60000
C37.94 Protocol Card — Northport (bundled Ph2 PO) |  | 5000 | [6 empty] | 5000 |  | 5000
Chakrapani Team — Engineering Design (6 sites) | 20000 | 40000 | 60000 | 60000 | 40000 | 20000 |  |  | 240000 |  | 240000
Johnny's Relay Team — Installation Labor (6 sites) |  |  |  | 80000 | 120000 | 80000 | 20000 |  | 300000 |  | 300000
PAR TOTAL
B. PHASE 3 ENGINEERING — Accelerated into Phase 2 Staging
Hawkeye Site Surveys — 31 Ph3 sites (in existing SOW) |  |  |  | 30000 | 30000 | 20000 |  |  | 80000 |  | 80000
B&M Engineering — Ph3 IFR/IFC Design (31 sites) |  |  |  | 100000 | 150000 | 150000 | 100000 | 100000 | 600000 | 400000 | 1000000
Nokia Equipment Pre-Order — Ph3 Nodes (Q3 2026 PO) |  |  |  | 150000 |  |  |  |  | 150000 |  | 150000
PHASE 3 ACCELERATION TOTAL
C. BASELINED SCOPE — On Track (Reference Only)
B&M Engineering — Phase 1 & 2 (baselined) | 80000 | 80000 | 80000 | 80000 | 60000 | 40000 | 20000 | 20000 | 460000 |  | 460000
Nokia Equipment — Phase 2 Nodes (26 nodes, on order) |  | 200000 | 200000 | [5 empty] | 400000 |  | 400000
Hawkeye Construction — Phase 2 (Aug start) |  |  |  | 200000 | 250000 | 200000 | 100000 | 50000 | 800000 |  | 800000
Graybar Ancillary Equipment — Phase 2 | 20000 | 30000 | 20000 | 10000 |  |  |  |  | 80000 |  | 80000
Nokia Training — First Week June 2026 |  | 30000 | [6 empty] | 30000 |  | 30000
BASELINED SCOPE TOTAL
GRAND TOTAL — ALL SCOPE
NOTES & ASSUMPTIONS
1. Actuals to date: $0 for PAR and Phase 3 acceleration — no charges posted yet as of May 12, 2026.
2. PAR CRITICAL GAP: Chad's current forecast includes only $120K (Apr–Jun) for equipment + design. Relay labor ($200K–$495K) is NOT yet in Chad's forecast. Reconciliation meeting required week of May 18.
3. Phase 3 engineering costs assume B&M quote of $900K–$1.29M total. $600K allocated to 2026; $400K to 2027.
4. Chakrapani design rate: $115.34/hr (under audit). Johnny relay team rate: $1,100–$1,200/hr.
5. Nokia equipment pre-order timing assumes PO placed Q3 2026 to meet Phase 3 construction schedule.
6. All numbers are estimates pending Chad/B&M/Hawkeye confirmed quotes by end of May 2026.
7. Total projected variance: -$668K (total project) / -$797K (2026 capital only).

## PAR Site Detail
PAR CIRCUIT MIGRATION — SITE-BY-SITE COST & STATUS
PRJ13797 ¦ As of May 12, 2026
Site | Substation ID | RC-30 Ordered | RC-30 PO# | Est. Delivery | Design Status | Design Owner | Equipment ($) | Design ($) | Install Labor ($)
Northport | Northport | Yes | TBD | TBD (8-wk) | In Progress | TBD | 15000 | 5000 | 40000
Hicksville (5HK) | 5HK | Yes | TBD | TBD (8-wk) | Not Started | TBD | 10000 | 5000 | 40000
Melville | Melville | Yes | TBD | TBD (8-wk) | Not Started | TBD | 10000 | 5000 | 40000
Lindenhurst (7Z) | 7Z | Yes | TBD | TBD (8-wk) | Not Started | TBD | 10000 | 5000 | 40000
Far Rockaway (2H) | 2H | Yes | TBD | TBD (8-wk) | Not Started | TBD | 10000 | 5000 | 40000
Hewlett (2R) | 2R | Yes | TBD | TBD (8-wk) | Not Started | TBD | 10000 | 5000 | 40000
TOTAL — ALL 6 SITES
NOTE: Northport equipment includes additional $5,000 for C37.94 protocol card. All install labor estimates based on $1,100–$1,200/hr Johnny team rate. All numbers pending Chakrapani design confirmation.

## Variance Dashboard
BUDGET VARIANCE DASHBOARD ¦ PRJ13797 ¦ May 12, 2026
Category | Original Budget | Actuals to Date | Forecast to Complete | Projected Final | Variance
PAR Migration (new scope) | 35000 | 0 | 530000 | 530000 | -495000
Phase 3 Engineering (accelerated) | 0 | 0 | 600000 | 1000000 | On Track / TBD
B&M Engineering (Phase 1+2) | On Track / TBD | On Track / TBD | On Track / TBD | On Track / TBD | 0
Nokia Equipment (Phase 1+2) | On Track / TBD | On Track / TBD | On Track / TBD | On Track / TBD | 0
Hawkeye Construction | On Track / TBD | On Track / TBD | On Track / TBD | On Track / TBD | 0
Graybar Ancillary | On Track / TBD | On Track / TBD | On Track / TBD | On Track / TBD | 0
Labor Overcharges (PQA/relay/assess.) | On Track / TBD | On Track / TBD | On Track / TBD | On Track / TBD | On Track / TBD
TOTAL PROJECTED VARIANCE | Baselined | $0 actuals | ~$1.13M+ | ~$1.53M+ | -$668K total -$797K 2026 cap
OPEN ITEMS REQUIRING LEADERSHIP DECISION
1. PAR Funding Approval — $530K Change Request required. NERC-CIP mandatory. No alternative path.
2. Phase 3 Budget Acceleration — Confirm Ph3 engineering ($900K–$1.29M) can be front-loaded into 2026 capital.
3. Chad Reconciliation — Week of May 18. Add $495K relay labor to PAR forecast.
4. Chakrapani Confirmation — Design owners unassigned for 5 of 6 PAR sites. RC-30 PO# and delivery date unknown.