## Project Financial Summary
PRJ13797 — JMUX REPLACEMENT ¦ PROJECT FINANCIAL SUMMARY BY CONTRACTOR ¦ ALL PHASES
Source: Chad Controller Workbook + B&M SOW + Hawkeye SOW + Vic call May 18 2026 ¦ ★PCR = pending PCR approval ¦ As of May 19 2026
# | CONTRACTOR | WHAT THEY HAVE TO DO | P1 | P2 | P3 | 2025 | 2026 | 2027 | TOTAL
1 | MATERIAL (Equipment & Hardware)
2 | Nokia / Presidio | Nokia SAR-8 MPLS nodes Phase 1: 31 nodes (complete ✅) ¦ Phase 2: 36 nodes ¦ Phase 3: ~31 nodes Includes licenses, SFPs, management modules | ✓ | ✓ | ✓ | 1412400 | 733293 | 963000 | 3108693
3 | Presidio / Graybar | CWDM Cards (mux/demux per site) Ordered per IFC requirements — one set per substation | ✓ | ✓ | ✓ |  | 25000 | 20000 | 45000
4 | Various | Other: Power supplies, connectors, patch cables Eltek PSUs, fiber jumpers, misc rack hardware | ✓ | ✓ | ✓ |  | 30000 | 10000 | 40000
| MATERIAL SUBTOTAL |  |  |  |  | 1412400 | 788293 | 993000 | 3193693
5 | B&M (Burns & McDonnell) — Engineering & Construction Management
6 | B&M — Alex Lennox | PM Service $5,500/month Project coordination, schedule, scope tracking across all phases | ✓ | ✓ | ✓ | 66000 | 66000 | 22000 | 154000
7 | B&M — Ethan Koch | Site Surveys — Phase 1 (COMPLETE ✅) On-site visits: measure rack space, cable runs, power, fiber. Feeds IFR. 36 sites completed. | ✓ |  |  | 86040 |  |  | 86040
8 | B&M — Ethan Koch | Site Surveys — Phase 2 Same scope as Ph1. Vinny (Hawkeye) also doing pre-construction survey after each IFC is issued. B&M survey feeds IFR design. 36 sites. |  | ✓
9 | B&M — Ethan Koch | Site Surveys — Phase 3 (★PCR — stays in Phase 3) 31 sites. Survey before IFR. Feeds MPLS design. |  |  | ✓ |  |  | 86000 | 86000
10 | B&M | Staging Support — Phase 1 (COMPLETE ✅) One week only (NOT two weeks per SOW). Lab rack-up, verify Nokia configs, port mapping, test. ★ SOW states 2 weeks — actual was 1 week. Phase 2 and 3 budgeted at 1 week each. | ✓ |  |  | 51250 |  |  | 51250
11 | B&M | Staging Support — Phase 2 One week (corrected from SOW 2-wk assumption). Lab verification of 36 nodes before Hawkeye ships to substations. ~$25,625. |  | ✓ |  |  | 25625 |  | 25625
12 | B&M | Staging Support — Phase 3 (★PCR) One week. ~31 nodes. ~$25,625. |  |  | ✓ |  |  | 25625 | 25625
13 | B&M — Nick Cianciolo | Node Design IFR+IFC — Phase 1+2 IFR = 60% design, PE-stamped. IFC = 100% issued-for-construction drawings. 39 sites Ph1 (done ✅) + 36 sites Ph2 (final IFR Jun 29 / IFC Jul 13 2026). Includes: single-line diagrams, rack elevation, cable schedule, fiber routing. | ✓ | ✓ |  | 601020 | 214668 |  | 815688
14 | B&M — Nick Cianciolo | Node Design IFR+IFC — Phase 3 (★PCR) 31 sites. Same scope as Ph1/Ph2. Feeds Hawkeye installation and PAR. Part of accelerated Ph3-into-Ph2 recovery plan. |  |  | ✓ |  |  | 450000 | 450000
15 | B&M | Node Design AS-BUILDs — Phase 1+2 Red-line mark-ups after installation complete. Final record drawings. Submitted after Hawkeye Go-Live sign-off. | ✓ | ✓ |  |  | 42912 |  | 42912
16 | B&M | Node Design AS-BUILDs — Phase 3 |  |  | ✓ |  |  | 37200 | 37200
17 | B&M — Ethan Koch | Construction Support Coordinator — Phase 1 (COMPLETE ✅) On-site daily field coordination at each substation. Coordinates Hawkeye installation, PSEG escort, RTU migration, sign-off. | ✓ |  |  | 368100 |  |  | 368100
18 | B&M — Ethan Koch | Construction Support Coordinator — Phase 2 Same scope. Starts Aug 5 2026, target complete Sep 28 2026. $61,350/month × 6 months (Aug–Jan 2027). |  | ✓ |  |  | 382824 |  | 382824
19 | B&M — Ethan Koch | Construction Support Coordinator — Phase 3 (★PCR) Same scope. ~$264K estimate. |  |  | ✓ |  |  | 264000 | 264000
20 | B&M | Phase 3 MPLS Detail Design (accelerated into Ph2) ★PCR 31-site full MPLS network design pulled forward from 2027 into 2026. Recovers 5-month schedule impact from PAR scope discovery. |  | ✓ |  |  | 360000 |  | 360000
| B&M SUBTOTAL |  |  |  |  | 1172410 | 1091029 | 884825 | 3148264
21 | HAWKEYE — Field Installation & Decommissioning
22 | Hawkeye — Vinny | Pre-Construction Site Survey (after IFC issued) Visits each substation with IFC drawings. Measures: cable runs, conduit, rack space, power feeds, fiber connection points. Orders cables, conduit, connectors, fiber jumpers per site. Feeds staging BOM. | ✓ | ✓ | ✓ |  | 50085 |  | 50085
23 | Hawkeye | Ordering: Cables, Connectors, Fiber Jumpers, Conduit Based on IFC cable schedule + site survey measurements. Custom lengths — cannot order until Hawkeye visits site. Includes RJ45→DB25 serial patch cables for RTU connections. | ✓ | ✓ | ✓
24 | Hawkeye | Staging — Phase 1 (COMPLETE ✅ — 1 week) Lab assembly: Nokia SAR-8 nodes racked, cards slotted, labeled. Power-on test, port-to-port verify. B&M provides connectivity matrix. ★ 1 WEEK ONLY — not 2 weeks as SOW states. | ✓ |  |  | 100170 |  |  | 100170
25 | Hawkeye | Staging — Phase 2 (1 week) Same scope as Ph1. 36 nodes. Lab burn-in Jul–Aug 2026. B&M provides card-slotting requirements per IFC. ★ 1 WEEK — not 2 weeks. Budgeted accordingly. |  | ✓ |  |  | 100170 |  | 100170
26 | Hawkeye | Staging — Phase 3 (★PCR — 1 week) ~31 nodes. Estimated 2027. |  |  | ✓ |  |  | 100170 | 100170
27 | Hawkeye — 3 visits/site | Installation at Each Substation — Phase 1 (COMPLETE ✅) Visit 1: Deliver & rack equipment, run conduit, pull cables. Visit 2: Terminate fiber, patch cables, connect serial adapters (RTU). Visit 3: Power-on, test connectivity, notify relay team for cutover. | ✓ |  |  | 302623 |  |  | 302623
28 | Hawkeye — 3 visits/site | Installation at Each Substation — Phase 2 Same 3-visit process. 36 sites. Construction window: Aug 5 – Sep 28 2026. Includes: Nokia SAR-8 rack & stack, CWDM install, Eltek PSU, fiber termination, serial patch panels, cable tray, labeling, as-built photos. |  | ✓ |  |  | 80136 |  | 80136
29 | Hawkeye — 3 visits/site | Installation at Each Substation — Phase 3 (★PCR) Same 3-visit process. ~31 sites. 2027. |  |  | ✓ |  |  | 220000 | 220000
30 | Hawkeye | Go-Live Sign-Off — Phase 2 (Milestone M4) Final verification after relay team completes RTU cutover. Hawkeye confirms: all circuits live on Nokia, no legacy JMUX traffic. PSEG formal sign-off. Triggers M4 invoice. |  | ✓ |  |  | 80136 |  | 80136
31 | Hawkeye | Go-Live Sign-Off — Phase 3 (★PCR) Same scope. 2027. |  |  | ✓ |  |  | 100000 | 100000
32 | Hawkeye | Decommissioning — ALL Phases (Phase 3 only) After ALL phases complete on Nokia: Break down legacy JMUX equipment at each substation. De-rack, palletize, transport to PSEG warehouse. Restore substation to pre-JMUX condition (patch plates, labels, clean cable tray). 134 total sites. Cannot start until Nokia confirmed live everywhere. |  |  | ✓ |  |  | 141351 | 141351
33 | Hawkeye | WD#8 Fiber Testing + Patch Panels (2026) Elwood to North port fiber test. Already in forecast. | ✓ |  |  |  | 8229 |  | 8229
| HAWKEYE SUBTOTAL |  |  |  |  | 402793 | 318756 | 561521 | 1283070
PAR | PAR (Phase Angle Regulator) ★ NEW SCOPE — PCR REQUIRED — 6 Substations
a | Nokia / Presidio | Equipment — Iniven RC-30 (6 units × $8,750) Serial→C37.94 protocol converter. NERC-CIP compliant (not programmable). PO placed. 8-week lead time. Delivery ~June 2026. Sites: Northport, 5HK Hicksville, Melville, 7Z Lindenhurst, 2H Far Rockaway, 2R Hewlett. |  | ✓ |  |  | 52500 |  | 52500
b | Chak's Team | Relay Engineering Design — 6 sites ★CONFIRMED Vic May 18 200 hrs/site × 6 sites × $200/hr = $240,000 Scope: review existing PAR protection scheme, design new C37.94 relay interface, prepare relay settings file, draft test procedures, NERC-CIP compliance review. |  | ✓ |  |  | 240000 |  | 240000
c | Steven Bradley (Relay Team) | Relay Installation, Configuration & Cutover — 6 sites ★CONFIRMED Vic May 18 ~1,298 hrs × $200/hr = $259,500 Scope: install Iniven RC-30 at each substation, wire to PAR relay contacts, configure C37.94 settings per Chak's design, end-to-end protection test, NERC-CIP commissioning, cutover from legacy to Nokia MPLS path. |  | ✓ |  |  | 259500 |  | 259500
d | Various | PAR Materials — Cables, Connectors, Misc ★CONFIRMED Vic May 18 Custom serial cables, C37.94 interface connectors, rack hardware across 6 sites. $30,000 flat estimate. |  | ✓ |  |  | 30000 |  | 30000
| PAR SUBTOTAL ★PCR★ (Equipment $52.5K + Engineering $240K + Install $259.5K + Materials $30K) | [5 empty] | 582000 |  | 582000
34 | PM / CONTROLLER / SCHEDULER
35 | Hermitage — Jay G | PM — Dhananjaya Gunaratne Overall project delivery, stakeholder management, PSEG/CIO reporting. | ✓ | ✓ | ✓ |  | 174000 | 58000 | 232000
36 | Hermitage — Ahsan | PM — Ahsan Khawaja Supporting PM, Phase 2 coordination. |  | ✓ |  |  | 257619 |  | 257619
37 | ComTec — Chad | Controller — Chad Boyett $8,400/mo Monthly forecast vs actuals, SAP tracking, PCR submissions. | ✓ | ✓ | ✓ | 67200 | 100800 | 33600 | 201600
38 | ComTec — Umair | Scheduler — Umair Mohammed $5,416/mo MS Project schedule, SPI, milestone tracking. | ✓ | ✓ | ✓ | 54160 | 67040 | 13400 | 134600
39 | ComTec — Farouk | Scheduler — Farouk Adelekan Schedule support. |  | ✓ | ✓ |  | 20000 | 6600 | 26600
40 | Hermitage — Ed S | O/S Sr. Engineer — Edward Schwartz $2,512/mo Technical oversight, design review. | ✓ | ✓ | ✓ |  | 30000 | 5000 | 35000
| PM / CONTROLS SUBTOTAL |  |  |  |  | 121360 | 649459 | 116600 | 887419
41 | INTERNAL LABOR (PSEG + Cognizant)
42 | PSEG — Multiple | PSEG Internal Labor (Rahiq, Brianna, Chok, Lok, Sameer, et al.) Network config, testing, RTU cutover, NSP administration. | ✓ | ✓ | ✓ | 82421 | 154989 | 60000 | 297410
43 | Cognizant — Lee | Lee Blackman — Sr. Network Architect $7,200/mo MPLS design review, IFR/IFC technical approval, BGP/Layer 3 design. | ✓ | ✓ |  |  | 86400 |  | 86400
44 | PSEG — Steven B | Relay Team Support — Steven Bradley (internal PSEG) ★ ZERO actuals to SAP to date. $195K in forecast. Manage relay team scheduling, coordinate Chok and Johnny's teams. Need names + hours by month before Mon May 25. | ✓ | ✓ | ✓ |  | 195000 | 30000 | 225000
| INTERNAL LABOR SUBTOTAL |  |  |  |  | 82421 | 436389 | 90000 | 608810
45 | PQA / ASSESSMENTS
46 | Cognizant / EPMO | PQA Audit — Margaret Tanner Glover Quality assurance reviews, milestone gate checks. | ✓ | ✓ | ✓ | 56330 | 40000 | 10000 | 106330
47 | PSEG | Assessments (PSEG overhead ~3.5%) PSEG IT overhead charged against project WBS. | ✓ | ✓ | ✓ | 19172 | 72737 | 20000 | 111909
| PQA / ASSESSMENTS SUBTOTAL |  |  |  |  | 75502 | 112737 | 30000 | 218239
T | TRC — Cyber Security
T1 | TRC — Raju K | Raju Khedkar — Security Architect NERC-CIP compliance review, cyber security assessment per phase. | ✓ | ✓ | ✓ | 3726 | 30000 | 5000 | 38726
| TRC SUBTOTAL |  |  |  |  | 3726 | 30000 | 5000 | 38726
★ | GRAND TOTAL — ALL CONTRACTORS |  |  |  |  | 3270612 | 4008663 | 2680946 | 9960221
| CP BUDGET (approved) |  |  |  |  | 3250000 | 2600000 | 1000000 | 6850000
| VARIANCE (Budget − EAC) ⚠ Negative = OVER BUDGET |  |  |  |  | -20612 | -1408663 | -1680946 | -3110221
★PCR items (green): PAR $582K + B&M Ph3 accel $835K + Hawkeye Ph3 $420K = ~$1.84M pending approval ¦ Staging = 1 WEEK (not 2 per SOW) ¦ Decommissioning all phases in Phase 3 only
PAR confirmed Vic May 18: RC-30 $52.5K + Engineering $240K (Chak) + Install $259.5K (Steven B) + Materials $30K = $582K ¦ Martin Gately DEPARTED — $0 2026 ¦ Phase 3 site surveys stay in Phase 3