PRJ13797 — JMUX REPLACEMENT PROJECT

Cost Actuals & Forecast Report

Prepared by: Dhananjaya (Jay) Gunaratne, Senior PM  |  Date: May 12, 2026  |  CONFIDENTIAL

EXECUTIVE SUMMARY

The JMUX Replacement Project is currently tracking a total projected budget variance of -$668K (-$797K for 2026 capital). This report details the two primary cost drivers:

1.  PAR Circuit Migration — mandatory NERC-CIP unbudgeted scope discovered during Phase 2 site surveys

2.  Phase 3 Engineering Acceleration — Phase 3 IFR/IFC design and site surveys being pulled forward into Phase 2 staging to compress schedule and avoid 2028 delays

SECTION 1 — PAR CIRCUIT MIGRATION (Grouped with Phase 2)

Description

PAR (Phase Angle Regulator) circuits control high-voltage power flow at 6 critical LIPA substations. The legacy JMUX system carried these signals via direct serial connection. The new Nokia MPLS network is IP-based — requiring physical serial-to-IP conversion devices (Iniven RC-30) at each site, plus full engineering design and relay labor for installation and cutover.

This scope was originally a Phase 3 placeholder estimated at $30,000–$40,000 in 2024. The full technical scope was discovered during Phase 2 site surveys. This work is MANDATORY for NERC-CIP compliance — there is no alternative path.

Sites Affected (6)

Northport: Unique — also requires C37.94 protocol card in addition to RC-30

Hicksville (5HK): RC-30 ordered. Design not started. Owner TBD.

Melville: RC-30 ordered. Design not started. Owner TBD.

Lindenhurst (7Z): RC-30 ordered. Design not started. Owner TBD.

Far Rockaway (2H): RC-30 ordered. Design not started. Owner TBD.

Hewlett (2R): RC-30 ordered. Design not started. Owner TBD.

PAR Cost Breakdown

| Line Item | Actuals to Date | Forecast Remaining | Total |
| --- | --- | --- | --- |
| Iniven RC-30 Equipment (6 units @ ~$10K each) PO in progress — 8-wk lead time Ordered by Chakrapani team | $0 | $60,000 | $60,000 |
| C37.94 Protocol Card (Northport only — unique requirement) To be bundled with Phase 2 Nokia PO | $0 | TBD | TBD |
| Chakrapani Team — Engineering Design (6 sites) Rate: $115.34/hr (under audit) Design not started — 5 of 6 sites Only Northport: In Progress | $0 | $240,000 | $240,000 |
| Johnny's Relay Team — Installation Labor (6 sites) Rate: ~$1,100–$1,200/hr Physical install, config, cutover Scope per site pending design | $0 | $200,000–$495,000 | $200,000–$495,000 |
| TOTAL PAR | $0 | ~$500,000–$795,000 | ~$530,000 (midpoint) |

⚠ CRITICAL GAP: Chad's current forecast includes only $120K (Apr–Jun) for equipment + design. The $200K–$495K relay labor (Johnny's team) is NOT yet in Chad's forecast. Reconciliation meeting required week of May 18.

PAR Timeline

| Milestone | Target Date | Status |
| --- | --- | --- |
| RC-30 Equipment PO Placed | April 30, 2026 | 🔴 In Progress — PO# unknown |
| RC-30 Equipment Delivery (8-wk lead) | June 2026 | ⏳ Pending |
| Chakrapani Design Complete — All 6 Sites | July 2026 | 🔴 Not Started (5 of 6) |
| Johnny's Team Installation — All 6 Sites | Aug–Sep 2026 | ⏳ Not Started |
| PAR Circuits Complete | September 2026 | 🎯 Target |

SECTION 2 — PHASE 3 ENGINEERING ACCELERATED INTO PHASE 2

Description

To avoid supply chain delays and compress the overall project schedule, Phase 3 site surveys and engineering (IFR/IFC packages) are being started during Phase 2 staging (August 2026) rather than waiting for Phase 2 completion.

Why We Are Accelerating

Nokia MPLS nodes have an 8–12 week lead time. Delaying Phase 3 engineering until after Phase 2 completes pushes Phase 3 construction into 2028.

Starting Phase 3 design in parallel with Phase 2 staging compresses the schedule by approximately 4–6 months.

Avoids double mobilization costs for Hawkeye construction crews.

Confirmed by Ethan (B&M): "As soon as Phase 2 staging begins, Phase 3 engineering can start."

Phase 3 Scope Being Accelerated

31 sites (confirmed scope). Site surveys by Hawkeye starting Aug 2026. Engineering IFR/IFC packages by Burns & McDonnell (B&M). Nokia equipment pre-order to be placed Q3 2026.

Phase 3 Cost Breakdown

| Line Item | Actuals to Date | Forecast (2026 Portion) | Total (Full Scope) |
| --- | --- | --- | --- |
| B&M Engineering — Phase 3 IFR/IFC Design 31 sites. Design starts Aug 2026 during Phase 2 staging. B&M/Hawkeye quotes pending — confirm with Chad by end of May. | $0 | $600,000 | $900,000–$1,290,000 |
| Hawkeye Site Surveys — Phase 3 31 sites. Field surveys to support B&M design. Starting week of May 18, 2026. Included in existing Hawkeye SOW. | $0 | TBD (in Hawkeye SOW) | TBD |
| Nokia Equipment Pre-Order — Phase 3 Pre-ordering to avoid 8-wk lead time delay. PO target: Q3 2026. | $0 | TBD (PO: Q3 2026) | TBD |
| TOTAL PHASE 3 ACCELERATION | $0 | ~$600,000 (2026) | ~$900K–$1.29M |

NOTE: This is a budget year timing shift. Phase 3 costs are being front-loaded from 2027 into the 2026 capital plan. Leadership approval required to confirm Phase 3 engineering budget can be accelerated into 2026 capital.

SECTION 3 — OVERALL BUDGET VARIANCE SUMMARY

| Category | Original Budget | Actuals to Date | Forecast Remaining | Variance |
| --- | --- | --- | --- | --- |
| PAR Migration (new unbudgeted scope) | $30K–$40K (2024 placeholder) | $0 | ~$530,000 | -$490,000 to -$500,000 |
| Phase 3 Engineering (accelerated into 2026) | Phase 3 budget (2027 original) | $0 | ~$600K (2026) $900K–$1.29M total | Budget year timing shift |
| B&M Engineering (Phase 1 + 2) | Baselined | On track | On track | ~$0 |
| Nokia Equipment (Phase 1 + 2) | Baselined | Ph1: Received Ph2: On order | On track | ~$0 |
| Hawkeye Construction | Baselined | Ph1: Complete | Aug 2026 start | ~$0 |
| Graybar Ancillary | Baselined | Ph1: Received | Ph2 BOM pending | ~$0 |
| Labor Overcharges (PQA/relay/assessments) | Baselined | Under audit | PCR in progress | Under review |
| TOTAL PROJECTED VARIANCE | — | — | — | -$668K total -$797K (2026 cap) |

SECTION 4 — COST CONTROL ACTIONS IN PROGRESS

PAR Change Request: $530K unbudgeted scope — Change Request to be submitted. NERC-CIP mandatory — no alternative path.

Assessment Cap: Joe Jekyll confirmed assessments capped at 3.5% of total budget. PCR "get out of jail free" cards being issued for over-cap charges.

PQA Audit: Marge Tanner (PQA) charges reviewed for potential double-billing. Escalation in progress.

Relay Labor Rate Audit: Chakrapani rate ($115.34/hr) and Johnny's team rate ($1,100–$1,200/hr) being verified against accounting. Detailed hour justification required for all future funding requests.

Chad Reconciliation: Meeting required week of May 18. Update forecast to include $495K relay labor for PAR and Phase 3 acceleration costs.

SECTION 5 — OPEN ITEMS REQUIRING LEADERSHIP DECISION

PAR Funding Approval — $530K Change Request required. Mandatory NERC-CIP compliance. No alternative.

Phase 3 Budget Acceleration — Confirm Phase 3 engineering ($900K–$1.29M) can be front-loaded into 2026 capital plan.

Chad Reconciliation Meeting — Week of May 18. Reconcile PAR relay labor gap and Phase 3 cost timing.

Chakrapani Confirmation — Design owners not yet assigned for 5 of 6 PAR sites. RC-30 PO number and delivery date still unknown. CRITICAL PATH.

PRJ13797 — JMUX Replacement Project  |  Cost Actuals & Forecast  |  May 12, 2026  |  CONFIDENTIAL