## SPI Calculator
📊 SPI CALCULATOR — PRJ13797 JMUX Replacement
Schedule Performance Index (SPI) = Earned Value (EV) ÷ Planned Value (PV)
WHAT IS SPI? (Plain English)
SPI tells you how much work you ACTUALLY completed vs. how much you PLANNED to complete by a certain date.
• SPI = 1.0 → Exactly on schedule • SPI > 1.0 → Ahead of schedule • SPI < 1.0 → Behind schedule
► ENTER YOUR NUMBERS BELOW
Description | PV — Planned Value (what you planned to finish) | EV — Earned Value (what you actually finished) | SPI = EV ÷ PV
Enter milestone / task 1 | 0 | 0
Enter milestone / task 2 | 0 | 0
Enter milestone / task 3 | 0 | 0
Enter milestone / task 4 | 0 | 0
Enter milestone / task 5 | 0 | 0
Enter milestone / task 6 | 0 | 0
Enter milestone / task 7 | 0 | 0
Enter milestone / task 8 | 0 | 0
Enter milestone / task 9 | 0 | 0
Enter milestone / task 10 | 0 | 0
TOTALS
YOUR OVERALL SPI:
STATUS:
SPI REFERENCE SCALE
Above 1.10 |  | 🔵 Ahead of Schedule
0.90 – 1.10 |  | 🟢 On Track
0.70 – 0.90 |  | 🟡 Yellow — Monitor Closely
0.50 – 0.70 |  | 🟠 Orange — Action Required
Below 0.50 |  | 🔴 Critical — Escalate to CIO/SVP

## EV & PV Deep Dive
EV & PV DEEP DIVE — How to Calculate Planned Value & Earned Value
Using real milestones from PRJ13797 JMUX Replacement — PSEG Long Island
SECTION 1: WHAT IS PLANNED VALUE (PV)?
PV = the budgeted cost (or milestone weight) of ALL work scheduled to be completed by a specific date.
Think of PV as your PROMISE to management. It's what your project schedule SAID would be done.
3 WAYS TO ASSIGN PV VALUE — Choose ONE method and stick with it
Task | METHOD 1: Milestone Count (Simplest ✅ Used on JMUX) | METHOD 2: Percentage Weight (Best for mixed-size tasks) | METHOD 3: Dollar Value (Best for budget tracking) | JMUX Used This?
BGP Design Approved | 1 milestone = 1 | 20% of network tasks | $25,000 (BGP design fee) | ✅ Method 1
Northport DC Power Complete | 1 milestone = 1 | 10% of infra tasks | $18,000 (power install) | ✅ Method 1
OTDR Test — Hicksville Link | 1 milestone = 1 | 15% of testing tasks | $8,500 (testing labor) | ✅ Method 1
NSP Fiber Run & Terminated | 1 milestone = 1 | 25% of cabling tasks | $12,000 (Hawkeye labor) | ✅ Method 1
Phase 2 IFR Packages x3 | 1 milestone = 1 | 30% of design tasks | $45,000 (BMcD design fee) | ✅ Method 1
TOTAL PV | PV = 5 (5 milestones) | PV = 100% | PV = $108,500
SECTION 2: WHAT IS EARNED VALUE (EV)?
EV = the budgeted value of work ACTUALLY completed to date. You only earn value when a task is DONE.
Think of EV as your SCORECARD. It's what you actually earned based on real completed work — not effort or time spent.
THE GOLDEN RULES OF EV — Critical for accurate SPI
✅ | RULE 1: 0% or 100% only (Binary Method) | A task is either DONE or NOT DONE. No partial credit. If BGP execution is 80% complete — EV = 0 until it's fully done. | JMUX Feb 2026: Northport ILO was blocked. It was 0% — EV = 0, not 0.5
✅ | RULE 2: Use the SAME unit as PV | If PV uses milestones, EV counts completed milestones. If PV uses dollars, EV uses the budgeted dollar value of completed work. | JMUX uses milestone count (1 per task). 3 done out of 5 = EV of 3
✅ | RULE 3: EV is based on PLANNED value — not actual cost | If a task was planned at $25K and you completed it spending $30K, EV is still $25K. Actual cost is tracked separately (CPI, not SPI). | JMUX: BGP design budgeted at $25K. Regardless of actual spend, EV = $25K when done.
✅ | RULE 4: EV can never exceed PV for a task | You cannot earn more than what was planned. Doing extra work that wasn't planned does NOT increase EV. | JMUX: Hawkeye moved Phase 2 equipment early. Not in PV — so EV = 0 for that task.
SECTION 3: FULL WORKED EXAMPLE — February 2026 (JMUX PRJ13797)
Scenario: End of February 2026. You need to report SPI to the CIO. Here is exactly how to do it.
# | Planned Milestone | PV Value (assigned at start) | Completed? (honest answer) | EV Earned (only if 100% done)
1 | Northport ILO port configuration complete | 1 | ❌ NO — DC power fuse tripping blocked all ILO work | 0
2 | OTDR test — Hicksville to Syosset link active | 1 | ✅ YES — Bad filter replaced. Link confirmed active. | 1
3 | NSP fiber cable run & terminated at Hicksville | 1 | ✅ YES — Hawkeye completed fiber run to NSP rack. | 1
4 | Phase 2 IFRs — Far Rockaway, Valley Stream, Cedarhurst | 1 | ✅ YES — Burns & McDonnell submitted all 3 packages. | 1
| TOTALS | PV = 4 | 3 tasks completed ✅ ¦ 1 task blocked ❌ | EV = 3
SPI CALCULATION: |  | SPI = EV ÷ PV = 3 ÷ 4 = 0.75 → 🟠 ORANGE — Action Required
SECTION 4: COMMON MISTAKES — What NOT to Do
❌ Mistake 1 | Giving partial EV credit | Saying 'ILO is 50% done so EV = 0.5' — WRONG. EV is 0 until the task is fully complete. | JMUX: ILO blocked in Feb. EV = 0, not 0.5. That honesty is what flagged the schedule risk.
❌ Mistake 2 | Counting effort instead of output | Saying 'we worked 40 hours on BGP so we earned 0.5' — WRONG. EV is about deliverables completed, not hours spent. | JMUX: Hawkeye spent weeks on NSP wiring. EV = 0 until fiber was run AND terminated.
❌ Mistake 3 | Changing PV mid-project without approval | Reducing PV to make SPI look better is data manipulation. If scope changes, get formal change control approval first. | JMUX: If ILO was removed from PV without a change request, SPI would look artificially good.
❌ Mistake 4 | Not updating EV regularly | SPI is only useful if updated consistently — weekly or monthly. Stale data gives stale decisions. | JMUX: Jay updates SPI monthly for CIO reporting. Weekly for internal team tracking.
PRJ13797 JMUX Replacement — PSEG Long Island ¦ PM: Jay Gunaratne ¦ Built by Sachi

## JMUX PV Examples
HOW TO CALCULATE PV — Real JMUX Project Examples (PRJ13797)
PV = the total value of work you PLANNED to complete by a specific date. Each milestone = 1 point on this project.
JANUARY 2026 — On Track
# | Planned Milestone | PV Value | EV (Done?) | Notes
1 | Complete Northport DC power installation | 1 | ✅ Done
2 | Hawkeye completes router racking at 5 Phase 1 sites | 1 | ✅ Done
3 | BGP design draft submitted to Lee Blackman | 1 | ✅ Done
4 | Phase 2 site surveys continue — 10 sites | 1 | ✅ Done
5 | Phase 1 IFC document review complete | 1 | ✅ Done
| TOTAL | PV = 5 | EV = 5 | SPI = 5/5 = 1.00
FEBRUARY 2026 — Northport DC Power Issue
# | Planned Milestone | PV Value | EV (Done?) | Notes
1 | Northport ILO port configuration complete | 1 | ❌ Not Done | ❌ DC power fuse tripping — ILO work blocked
2 | OTDR test Hicksville–Syosset link confirmed active | 1 | ✅ Done | ✅ Bad filter found & replaced. Link active.
3 | NSP fiber cabling run and terminated at Hicksville | 1 | ✅ Done | ✅ Hawkeye completed fiber run
4 | Phase 2 IFR packages — Far Rockaway, Valley Stream, Cedarhurst | 1 | ✅ Done | ✅ Submitted by BMcD
| TOTAL | PV = 4 | EV = 3 | SPI = 3/4 = 0.75
MARCH 2026 — Recovery Underway
# | Planned Milestone | PV Value | EV (Done?) | Notes
1 | iLO configuration complete at Hicksville & Melville | 1 | ❌ Not Done | ⏳ In progress — Rahiq & Brianna on-site this week
2 | BGP design approved by Vikas Vohra | 1 | ✅ Done | ✅ Approved March 16
3 | Nokia NSP equipment wiring complete at Hicksville | 1 | ✅ Done | ✅ Hawkeye completed March 24
4 | BGP Change Review Board approval | 1 | ❌ Not Done | ⏳ Target March 31 — peer review underway
5 | BGP execution at Hicksville (Apr 1) & Melville (Apr 2) | 1 | ❌ Not Done | 📅 Scheduled April 1–2
| TOTAL | PV = 5 | EV = 2 | SPI = 2/5 = 0.40
💡 PRO TIP: Each milestone = 1 point keeps it simple. You can also use dollar values (e.g. BGP config = $50K). Stay consistent throughout the project!

## Step-by-Step Guide
HOW TO CALCULATE SPI — Step by Step Guide
1 | List all milestones for the period
| What did your schedule say should be DONE by the end of this month? Write down every task, deliverable, or milestone. Be specific. | JMUX Example: BGP design approved, NSP wiring complete, ILO configured, Phase 2 surveys done
2 | Assign a value to each milestone
| Give each task a number. On JMUX we use 1 per milestone. You can also use dollar values — just be consistent. | JMUX Example: 5 milestones planned in March → PV = 5
3 | Add them all up — that is your PV
| PV = Planned Value = the total of all milestone values you planned to complete. | JMUX Example: Jan PV=5, Feb PV=4, Mar PV=5
4 | Go through the list — mark what actually got done
| Check each milestone. Did it actually get completed this period? Only count things FULLY done — partial credit = 0 on a binary scale. | JMUX Example: Feb — Northport ILO NOT done (DC power blocked). 3 out of 4 done → EV = 3
5 | Add up completed milestones — that is your EV
| EV = Earned Value = total value of work ACTUALLY completed. | JMUX Example: Feb EV = 3 (one milestone blocked by Northport power issue)
6 | Divide EV ÷ PV = SPI
| That's it. The formula is simple. The hard part is being honest about what's done. | JMUX Example: Feb SPI = 3 ÷ 4 = 0.75 → Orange (action required)
THE FORMULA: SPI = EV ÷ PV ¦ EV = work done ¦ PV = work planned