## Project Financial Summary
PRJ13797 — JMUX REPLACEMENT ¦ PROJECT FINANCIAL SUMMARY v4 ¦ ALL PHASES ¦ May 19 2026
Source: B&M SOW v0.03 (Appendix D) + Hawkeye POs + Chad Controller Workbook + Vic call May 18 2026 ¦ ★PCR = pending approval
# | CONTRACTOR | STEP / DELIVERABLE (per SOW + project plan) | P1 | P2 | P3 | 2025 | 2026 | 2027 | TOTAL
1 | MATERIAL (Equipment & Hardware)
2 | Nokia / Presidio | Nokia SAR-8 MPLS Nodes + licenses Ph1: 31 nodes (complete ✅) ¦ Ph2: 36 nodes ¦ Ph3: ~31 nodes Includes: SFPs, CSM management cards, chassis, firmware | ✓ | ✓ | ✓ | 1412400 | 733293 | 963000 | 3108693
3 | Presidio / Graybar | CWDM Cards (mux/demux) Ordered per IFC cable schedule. One set per site. | ✓ | ✓ | ✓ |  | 25000 | 20000 | 45000
4 | Various | Other: Eltek PSUs, connectors, rack hardware, fiber jumpers | ✓ | ✓ | ✓ |  | 30000 | 10000 | 40000
| MATERIAL SUBTOTAL |  |  |  |  | 1412400 | 788293 | 993000 | 3193693
5 | B&M (Burns & McDonnell) — Engineering & Construction Management ¦ SOW Total $1,370,040
6 | B&M — Alex Lennox | Step 1: PM Service ($5,500/month) Scope: Weekly status calls, schedule maintenance, stakeholder reporting, meeting minutes for all key meetings, manage all deliverables per PSEG PDLC. Ph1: Oct 2024–Jan 2026 ¦ Ph2: Feb 2026–Sep 2026 ¦ Ph3: 2027 | ✓ | ✓ | ✓ | 66000 | 66000 | 22000 | 154000
7 | B&M — Ethan Koch / Nick C. | Step 2a: Substation Site Surveys — Phase 1 (SOW CPS Milestone 3) COMPLETE ✅ Visual inspection at each building (floor level). Digital photos + video. Confirms: rack space, power, fiber connectivity, cable routing path. Output feeds IFR design. 36 Phase 1 sites. Completed 2/27/2026. SOW Payment: $86,040 | ✓ |  |  | 86040 |  |  | 86040
8 | B&M — Ethan Koch / Nick C. | Step 2b: Substation Site Surveys — Phase 2 (36 sites, rolling with IFR) Same scope. Running May–Jun 2026 parallel to IFR submissions. Included in MPLS Node Design pricing ($16,695 IFR per site includes survey). |  | ✓
9 | B&M — Nick Cianciolo / Global One | Step 2c: Site Surveys — Phase 3 (31 sites) ★PCR — stays in Phase 3 ~$86,000 estimate. Triggers after Ph2 IFCs complete. |  |  | ✓ |  |  | 86000 | 86000
10 | B&M — Ethan Koch | Step 3a: Staging Support — Phase 1 (SOW CPS Milestone 1) COMPLETE ✅ ★ ONE WEEK only (not 2 wks per SOW). Deliverables to PSEG: • Card slotting + SFP install requirements for Nokia 7705 SAR routers • Physical fiber jumper connectivity matrix • Chassis labelling plan • Staging test plan: network connectivity, firmware, control plane (IGP/BGP/BFD), synchronization (SyncE), NMS (SNMPv3/SCP), service validation (VPRN/Epipe/Cpipe), service tests (traffic pass), network impairment tests (link/node/BGP failure) SOW Payment: $57,300 | ✓ |  |  | 51250 |  |  | 51250
11 | B&M — Ethan Koch | Step 3b: Staging Support — Phase 2 (★ 1 week — corrected from SOW) Same test plan scope. 36 nodes. B&M provides card slotting reqs + connectivity matrix to Hawkeye. B&M executes staging test plan alongside Hawkeye. ~$25,625 (prorated from Ph1 $57,300 × 36/39 nodes). |  | ✓ |  |  | 25625 |  | 25625
12 | B&M — Ethan Koch | Step 3c: Staging Support — Phase 3 ★PCR (1 week, ~31 nodes, ~$25,625) |  |  | ✓ |  |  | 25625 | 25625
13 | B&M — Nick Cianciolo / Global One | Step 4a: MPLS Node Design — IFR (Issued For Review) Phase 1 COMPLETE ✅ Per site deliverable package: • Floor plan (AutoCAD) • AC/DC power drawings (AutoCAD) • Network Block Diagram (Visio/PDF) • Rack Elevation (Visio/PDF) • Communication Power One-Line (Visio/PDF) • Cable schedule + labels (Excel) • Site-specific installation scope of work (Word) • Bill of materials (Excel) PSEG reviews + comments within 10 working days. Per site: $16,695 ¦ 36 Ph2 sites = $601,020 (in 2026 forecast) | ✓ | ✓ |  | 601020 |  |  | 601020
14 | B&M — Nick Cianciolo | Step 4b: MPLS Node Design — IFR Phase 2 (final IFR Jun 29 2026) Per Appendix D: $16,695/site × 36 sites = $601,020 Rolling submissions per IFR schedule (Feb–Jun 2026). PSEG has 10 business days to review each IFR before B&M issues IFC. |  | ✓ |  |  | 601020 |  | 601020
15 | B&M — Nick Cianciolo | Step 4c: MPLS Node Design — IFC (Issued For Construction) Phase 2 PE-sealed final drawings. Per Appendix D: $5,963/site × 36 sites = $214,668 Final IFC deadline: July 13 2026. IFC package triggers: Hawkeye cable orders + Hawkeye staging + construction. |  | ✓ |  |  | 214668 |  | 214668
16 | B&M — Nick Cianciolo | Step 4d: MPLS Node Design — IFR + IFC Phase 3 ★PCR 31 sites × $23,850/site = $738,150 (split: IFR $517,545 / IFC $184,853 / As-Built $36,960) Accelerated Phase 3 MPLS design pulled into Phase 2 window (PCR recovery plan). |  |  | ✓ |  |  | 450000 | 450000
17 | B&M — Nick Cianciolo | Step 5a: AS-BUILT Drawings — Phase 1+2 (Issued For Record) Per Appendix D: $1,192/site × 36 sites = $42,912 Issued 1 month after site construction complete. Final record drawings incorporating all field changes. | ✓ | ✓ |  |  | 42912 |  | 42912
18 | B&M | Step 5b: AS-BUILT Drawings — Phase 3 ★PCR $1,192/site × 31 sites = $36,952 |  |  | ✓ |  |  | 37200 | 37200
19 | B&M — Ethan Koch | Step 6a: Construction Support Coordinator — Phase 1 COMPLETE ✅ (SOW CPS Milestone 2 — invoiced monthly $61,350/mo) On-site daily at each substation during construction + cutover. Scope: • Pre-construction planning meetings with PSEG + Hawkeye • Field support: respond to RFIs, track progress vs IFC, daily field reports • RFI log: receive from Hawkeye, route to B&M engineering for resolution • Cutover/commissioning: attend planning sessions, check prerequisites, communicate test outcomes, coordinate remote B&M tech support • Identify discrepancies between field conditions and design docs Aug 2025–Jan 2026 ¦ $368,100 total | ✓ |  |  | 368100 |  |  | 368100
20 | B&M — Ethan Koch | Step 6b: Construction Support Coordinator — Phase 2 (SOW Milestone 2-Ph2, invoiced monthly $61,350/mo) Same scope as Phase 1. Aug 5 2026 – Jan 2027 (6 months). • Pre-construction planning with Hawkeye (scope: 36 sites) • On-site field coordination at each substation installation • Daily field reports to PSEG PM • RFI log management • Cutover support: verify Nokia circuits live before relay team leaves site • Attend Hawkeye Go-Live sign-off review $382,824 total (6.25 months) |  | ✓ |  |  | 382824 |  | 382824
21 | B&M — Ethan Koch | Step 6c: Construction Support Coordinator — Phase 3 ★PCR Same scope. ~4 months. ~$264,000. |  |  | ✓ |  |  | 264000 | 264000
22 | B&M | Step 7: Phase 3 MPLS Detail Design (accelerated into Ph2) ★PCR 31-site full MPLS network design pulled forward from 2027 → 2026. Includes: template node design, site-specific designs, IFR/IFC packages. Recovers 5-month schedule impact from PAR scope discovery. $360,000 estimated (PCR pending approval). |  | ✓ |  |  | 360000 |  | 360000
| B&M SUBTOTAL (SOW $1,370,040 + PCR items) |  |  |  |  | 1172410 | 1092029 | 884825 | 3149264
23 | HAWKEYE (Elecnor Hawkeye) — Staging, Installation & Decommissioning
24 | Hawkeye — Vinny | Step 1: Pre-Construction Site Survey (after each IFC issued) Triggered per site when B&M issues IFC. Vinny visits substation. • Measures cable run lengths (exact) for custom cable orders • Confirms rack location per IFC drawing • Identifies conduit/cable tray path • Confirms power feed location • Photos all existing JMUX equipment (decom reference) • Generates site-specific BOM (cables, conduit, connectors, patch panels) Ph2 scope: 36 sites. Running May–Jul 2026. SOW M1 = $100,170 (split May/Jun 2026) |  | ✓ | ✓ |  | 50085 | 50085 | 100170
25 | Hawkeye — Vinny | Step 2: Cable + Material Ordering (per site, after survey) • Custom-length RJ45→DB25 serial patch cables (RTU connections) • Custom fiber jumpers (measured lengths per IFC) • Conduit + fittings (per cable tray path) • Rack hardware, patch panels, labels • Cannot order until site visit confirms exact measurements Lead times: standard 2–3 weeks ¦ custom serial cables 4–6 weeks Costs included in equipment materials budget (Nokia/Presidio line) | ✓ | ✓ | ✓
26 | Hawkeye | Step 3a: Staging — Phase 1 COMPLETE ✅ (★ 1 WEEK — not 2 per SOW) Lab rack-up and test at Hawkeye facility. • Rack and mount all Nokia SAR-8 nodes per B&M card slotting plan • Slot all cards per B&M connectivity matrix • Install SFPs per fiber connectivity plan • Power-on, confirm no alarm/fault • Execute B&M staging test plan (connectivity, firmware, BFD, BGP, QoS, SyncE, NMS, VPRN/Epipe/Cpipe services, link/node failure tests) • Label chassis, ports, cards per B&M labeling plan SOW M-Ph0 = $100,170 | ✓ |  |  | 100170 |  |  | 100170
27 | Hawkeye | Step 3b: Staging — Phase 2 (★ 1 WEEK, Jul–Aug 2026) Same scope. 36 nodes. B&M card slotting + connectivity matrix issued before staging starts. SOW M-Ph0-Ph2 = $100,170 |  | ✓ |  |  | 100170 |  | 100170
28 | Hawkeye | Step 3c: Staging — Phase 3 ★PCR (1 week, ~31 nodes, 2027) ~$100,170 |  |  | ✓ |  |  | 100170 | 100170
29 | Hawkeye — 3 visits/site | Step 4a: Substation Installation — Phase 1 COMPLETE ✅ Visit 1 — Deliver & rough-in: • Transport Nokia nodes from staging to substation • Install rack/wall mount per IFC • Run conduit + pull cables (power, fiber, serial) • Install Eltek PSU, connect to DC bus Visit 2 — Terminate & patch: • Terminate all fiber connections per cable schedule • Install CWDM mux/demux cards • Connect serial patch cables to RTU patch panel • Terminate ethernet, label all ports Visit 3 — Power-on & test: • Power-on Nokia node, confirm no alarms • Notify B&M CSC: node ready for circuit configuration • Notify relay team: ready for RTU cutover • Take as-built photos for B&M record drawings SOW M2-Ph1 = $302,623 (39 sites) | ✓ |  |  | 302623 |  |  | 302623
30 | Hawkeye — 3 visits/site | Step 4b: Substation Installation — Phase 2 (Aug 5 – Sep 28 2026) Same 3-visit process. 36 sites. Construction window: Aug 5 2026 target start, Sep 28 2026 complete. SOW M2-Ph2 = $80,136 |  | ✓ |  |  | 80136 |  | 80136
31 | Hawkeye — 3 visits/site | Step 4c: Substation Installation — Phase 3 ★PCR ~31 sites. 2027. ~$220,000 estimate. |  |  | ✓ |  |  | 220000 | 220000
32 | Hawkeye | Step 5a: Go-Live Sign-Off — Phase 2 (SOW Milestone M4) After relay team completes RTU cutover at all 36 sites: • Hawkeye verifies: all Nokia circuits confirmed live • No legacy JMUX traffic on any migrated circuit • B&M CSC confirms field punch list items resolved • PSEG formal acceptance sign-off (Vic / Jay) • Triggers M4 invoice to PSEG SOW M4-Ph2 = $80,136 |  | ✓ |  |  | 80136 |  | 80136
33 | Hawkeye | Step 5b: Go-Live Sign-Off — Phase 3 ★PCR Same scope. ~$100,000 estimate. |  |  | ✓ |  |  | 100000 | 100000
34 | Hawkeye | Step 6: Decommissioning — ALL Phases (Phase 3 window only) Cannot start until Nokia is confirmed LIVE on ALL phases. Per site scope: • De-rack and disconnect all JMUX equipment • Remove all JMUX cabling (power, fiber, serial) • Palletize and transport to PSEG designated warehouse • Restore substation: patch cable tray openings, remove labels, clean up, restore to pre-JMUX condition • B&M CSC confirms decom complete per IFC decom drawings 134 total sites (Ph1 + Ph2 + Ph3). $141,351 total. |  |  | ✓ |  |  | 141351 | 141351
35 | Hawkeye | WD#8 Fiber Testing — Elwood to Northport + 7 Patch Panels | ✓ |  |  |  | 8229 |  | 8229
| HAWKEYE SUBTOTAL |  |  |  |  | 402793 | 318756 | 611606 | 1333155
PAR | PAR (Phase Angle Regulator) ★ NEW SCOPE — PCR REQUIRED ¦ 6 Sites
a | Nokia / Presidio | Step 1: Equipment — Iniven RC-30 (6 units × $8,750 = $52,500) Serial→C37.94 protocol converter for each PAR substation. Sites: Northport, 5HK Hicksville, Melville, 7Z Lindenhurst, 2H Far Rockaway, 2R Hewlett. PO placed. 8-week lead time. Target delivery: June 2026. NERC-CIP compliant — not a programmable device. |  | ✓ |  |  | 52500 |  | 52500
b | Chak's Team | Step 2: Relay Engineering Design ($240,000 — CONFIRMED Vic May 18) 200 hrs/site × 6 sites × $200/hr Scope per site: • Review existing PAR protection relay scheme + settings • Design new C37.94 serial relay interface via Iniven RC-30 • Prepare new relay settings file • Draft installation + test procedures (MOP) • NERC-CIP compliance review and documentation • Coordinate with B&M on IFC drawings for PAR circuit changes Timeline: June–August 2026. URGENT: Chok meeting needed this week. |  | ✓ |  |  | 240000 |  | 240000
c | Steven Bradley (Relay Team) | Step 3: Relay Installation, Configuration & Cutover ($259,500 — CONFIRMED Vic May 18) ~1,298 hrs × $200/hr Scope per site: • Install Iniven RC-30 at PAR substation per Chok's design • Wire RC-30 to PAR relay contact outputs • Configure C37.94 settings per Chok's relay settings file • End-to-end protection scheme test (relay operation verified) • NERC-CIP commissioning documentation • Cutover from legacy serial path to Nokia MPLS C37.94 path • Confirm relay teleprotection operating correctly on new path Cannot start until: Chok design complete ✅ + RC-30 delivered ✅ Timeline: Aug–Oct 2026. ★ Call Steven before Mon May 25. |  | ✓ |  |  | 259500 |  | 259500
d | Various | Step 4: PAR Materials ($30,000 — CONFIRMED Vic May 18) Custom serial cables, C37.94 interface connectors, rack hardware across 6 sites. |  | ✓ |  |  | 30000 |  | 30000
| PAR SUBTOTAL ★PCR★ (RC-30 $52.5K + Engineering $240K + Install $259.5K + Materials $30K = $582K) | [5 empty] | 582000 |  | 582000
36 | PM / CONTROLLER / SCHEDULER
37 | Hermitage — Jay G | PM — Dhananjaya Gunaratne Overall delivery, CIO reporting, PCR submissions, budget management. | ✓ | ✓ | ✓ |  | 174000 | 58000 | 232000
38 | Hermitage — Ahsan | PM — Ahsan Khawaja (Phase 2 supporting) |  | ✓ |  |  | 257619 |  | 257619
39 | ComTec — Chad | Controller — Chad Boyett $8,400/mo Forecast vs actuals, SAP, monthly cost reports, PCR prep. | ✓ | ✓ | ✓ | 67200 | 100800 | 33600 | 201600
40 | ComTec — Umair | Scheduler — Umair Mohammed $5,416/mo MS Project schedule, SPI, milestone tracking. | ✓ | ✓ | ✓ | 54160 | 67040 | 13400 | 134600
41 | ComTec — Farouk | Scheduler — Farouk Adelekan |  | ✓ | ✓ |  | 20000 | 6600 | 26600
42 | Hermitage — Ed S | O/S Sr. Engineer — Edward Schwartz $2,512/mo Technical oversight, IFR/IFC design review. | ✓ | ✓ | ✓ |  | 30000 | 5000 | 35000
| PM / CONTROLS SUBTOTAL |  |  |  |  | 121360 | 649459 | 116600 | 887419
43 | INTERNAL LABOR (PSEG + Cognizant)
44 | PSEG | Internal Labor (Rahiq, Brianna, Chok, Lok, Sameer et al.) Network config, NSP, RTU cutovers, BGP. | ✓ | ✓ | ✓ | 82421 | 154989 | 60000 | 297410
45 | Cognizant — Lee | Lee Blackman — Sr. Network Architect $7,200/mo MPLS design review, IFR/IFC approval, Layer 3 design. | ✓ | ✓ |  |  | 86400 |  | 86400
46 | PSEG — Steven B | Relay Team Support — Steven Bradley (internal PSEG) ★ ZERO actuals in SAP to date. $195K in 2026 forecast. Need: names + hours by month before Mon May 25. | ✓ | ✓ | ✓ |  | 195000 | 30000 | 225000
| INTERNAL LABOR SUBTOTAL |  |  |  |  | 82421 | 436389 | 90000 | 608810
47 | PQA / ASSESSMENTS / TRC
48 | Cognizant / EPMO | PQA Audit — Margaret Tanner Glover | ✓ | ✓ | ✓ | 56330 | 40000 | 10000 | 106330
49 | PSEG | Assessments (PSEG IT overhead) | ✓ | ✓ | ✓ | 19172 | 72737 | 20000 | 111909
50 | TRC — Raju K | Raju Khedkar — Cyber Security / NERC-CIP Architect | ✓ | ✓ | ✓ | 3726 | 30000 | 5000 | 38726
| PQA / ASSESSMENTS / TRC SUBTOTAL |  |  |  |  | 79228 | 142737 | 35000 | 256965
★ | GRAND TOTAL — ALL CONTRACTORS |  |  |  |  | 3270612 | 4009663 | 2731031 | 10011306
| CP BUDGET (approved) |  |  |  |  | 3250000 | 2600000 | 1000000 | 6850000
| VARIANCE (Budget − EAC) ⚠ Negative = OVER BUDGET |  |  |  |  | -20612 | -1409663 | -1731031 | -3161306
B&M SOW Appendix D: IFR $16,695/site ¦ IFC $5,963/site ¦ As-Built $1,192/site ¦ Site Total $23,850 ¦ 36 Ph2 sites = $858,600 ¦ Staging M1=$57,300 ¦ CSC M2=$368,100 (Ph1) invoiced monthly ¦ ★PCR items highlighted green ¦ Staging = 1 WEEK (not 2 per SOW) ¦ Phase 3 surveys in Phase 3 only
PAR confirmed Vic May 18: RC-30 $52.5K + Chok Engineering $240K + Steven B Install $259.5K + Materials $30K = $582K ¦ Martin Gately DEPARTED ¦ Steven Bradley call before Mon May 25 (relay hrs needed)