# PRJ13797 — JMUX Replacement Program

PSEG Long Island  |  Private Field Area Network Modernization

Project Manager: Dhananjaya Gunaratne
Log Generated: April 25, 2026
Classification: Confidential — Internal Use Only

────────────────────────────────────────────────────────────────────────────────

# 1. PROJECT OVERVIEW

Project Number: PRJ13797

Project Name: JMUX Replacement — Private Field Area Network (PFAN) Modernization

Project Manager: Dhananjaya (Jay) Gunaratne

Owner: PSEG Long Island

Status (April 2026): YELLOW — SPI 0.77 | Recovery Plan in Place

Total Program Spend to Date: $5.66M (2024–2026)

Goal: Modernize PSEG Long Island's substation communications by replacing legacy JMUX infrastructure with Nokia MPLS nodes to deliver a reliable, scalable, and future-ready network across 129 substations.

## 1.1 Program Scope

• Total substations: 129

• Total MPLS sites: 74

• Total RTU sites: 36

• Total Nokia MPLS nodes: 79 (across 3 phases)

• Phase 1: 31 Nokia MPLS nodes — COMPLETE ✅

• Phase 2: 36 sites — Engineering underway, Construction Aug 2026

• Phase 3: Remaining sites — Engineering accelerated into Phase 2 staging window (~Aug 2026)

## 1.2 Key Vendors / Contractors

• Burns & McDonnell (B&M) — Engineering Services, PAR Design, RTU Migration Planning

• Nokia — MPLS Equipment Supply, NSP Management System

• Graybar — Ancillary Equipment Procurement

• Hawkeye Construction — Construction, Installation, Site Surveys

• CNI — Test Circuit Installation at Hicksville

• Iniven — RC-30 PAR Circuit Conversion Devices

• Chakrapani / T&D Team (PSEG) — PAR Engineering Design

## 1.3 Key Baseline Dates

• Phase 1 Baseline Start: January 2026

• Final IFR — All Phase 2 Sites: June 29, 2026

• Final IFC — All Phase 2 Sites: July 13, 2026

• Phase 2 Construction Start: August 5, 2026

• Phase 2 Deployment Complete: September 28, 2026

• Phase 3 Engineering Start: August 2026 (accelerated)

• Full Program Recovery: End of 2026

# 2. WORKSTREAM STATUS

✅  Phase 2 Site Surveys

Phase: Phase 2  |  Owner: Hawkeye  |  Status: Complete  |  Complete: 100%

All 36 Phase 2 site surveys complete.

✅  BGP Configuration

Phase: Phase 1  |  Owner: Lee / B&M  |  Status: Complete  |  Complete: 100%

BGP design approved. Change docs in progress for Hicksville & Melville.

✅  NMS Node Buildout (Phase 1)

Phase: Phase 1  |  Owner: Lee / Rahiq / Brianna  |  Status: Complete  |  Complete: 100%

All 31 Phase 1 nodes built into NSP GUI. All routers accessible remotely. SSP configuration check in progress.

✅  Nokia NSP Remote Access

Phase: Phase 1  |  Owner: B&M / PSEG  |  Status: Complete  |  Complete: 100%

NSP installed. Remote access confirmed April 21, 2026. DNS resolved.

🟢  Engineering IFR/IFC (Phase 2)

Phase: Phase 2  |  Owner: B&M  |  Status: On Track  |  Complete: 25%

9/36 IFCs sent to Hawkeye. IFRs rolling May–June. Final IFR: June 29. Final IFC: July 13.

⏳  RTU Test Circuit — Hicksville

Phase: Phase 1  |  Owner: CNI / John Ng  |  Status: In Progress  |  Complete: 50%

DB9 cables delivered to John Ng. Test scheduled week of April 27.

⏳  PAR Equipment Order (Iniven RC-30)

Phase: Phase 1  |  Owner: Dhananjaya  |  Status: In Progress  |  Complete: 50%

PO placed. 8-week lead time. Chakrapani engaged for PAR engineering design. 6 sites.

⬜  Phase 2 Construction

Phase: Phase 2  |  Owner: Hawkeye  |  Status: Not Started  |  Complete: 0%

Construction start target: August 2026.

# 3. MILESTONE TRACKER

✅  iLO Corporate Connectivity — Melville & Hicksville

Phase: Phase 1  |  Workstream: NMS/NSP  |  Status: Complete  |  Complete: 100%

Planned: 2026-02-26  |  Actual: 2026-02-26  |  Weekly SPI: 1.0  |  Cumulative SPI: 0.76

Notes: Northport fuse tripping — ILO work blocked. DC power issue resolved.

✅  Layer 3 (BGP) Network Design & Configurations

Phase: Phase 1  |  Workstream: Network  |  Status: Complete  |  Complete: 100%

Planned: 2026-03-09  |  Actual: 2026-03-09  |  Weekly SPI: 1.0  |  Cumulative SPI: 0.77

Notes: OTDR confirmed bad filter at Hicksville. Link now active.

✅  BGP Design Approved

Phase: Phase 1  |  Workstream: Network  |  Status: Complete  |  Complete: 100%

Planned: 2026-03-16  |  Actual: 2026-03-16  |  Weekly SPI: 1.0  |  Cumulative SPI: 0.8

Notes: BGP design formally approved. Lee to begin change docs.

✅  Remote Access to NSP — Fiber Terminated at Hicksville

Phase: Phase 1  |  Workstream: NMS/NSP  |  Status: Complete  |  Complete: 100%

Planned: 2026-04-13  |  Actual: 2026-04-21  |  Weekly SPI: 1.0  |  Cumulative SPI: 0.78

Notes: DNS update escalated to Vic. Full GUI access confirmed week of Apr 21.

✅  Work with B&M to Access Nokia NSP

Phase: Phase 1  |  Workstream: NMS/NSP  |  Status: Complete  |  Complete: 100%

Planned: 2026-04-05  |  Actual: 2026-04-24  |  Weekly SPI: 1.0  |  Cumulative SPI: 0.88

Notes: All 31 Nokia MPLS routers installed. All nodes built and verified in NSP GUI.

✅  Build Phase 1 Nodes into NMS GUI Interface

Phase: Phase 1  |  Workstream: NMS/NSP  |  Status: Complete  |  Complete: 100%

Planned: 2026-04-18  |  Actual: 2026-04-23  |  Weekly SPI: 1.0  |  Cumulative SPI: 0.85

Notes: Completed by Lee, Rahiq & Brianna on April 23, 2026.

✅  9 IFCs Sent to Hawkeye for Phase 2 Site Surveys

Phase: Phase 1  |  Workstream: Engineering  |  Status: Complete  |  Complete: 100%

Planned: 2026-04-20  |  Actual: 2026-04-20  |  Weekly SPI: 1.0  |  Cumulative SPI: 0.77

Notes: Hawkeye to compile installation requirements per site.

⏳  Lindenhurst (7Z) IFR Submission

Phase: Phase 2  |  Workstream: Engineering  |  Status: In Progress  |  Complete: 0%

Planned: 2026-04-27  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: Due Monday April 27th — URGENT.

⏳  PAR Equipment Order — Iniven RC-30 (6 Sites)

Phase: Phase 1  |  Workstream: RTU Migration  |  Status: In Progress  |  Complete: 25%

Planned: 2026-04-30  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: PO exists. Chakrapani has NOT confirmed design status. $495K relay labor not yet in forecast.

⏳  Test Circuit — RTU Communication with EMS at Hicksville

Phase: Phase 1  |  Workstream: RTU Migration  |  Status: In Progress  |  Complete: 50%

Planned: 2026-04-30  |  Actual: —  |  Weekly SPI: 0.15  |  Cumulative SPI: 0.72

Notes: Cables delivered to John Ng. Test week of Apr 27.

⏳  RTU Serial Test — Hicksville (B&M + John Ng)

Phase: Phase 1  |  Workstream: RTU Migration  |  Status: In Progress  |  Complete: 10%

Planned: 2026-04-30  |  Actual: —  |  Weekly SPI: 0.1  |  Cumulative SPI: —

Notes: SEL-2829 transceivers confirmed compatible.

⬜  Baldwin (4M & 4M1) IFR Submission

Phase: Phase 2  |  Workstream: Engineering  |  Status: Not Started  |  Complete: 0%

Planned: 2026-05-04  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: Due May 4th.

⬜  Remote Node Verification — All 31 Phase 1 Sites

Phase: Phase 1  |  Workstream: NMS/NSP  |  Status: Not Started  |  Complete: 0%

Planned: 2026-05-09  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: Remote login to each of 31 nodes — verify configs and connectivity.

⬜  Develop MOP — Production RTU Migration

Phase: Phase 1  |  Workstream: RTU Migration  |  Status: Not Started  |  Complete: 0%

Planned: 2026-05-16  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: Required before any production cutover.

⬜  Final IFR — All Phase 2 Sites

Phase: Phase 2  |  Workstream: Engineering  |  Status: Not Started  |  Complete: 0%

Planned: 2026-06-29  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: Baseline date — do not change.

⬜  Final IFC — All Phase 2 Sites

Phase: Phase 2  |  Workstream: Engineering  |  Status: Not Started  |  Complete: 0%

Planned: 2026-07-13  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: Baseline date — do not change.

⬜  Phase 2 Construction Start

Phase: Phase 2  |  Workstream: Construction  |  Status: Not Started  |  Complete: 0%

Planned: 2026-08-05  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: Hawkeye mobilization across all Phase 2 sites.

⬜  Phase 2 Deployment Complete

Phase: Phase 2  |  Workstream: Deployment  |  Status: Not Started  |  Complete: 0%

Planned: 2026-09-28  |  Actual: —  |  Weekly SPI: 0.0  |  Cumulative SPI: —

Notes: Target completion for all Phase 2 Nokia MPLS deployment.

# 4. PAR CIRCUIT MIGRATION — 6 HIGH-IMPACT SITES

Solution: Iniven RC-30 (direct contact → C37.94 IP protocol conversion)

Compliance: NERC CIP mandatory — no direct Nokia-to-RTU connection permitted

Total Additional Unbudgeted Cost: ~$550,000+

• Equipment (RC-30 x6): ~$59,500 — PO Placed ✅

• PAR Engineering Design (Chakrapani/T&D): TBD — In Progress ⏳

• Installation/Config/Cutover Labor (Johnny's relay team ~$1,100–$1,200/hr): ~$495,000 — Not Started 🔴

Note: Chad's Apr–Jun forecast = $120K (equipment + design only). $495K relay labor NOT YET included.

Site: Northport (Northport)

RC-30: Ordered (Chakrapani)  |  C37.94 Card Needed: Yes

Design Status: In Progress  |  Installation: Not Started

Notes: Requires C37.94 card IN ADDITION to RC-30. Must bundle with Phase 2 PO.

Site: Hicksville (5HK) (5HK)

RC-30: Ordered (Chakrapani)  |  C37.94 Card Needed: No

Design Status: Not Started  |  Installation: Not Started

Notes: 8-week lead time on RC-30 is critical path.

Site: Melville (Melville)

RC-30: Ordered (Chakrapani)  |  C37.94 Card Needed: No

Design Status: Not Started  |  Installation: Not Started

Notes: RC-30 ordered by Chakrapani. Design not yet started.

Site: Lindenhurst (7Z) (7Z)

RC-30: Ordered (Chakrapani)  |  C37.94 Card Needed: No

Design Status: Not Started  |  Installation: Not Started

Notes: IFR for 7Z due Apr 27 — PAR design must align.

Site: Far Rockaway (2H) (2H)

RC-30: Ordered (Chakrapani)  |  C37.94 Card Needed: No

Design Status: Not Started  |  Installation: Not Started

Notes: Delivery timeline must align with Phase 2 construction.

Site: Hewlett (2R) (2R)

RC-30: Ordered (Chakrapani)  |  C37.94 Card Needed: No

Design Status: Not Started  |  Installation: Not Started

Notes: Delivery timeline must align with Phase 2 construction.

# 5. EQUIPMENT & PROCUREMENT LOG

✅  Nokia MPLS Nodes — Phase 1

Category: Nokia MPLS Node  |  Vendor: Nokia / Graybar  |  Phase: Phase 1

Ordered: 31  |  Received: 31  |  Staged: 31  |  Installed: 0  |  PO Status: Received

Notes: All 31 received and staged at Hawkeye warehouse.

📦  Nokia MPLS Nodes — Phase 2

Category: Nokia MPLS Node  |  Vendor: Nokia / Graybar  |  Phase: Phase 2

Ordered: 26  |  Received: 0  |  Staged: 0  |  Installed: 0  |  PO Status: PO Placed

Notes: Delivery expected ahead of August construction start.

⚠️  Iniven RC-30 — PAR Circuit Conversion (6 Sites)

Category: Iniven RC-30  |  Vendor: Iniven  |  Phase: Phase 1

Ordered: 6  |  Received: 0  |  Staged: 0  |  Installed: 0  |  PO Status: Not Ordered

Notes: CRITICAL — 8-week lead time. Required for PAR at 6 substations. Change Request in progress.

⚠️  C37.94 Protocol Card — Northport

Category: C37.94 Card  |  Vendor: TBD  |  Phase: Phase 2

Ordered: 1  |  Received: 0  |  Staged: 0  |  Installed: 0  |  PO Status: Not Ordered

Notes: To be bundled with Phase 2 equipment order. Required for Northport PAR.

✅  Patch Panels, Fiber Cables, Mounting Kits — Phase 1

Category: Patch Panel  |  Vendor: Graybar  |  Phase: Phase 1

Ordered: 31  |  Received: 31  |  Staged: 25  |  Installed: 0  |  PO Status: Received

Notes: Staging ongoing at Hawkeye warehouse.

✅  SEL C382 DB9 Serial Cables (50ft)

Category: Ancillary  |  Vendor: SEL  |  Phase: Phase 1 / Hicksville

Ordered: 4  |  Received: 4  |  Staged: 0  |  Installed: 0  |  PO Status: Received

Notes: Delivered to John Ng at Hicksville. Required for RTU serial test.

# 6. STATEMENT OF WORK — ACTIVE VENDORS

Burns & McDonnell (B&M)

Status: Active  |  Period: 2025-01-01 to 2026-12-31

Scope: Engineering services: site surveys, rack elevations, power & cabling design, IFR/IFC/As-Built documents, on-site construction coordination, technical support and commissioning oversight.

Open Items: 1. Lindenhurst IFR due 4/27
2. Hewlett DO IFR due 6/2
3. Final IFR all Phase 2 sites due 6/29
4. Final IFC all Phase 2 sites due 7/13
5. MOP for production RTU migration pending

Hawkeye Construction

Status: Active  |  Period: 2025-06-01 to 2026-09-30

Scope: Construction and installation: equipment racking, stacking, power, site surveys for construction support, fiber/copper cabling installation per approved IFC documents.

Open Items: 1. Phase 2 site surveys to be scheduled as IFCs are issued
2. Construction start August 2026

Nokia

Status: Active  |  Period: 2025-01-01 to 2026-12-31

Scope: MPLS equipment supply, Nokia NSP management system, network configuration support, Nokia Systems Operator training.

Open Items: 1. Training dates to be confirmed with Glenn/Nokia
2. Phase 2 node delivery tracking

Graybar

Status: Active  |  Period: 2025-01-01 to 2026-12-31

Scope: Procurement and staging of ancillary equipment: patch panels, fiber cables, power equipment, mounting kits.

Open Items: 1. Phase 2 ancillary equipment BOM to be finalized

CNI

Status: Active  |  Period: 2026-04-01 to 2026-06-30

Scope: Test circuit installation at Hicksville to verify RTU communication with EMS before production migration.

Open Items: 1. Schedule test circuit run at Hicksville
2. Coordinate with John Ng relay team for test date

# 7. MEETING MINUTES & CALL LOGS

📅  2026-04-07 — JMUX Weekly Sync — Apr 7

Attendees: Dhananjaya, Irving, Vikas, Lee, Rahiq, Brianna, John Ng, B&M Team

Key Decisions:

Phase 1 NMS buildout assigned to Lee, Rahiq, Brianna. Nokia license received 4/13 unblocks NSP work. DNS ticket escalated to Vic.

Action Items:

1. Lee/Rahiq/Brianna to configure remaining 18 nodes in NSP GUI
2. Vic to complete DNS record update
3. John Ng team to schedule RTU test circuit at Hicksville

Notes: Phase 1 is ~3 months behind on NSP items. Phase 2 IFR/IFC progressing on schedule.

Status: Action Items Open  |  Due: 2026-04-14

────────────────────────────────────────────────────────────────────────────────

📅  2026-04-14 — JMUX Weekly Sync — Apr 14

Attendees: Dhananjaya, Irving, Vikas, Lee, B&M Team, Hawkeye

Key Decisions:

Nokia NSP license received and confirmed. NMS buildout kicked off. Sterling & Whiteside IFR issued. Hewlett IFR due 4/20.

Action Items:

1. Lee to begin NSP node configuration — COMPLETE ✅
2. B&M to submit Hewlett IFR by 4/20
3. Nokia training dates — Call scheduled with Glenn, Shelton, Rahiq, Brianna, Lee to finalize dates and syllabus. IN PROGRESS ⏳

Notes: 13 of 31 Phase 1 nodes now in NSP GUI. DNS resolved. NSP access confirmed.

Status: Action Items Open  |  Due: 2026-04-21

────────────────────────────────────────────────────────────────────────────────

📅  2026-04-21 — JMUX Weekly Sync — Apr 21

Attendees: Dhananjaya, Irving, Vikas, Lee, Rahiq, Brianna, John Ng, B&M Team, Hawkeye, CNI

Key Decisions:

50ft DB9 cables delivered to John Ng at Hicksville. CNI to run test circuit. 9 IFCs sent to Hawkeye for Phase 2 site surveys. Northport C37.94 card to be bundled with Phase 2 order.

Action Items:

1. CNI to schedule RTU test circuit at Hicksville
2. John Ng to confirm test date
3. B&M to submit Lindenhurst IFR by 4/27
4. Bundle Northport C37.94 card with Phase 2 equipment order
5. Confirm Nokia training dates with Glenn/Nokia

Notes: PAR migration approach confirmed — Iniven RC-30 selected. 8-week lead time PO not placed — CRITICAL.

Status: Action Items Open  |  Due: 2026-04-28

────────────────────────────────────────────────────────────────────────────────

📅  2026-04-24 — JMUX Project Sync — PAR Narrative, CIO Deck Review, Financial Reconciliation

Attendees: Jay Gunaratne, Vic (Director)

Key Decisions:

1. Nokia EMS node buildout for all 31 Phase 1 sites = 100% COMPLETE as of April 23.
2. Remote access to NSP = 100% COMPLETE.
3. RTU serial testing = 50% complete. Cables delivered by Vinny to John Ng. Test week of Apr 27.
4. Greg CIO presentation = Wednesday April 29, 4 PM. Deck review with Vic = Monday April 27.
5. PAR narrative for Greg agreed: discovered during Phase 2 site surveys, was Phase 3 placeholder at ~$30-40K, now $550K full scope.
6. Two new PAR slides to be added to deck.
7. Phase 3 engineering to start during Phase 2 staging (~Aug 2026).
8. Chad's email: $120K forecasted Apr-Jun for PAR. $495K relay labor NOT yet in forecast.

Action Items:

1. Jay to get confirmation from Chakrapani — design status for 6 PAR sites — DUE: ASAP
2. Jay to call Chad — reconcile $495K relay labor, spread across months — DUE: Mon Apr 27
3. Jay to talk to Ethan — get PAR technical narrative — DUE: Today/Monday
4. Jay to finish updated CIO deck — DUE: Sunday night / Monday AM
5. Jay + Vic to review deck — DUE: Mon Apr 27
6. Update IFR/IFC dates in dashboard per B&M updated email

Notes: OPEN QUESTIONS: Chakrapani design status unknown. $495K relay labor not in Chad's forecast — critical gap.

Status: Open  |  Due: 2026-04-27

────────────────────────────────────────────────────────────────────────────────

📅  2026-04-24 — Chad Call — PAR Financial Reconciliation

Source: WhatsApp - April 24, 2026

Attendees: Jay Gunaratne, Chad (Cost Controller)

Key Decisions:

1. Chad currently has $40K/month x 3 months ($120K Apr-Jun) forecasted — covers Chakrapani team only.
2. Relay team ($495K) has NOT been charged yet and is NOT in Chad's forecast.
3. Vic asked Jay to split the $495K across Apr/May/Jun.
4. CRITICAL QUESTION: Is relay labor internal (~$200/hr) or external (~$1,100–$1,200/hr)?
5. Chad flagged: if internal labor not captured, already a $40K variance for April.
6. Ethan recommended splitting across 3 months. Chad to send email with his view.

Action Items:

1. Jay to verify email — how many hours allocated for relay labor at each PAR site — DUE: Mon Apr 27
2. Chad to send email showing current forecast and questions on $495K — DUE: ASAP
3. Jay to reach out to Ethan — confirm hours AND rate for internal relay team — DUE: Mon Apr 27
4. Split $495K relay labor across Apr/May/Jun per Ethan guidance — DUE: Mon Apr 27

Notes: KEY RISK: Labor rate and hours unconfirmed. If internal at ~$200/hr and ~200hrs total, cost could be much less than $495K. Must clarify before Greg presentation Apr 29.

Status: Open  |  Due: 2026-04-27

────────────────────────────────────────────────────────────────────────────────

📅  2026-04-24 — Ethan Call — PAR 2024 Planning History

Source: WhatsApp - April 24, 2026

Attendees: Jay Gunaratne, Ethan (Solution Architect)

Key Decisions:

1. PAR was discussed in 2024 during initial kickoff meetings with Martin (Marty).
2. The initial agreement was general/high-level only — no detailed design, no cost, no schedule.
3. Marty indicated the cost for technical security design would be on their team — no dollar figure agreed upon.
4. No formal forecast or budget was established for PAR in 2024.
5. Ethan: "I don't remember the details of what was discussed."
6. Ethan believes this is more of an ALEX discussion — Alex was involved at the start.

Action Items:

1. Jay to call Alex — get full 2024 PAR planning history — DUE: Mon Apr 27
2. Use Ethan's input to frame the narrative: 2024 = high-level only, full scope discovered during Phase 2 site surveys

Notes: KEY NARRATIVE CONFIRMED: 2024 = high-level only. Full scope discovered during Phase 2 site surveys. Supports narrative that this is not a PM oversight.

Status: Open  |  Due: 2026-04-27

────────────────────────────────────────────────────────────────────────────────

# 8. FINANCIAL SUMMARY

Total Program Spend to Date: $5.66 Million (2024–2026)

Spend Breakdown:

76%  Outside Services (B&M, Hawkeye, Nokia)

18%  Materials (Equipment & Cabling)

4%  Internal Labor

2%  Assessments

Budget Variance:

Projected Total Variance: -$668,000

Projected 2026 Capital Variance: -$797,000

PAR Circuit Migration — Unbudgeted Costs:

Iniven RC-30 Equipment (6 sites):          ~$59,500    PO Placed ✅

PAR Engineering Design (Chakrapani/T&D):     TBD       In Progress ⏳

Installation/Config Labor (Johnny's team):  ~$495,000   Not Started 🔴

TOTAL ADDITIONAL FUNDING REQUIRED:          ~$550,000+

Note: Chad's Apr–Jun forecast = $120K (equipment + design only). $495K relay labor NOT YET in forecast.

Formal Change Request to be submitted — target within 2 weeks of April 29, 2026.

# 9. SCHEDULE PERFORMANCE INDEX (SPI)

SPI = Earned Value (EV) ÷ Planned Value (PV)

SPI < 0.70 = Critical  |  0.70–0.90 = Yellow  |  0.90–1.10 = On Track  |  >1.10 = Ahead

March 2026 SPI:  0.80  (Yellow)

April 2026 SPI:  0.77  (Yellow — Recovery Plan in Place)

Root Causes of SPI < 1.0:

1. Nokia corporate server license delay — license received April 13, 2026 (after extended wait)

2. IT DNS change request delay — DNS record updated after escalation to Vic, resolved week of April 21

Recovery Actions Completed:

✅ Nokia NSP installed and operational

✅ Remote access to NSP confirmed April 21, 2026

✅ All 31 Phase 1 nodes built into NSP GUI — completed April 23, 2026

✅ 9 IFCs sent to Hawkeye for Phase 2

⏳ RTU test circuit at Hicksville — cables delivered, test week of April 27

⏳ Production RTU MOP — pending test completion

# 10. RISK REGISTER

🔴 HIGH  Legacy JMUX Equipment Condition

Description: JMUX infrastructure is 25+ years old. Faulty connectors encountered — parts no longer available from vendors. Risk of brittle fiber patch panels, face plates, connectors. Potential for unplanned outage.

Mitigation: Tracking weekly. Prioritizing Phase 1 completion to decommission JMUX asap.

🟡 MEDIUM  PAR Relay Labor Cost Uncertainty

Description: $495K relay labor estimate based on ~$1,100–$1,200/hr external rate. If internal labor (~$200/hr), total cost could be significantly lower. Rate and hours per site not yet confirmed.

Mitigation: Jay to verify rate and hours with Ethan and Chad by April 27 before Greg presentation.

🟡 MEDIUM  Weather Delays — Summer Construction

Description: Substation installations trigger safety protocols at temperatures above 90°F. Risk of delays during summer 2026 construction window.

Mitigation: Plan critical activities in cooler windows. Monitor forecast. Track weekly.

🟡 MEDIUM  Phase 2/Phase 3 Resource Conflicts

Description: Other major substation projects running concurrently at PSEG. Risk of resource and site access conflicts.

Mitigation: Coordinating with other project teams. Escalate conflicts to Vic as needed.

🟡 MEDIUM  Chakrapani PAR Design — Status Unknown

Description: Chakrapani has NOT confirmed: (1) whether he is tracking the RC-30 PO, (2) where PAR design stands for any of the 6 sites.

Mitigation: Jay to follow up with Chakrapani ASAP. Critical before Apr 29 Greg meeting.

🟡 MEDIUM  Iniven RC-30 — 8-Week Lead Time

Description: RC-30 devices have 8-week lead time. PO status and confirmed delivery date not yet received from Iniven.

Mitigation: Jay to get PO number and delivery confirmation from Chakrapani.

# 11. PRESENTATIONS & DOCUMENTS LOG

📄  PRJ13797_JMUX_CIO_Update_April2026_v1.pptx

Type: CIO Presentation  |  Date: April 2026

Description: Initial April CIO deck

📄  PRJ13797_JMUX_CIO_Update_April2026_v2.pptx

Type: CIO Presentation  |  Date: April 2026

Description: V2 with updated content

📄  PRJ13797_JMUX_CIO_Update_April2026_v4.pptx

Type: CIO Presentation  |  Date: April 2026

Description: V4 iteration

📄  PRJ13797_JMUX_CIO_Update_April2026_v5.pptx

Type: CIO Presentation  |  Date: April 2026

Description: V5 iteration

📄  c63556302_PRJ13797JMUXReplacementUpdate-Marchend-final_v1a6.pptx

Type: CIO Presentation — FINAL  |  Date: April 25, 2026

Description: FINAL VERSION — approved for Greg presentation April 29, 2026

📄  PRJ13797_JMUX_PAR_Slides_Apr24_2026.pptx

Type: PAR Migration Slides  |  Date: April 24, 2026

Description: Two PAR slides: Background & Discovery + Schedule & Financial Impact

📄  PRJ13797_JMUX_NextSteps_Apr24_2026.pptx

Type: Next Steps Slide  |  Date: April 24, 2026

Description: Updated Next Steps slide for CIO deck

📄  PRJ13797_JMUX_NextSteps_Final.pptx

Type: Next Steps Slide — Final  |  Date: April 24, 2026

Description: Final Next Steps slide

📄  PRJ13797_JMUX_OralPresentation_Greg_CIO_v1a6.docx

Type: Oral Presentation Script — FINAL  |  Date: April 25, 2026

Description: Full oral presentation script for Greg — v1a6 FINAL. Includes 8-10 min sections for Slides 4, 5, and 10.

📄  PRJ13797_SPI_Calculator.xlsx

Type: SPI Calculator  |  Date: April 2026

Description: Excel SPI calculator for milestone tracking

📄  PRJ13797_JMUX_CIO_OralPresentation_Mar24.md

Type: Oral Presentation Script  |  Date: March 2026

Description: Earlier oral script version

📄  jmux_call_minutes_apr7_2026.md

Type: Meeting Minutes  |  Date: April 7, 2026

Description: Weekly sync — Apr 7

📄  jmux_call_minutes_apr21_2026.md

Type: Meeting Minutes  |  Date: April 21, 2026

Description: Weekly sync — Apr 21

📄  jmux_call_minutes_apr24_2026.md

Type: Meeting Minutes  |  Date: April 24, 2026

Description: PAR narrative, CIO deck review, financial reconciliation

📄  jmux_chad_call_apr24_2026.md

Type: Call Notes  |  Date: April 24, 2026

Description: Chad — PAR financial reconciliation

📄  jmux_bgp_call_mar31.md

Type: Call Notes  |  Date: March 31, 2026

Description: BGP call notes

📄  par_controls_meeting_mar31.md

Type: Meeting Notes  |  Date: March 31, 2026

Description: PAR controls meeting

📄  jmux_cio_status_update_apr22_2026.md

Type: Status Update  |  Date: April 22, 2026

Description: CIO status update narrative

📄  jmux_pmo_review_apr22_2026.md

Type: PMO Review  |  Date: April 22, 2026

Description: PMO review notes

📄  jmux_weekly_status_report_april7_2026.html

Type: Weekly Status Report  |  Date: April 7, 2026

Description: HTML status report

# 12. OPEN ACTION ITEMS

As of April 25, 2026

🔴 CRITICAL  Follow up with Chakrapani — confirm: (a) Is he tracking the RC-30 PO? (b) Where is PAR design for all 6 sites?

Owner: Jay  |  Due: Mon Apr 27

🔴 CRITICAL  Call Alex — get full 2024 PAR planning history: what was discussed, what was agreed, was cost/schedule ever discussed?

Owner: Jay  |  Due: Mon Apr 27

🔴 CRITICAL  Verify relay labor rate and hours — internal (~$200/hr) or external (~$1,100–$1,200/hr)? Confirm total hours per site with Ethan.

Owner: Jay  |  Due: Mon Apr 27

🔴 CRITICAL  Reconcile $495K relay labor — spread across Apr/May/Jun based on Chakrapani design schedule and Johnny team start date.

Owner: Jay / Chad  |  Due: Mon Apr 27

🟡 HIGH  Deck review with Vic — review final CIO deck v1a6 before Greg presentation April 29.

Owner: Jay / Vic  |  Due: Mon Apr 27

🟡 HIGH  Lindenhurst (7Z) IFR submission — due Monday April 27. URGENT.

Owner: B&M  |  Due: Mon Apr 27

🟡 HIGH  Execute RTU serial test at Hicksville — cables delivered, test to run week of April 27.

Owner: John Ng / CNI  |  Due: Apr 30

🟡 HIGH  CIO Presentation to Greg — Wednesday April 29, 4 PM. Oral script finalized (v1a6).

Owner: Jay  |  Due: Apr 29

🟢 MEDIUM  Baldwin (4M & 4M1) IFR submission.

Owner: B&M  |  Due: May 4

🟢 MEDIUM  Remote node verification — confirm all 31 Phase 1 nodes accessible and configured per SSP.

Owner: Lee / Rahiq / Brianna  |  Due: May 9

🟢 MEDIUM  Develop MOP for production RTU migration at Hicksville.

Owner: Jay / B&M  |  Due: May 16

🟢 MEDIUM  Prepare and submit formal Change Request for $550K+ PAR unbudgeted costs.

Owner: Jay / Chad  |  Due: ASAP

🟢 MEDIUM  Confirm Nokia training dates with Glenn/Nokia — syllabus finalized with Shelton.

Owner: Nokia / Jay  |  Due: TBD

🟢 MEDIUM  Track Phase 2 IFR/IFC submissions — 9/36 IFCs issued. Continue rolling submissions through June 29.

Owner: Hawkeye / B&M  |  Due: Ongoing

────────────────────────────────────────────────────────────────────────────────

PRJ13797 JMUX Replacement Program — Project Log
Generated by Daminie AI  |  April 25, 2026  |  Confidential — Internal Use Only