## 2026 Budget vs Forecast
PRJ13797 — JMUX REPLACEMENT ¦ 2026 BUDGET vs FORECAST — WILL WE RUN OUT OF MONEY? ¦ May 18 2026
CP Budget 2026: $2,600,000 ¦ Actuals Jan–Apr: $2,065,144 ¦ Remaining: $534,856 ¦ Base forecast May–Dec: $1,294,293 ¦ ★ BUDGET RUNS OUT IN JUNE 2026
▶ SECTION 1 — BUDGET STATUS SNAPSHOT
CP Budget 2026 | 2600000 |  |  | Approved Capital Program budget for 2026
Actuals Jan–Apr 2026 | 2065144 |  |  | Already spent: Jan $575K + Feb $276K + Mar $919K + Apr $295K
Remaining Budget TODAY | 534856 |  |  | ★ Only $534,856 left for remaining 8 months of 2026
Base Forecast May–Dec | 1294293 |  |  | Contracted/committed spend EXCLUDING PCR items
PCR Forecast May–Dec | 889500 |  |  | PCR items pending approval: PAR $530K + Ph3 MPLS accel $360K
TOTAL Forecast May–Dec | 2183793 |  |  | BASE + PCR combined May–Dec
Full Year EAC (BASE only) | 3359437 |  |  | $759K OVER budget on contracted work alone — NO PCR yet
Full Year EAC (with PCR) | 4248937 |  |  | $1,648,937 OVER budget if PCR approved without extra funding
Budget Exhausted (BASE) | END OF JUNE 2026 |  |  | ★★★ On base spend alone, remaining $534,856 is consumed by end of June. Jul–Dec = UNFUNDED
▶ SECTION 2 — MONTHLY CASHFLOW TABLE (Jan–Apr = Actuals ¦ May–Dec = Forecast)
# | Vendor | Line Item | Jan Actual | Feb Actual | Mar Actual | Apr Actual | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2026 TOTAL | Type
1 | B&M | IFR/IFC Design (SOW M4) Rolling per site deliveries | — | — | — | 162181 | 148938 | 89445 | 50000 | — | — | — | — | — | 450564 | OS
2 | B&M | PM — Alex Lennox $5,500/mo | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 66000 | OS
3 | B&M | Phase 2 CSC — on-site Aug–Dec $61,350/mo | — | — | — | — | — | — | — | 61350 | 61350 | 61350 | 61350 | 61350 | 306750 | OS
4 | Hawkeye | Phase 1 SOW remaining 2026 | — | — | 335993 | — | [8 empty] | 335993 | OS | bar: May to Dec
5 | Hawkeye | Phase 2 Surveys M1 ($100,170) | — | — | — | — | 50085 | 50085 | — | — | — | — | — | — | 100170 | OS
6 | Hawkeye | Phase 2 Staging M-Ph0 ($100,170) | — | — | — | — | — | — | 50085 | 50085 | — | — | — | — | 100170 | OS
7 | Hawkeye | Phase 2 Installation M2 ($80,136) | — | — | — | — | — | — | — | 40068 | 40068 | — | — | — | 80136 | OS
8 | Hawkeye | Phase 2 Go-Live M4 ($80,136) | — | — | — | — | — | — | — | — | 40068 | 40068 | — | — | 80136 | OS
9 | Nokia/Presidio | Equipment (CWDM, Eltek PSUs) | — | — | 753373 | — | — | 25000 | — | — | — | — | — | — | 778373 | Equip
10 | Nokia | Iniven RC-30 PAR equipment | — | — | — | 52500 | — | 52500 | — | — | — | — | — | — | 105000 | Equip
11 | Ext.Relay | PAR Engineering ★PCR★ 200hrs×6×$200/hr | — | — | — | — | 40000 | 80000 | 80000 | 40000 | — | — | — | — | 240000 | ★PCR
12 | Ext.Relay | PAR Installation ★PCR★ ~1,298hrs×$200/hr | — | — | — | — | — | — | — | 64875 | 64875 | 64875 | 64875 | — | 259500 | ★PCR
13 | Procure | PAR Materials ★PCR★ | — | — | — | — | — | — | 30000 | — | — | — | — | — | 30000 | ★PCR
14 | B&M | Ph3 MPLS Design ★PCR★ (accelerated into Ph2) | — | — | — | — | — | — | 120000 | 120000 | 120000 | — | — | — | 360000 | ★PCR
15 | PSEG | Internal Labor (all resources) | 13537 | 6082 | 13537 | 13537 | 14684 | 14684 | 14684 | 14684 | 14684 | 14684 | 14684 | 14684 | 164165 | Labor
16 | Cognizant | Lee Blackman $7,200/mo | 15000 | 15000 | 29000 | 14902 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 131502 | OS
17 | PSEG | Assessments/PQA/Chad/Umair | 11696 | 3396 | 12000 | 3669 | 6067 | 7567 | 5307 | 4567 | 4567 | 4567 | 4267 | 5067 | 72737 | Assess
MONTHLY TOTAL |  |  | 45733 | 29978 | 1149403 | 252289 | 272474 | 331981 | 362776 | 408329 | 358312 | 198244 | 157876 | 93801 | 3661196
CUMULATIVE SPEND |  |  | 45733 | 75711 | 1225114 | 1477403 | 1749877 | 2081858 | 2444634 | 2852963 | 3211275 | 3409519 | 3567395 | 3661196 | 3661196
CP BUDGET 2026 = $2,600,000 |  |  | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | BUDGET
VARIANCE (Budget − Cumulative) 🔴 RED = OVER BUDGET |  |  | 2554267 | 2524289 | 1374886 | 1122597 | 850123 | 518142 | 155366 | -252963 | -611275 | -809519 | -967395 | -1061196 | -1061196 | ⚠ OVER
▶ SECTION 3 — OPTIONS TO CLOSE THE GAP
Option | Action | $ Impact | Recommendation
1 ✅ RECOMMENDED | Submit FULL PCR: PAR $530K + Ph3 Accel $800K → Request 2026 budget increase to ~$3.93M | [5 empty] | May: +$1,330,000; Jul: Best path. Scope is real and confirmed by Vic. Recovers 5-month schedule slip. Without this, Phase 2 construction CANNOT start Aug 5 — budget is exhausted in June. Vic already briefed. Submit ASAP to Finance/CIO.
2 — PARTIAL | Submit PAR PCR only ($530K) Defer Ph3 MPLS design to 2027 budget | [5 empty] | May: +$530,000; Jul: Partial relief. Still $759K over on base contracted work. Need to explain to CIO why we're already over budget before PCR. Works if Finance won't approve $1.33M in one shot.
3 — AGGRESSIVE | Defer PAR installation to Jan 2027 Keep PAR engineering in 2026 only | [5 empty] | May: Saves $259,500 in 2026; Jul: Risky — delays NERC-CIP compliance. RC-30 already ordered (8-week lead). Team is ready. Deferring = wasted momentum. Not recommended.
4 ❌ WORST CASE | Do nothing — absorb overrun | [5 empty] | May: −$1,648,937 unfunded; Jul: Not viable. Budget exhausted June 2026. Phase 2 construction halts Aug 5. Hawkeye field teams idle. Schedule slips to 2028. NERC-CIP non-compliance risk.

## SUMMARY
PRJ13797 – JMUX Replacement ¦ Vendor & Internal Cost Forecast 2026 & 2027
Source: B&M SOW v03 (Aug 2025) · Hawkeye Phase 2 SOW (Mar 2026) · Call minutes May 18 2026 ¦ Prepared: May 18 2026
Vendor / Category | Service / Deliverable | PO / Reference | Phase | Timing | SOW / Est. Total ($) | 2026 ($) | 2027 ($) | Notes / Basis
BURNS & McDONNELL (B&M) — SOW Fixed Price: $1,370,040 ¦ PO Balance Remaining: ~$400K
B&M | PM Service (Alex Lenox – Project Coordinator) | PO7000001429 | Ph2 | 2026 | 66000 | 66000 |  | $5,500/mo × 12 months. Static monthly cost.
B&M | Phase 1 Staging Support (Milestone 1 – carryover) | PO7000001415 | Ph1→2026 | 2026 | 57300 | 57300 |  | B&M SOW Milestone 1: $57,300 fixed. Staging test plan, card slotting, SFP install.
B&M | Phase 1 Construction Support Coordinator (Milestone 2 – monthly Aug 2025–Jan 2026) | PO7000001415 | Ph1 | 2025→2026 | 368100 | 61350 |  | B&M SOW Milestone 2: $368,100 total (~$61,350/mo). Aug 2025–Jan 2026. ~1 month in 2026.
B&M | Substation Site Surveys – Phase 2 (Milestone 3 – 36 sites) | PO7000002099 | Ph2 | 2026 Jan–Feb | 86040 | 86040 |  | B&M SOW Milestone 3: $86,040 fixed. 36 sites × 3 weeks. Completed Feb 27 2026.
B&M | MPLS Node Design – IFR 36 sites × $16,695 = $601,020 | PO7000001415 / PO7000002099 | Ph2 | 2026 Jan–Jun | 601020 | 601020 |  | B&M Appendix D: 36 × $16,695. Rolling IFRs Jan–Jun 2026. All IFRs due Jun 29 2026.
B&M | MPLS Node Design – IFC 36 sites × $5,963 = $214,668 | PO7000001415 / PO7000002099 | Ph2 | 2026 Mar–Jul | 214668 | 214668 |  | B&M Appendix D: 36 × $5,963. Rolling IFCs Mar–Jul 2026. All IFCs due Jul 13 2026.
B&M | MPLS Node Design – As-Built (Phase 2) → ALL As-Builts consolidated into Phase 3 row below | PO7000001415 / PO7000002099 | → Ph3 | → See Ph3 row |  |  |  | ★ Phase 2 As-Builts ($42,912) moved to Phase 3 consolidated row. All phases together 2027.
B&M | Phase 2 Construction Support Coordinator (Milestone 2 Ph2 – monthly Aug–Dec 2026) | PO7000001415 | Ph2 | 2026 Aug–Dec | 382824 | 382824 |  | B&M SOW Milestone 2 (Phase 2): On-site coordinator up to 45 hrs/wk. ~$61,350/mo × ~6 months.
B&M | Phase 3 Engineering – IFR + IFC 31 sites × $22,658 (ACCELERATED from 2027→2026) | TBD – Ph3 PO | Ph3 | 2026 start / 2027 complete | 702398 | 215000 | 487398 | Surveys + IFRs start Aug 2026 during Ph2 staging. ~1/3 in 2026, ~2/3 in 2027. Avoids 2028 schedule slip.
B&M | MPLS Node Design – As-Built ★ ALL PHASES CONSOLIDATED → PHASE 3 Phase 1: 31 sites × $1,192 = $36,952 Phase 2: 36 sites × $1,192 = $42,912 Phase 3: 31 sites × $1,192 = $36,952 TOTAL: 98 sites = $116,816 | PO7000001415 / PO7000002099 / TBD Ph3 | Ph1+2+3 | 2027 – Phase 3 (ALL As-Builts) | 116816 |  | 116816 | ★ UPDATED per Jay: ALL As-Builts (Ph1+Ph2+Ph3) deferred to Phase 3. Ph1: 31×$1,192=$36,952 ¦ Ph2: 36×$1,192=$42,912 ¦ Ph3: 31×$1,192=$36,952 ¦ TOTAL: $116,816. Issued AFTER all Phase 3 construction complete.
SUBTOTAL — B&M TOTAL |  |  |  |  | 2158962 | 1683202 | 567262
HAWKEYE CONSTRUCTION (ELECNOR HAWKEYE LLC) — SOW Fixed Price: $400,680 ¦ Target completion: Dec 31 2026
Hawkeye | Milestone Ph0: Equipment Staging & Assembly Receive, rack, load firmware, burn-in & test all 36 Phase 2 Nokia nodes at Hawkeye lab | PO7000002099 | Ph2 | 2026 Jun–Aug | 100170 | 100170 |  | Hawkeye SOW Milestone Ph0: $100,170 (25% of $400,680). Lab assembly before site shipment.
Hawkeye | Milestone 1: Site Surveys (pre-construction) On-site: cable types, power verification, rack space per IFC | PO7000002099 | Ph2 | 2026 May–Jul | 100170 | 100170 |  | Hawkeye SOW Milestone 1: $100,170 (25%). 3 mobilisations/site. Vinny started week of May 18 2026.
Hawkeye | Milestone 2: Installation Complete – All 36 Sites Install Nokia SAR-8, CWDM, Eltek PSU, RS-232 patch panel, fiber, CAT6, 4-wire VF. Energize & test. | PO7000002099 | Ph2 | 2026 Aug–Sep | 80136 | 80136 |  | Hawkeye SOW Milestone 2: $80,136 (20%). Construction start Aug 5 2026. Notify PSEG Relay when ready for migration.
Hawkeye | Milestone 4: Project Ready for Go-Live All 36 sites installed, tested, relay migration complete, PSEG sign-off | PO7000002099 | Ph2 | 2026 Sep–Oct | 80136 | 80136 |  | Hawkeye SOW Milestone 4: $80,136 (20%). Go-live approval from Vic/PSEG.
Hawkeye | Hawkeye – Decommissioning ★ ALL PHASES IN PHASE 3 Phase 2: 36 sites – $40,068 (SOW Milestone 6, 10% of SOW) Phase 3: 31 sites – ~$34,503 (est. $1,113/site same rate) TOTAL: 67 sites = ~$74,571 | PO7000002099 / TBD Ph3 | Ph2+Ph3 | 2027 – Phase 3 (ALL Decommissioning) | 74571 |  | 74571 | ★ UPDATED per Jay: ALL Hawkeye decommissioning moved to Phase 3. Cannot begin until ALL circuits migrated off JMUX across all phases. Ph2 SOW Milestone 6 = $40,068 ¦ Ph3 estimated = ~$34,503 (31 sites @ $1,113/site) ¦ TOTAL ~$74,571.
SUBTOTAL — HAWKEYE TOTAL (SOW $400,680) |  |  |  |  | 400680 | 360612 | 40068
NOKIA & EQUIPMENT — Master PO: $1,899,000 ¦ Phase 2 paid: $733,293 ¦ Phase 3 remaining: ~$395,000
Nokia | Phase 2 Equipment 36 Nokia 7705 SAR nodes + cards + SFPs [DELIVERED & PAID] | PO7000001811/2119/1841/1767 | Ph2 | PAID 2025/2026 | 733293 |  |  | ALL Phase 2 equipment delivered and paid. No further 2026 Nokia Phase 2 cost.
Nokia | Phase 3 Equipment 31 Nokia 7705 SAR nodes + cards [ORDER ~Q3 2026, DELIVER 2027] | TBD – Ph3 PO | Ph3 | 2027 | 395000 |  | 395000 | Remaining $395K on master $1.899M PO. Confirm BOM with Ethan/Tim. Lead time ~8-12 wks. Order Q3 2026, deliver Q1 2027.
Presidio | CWDM Cards (Phase 2: ~8-10 additional ¦ Phase 3: TBD) | TBD – Presidio PO | Ph2+3 | 2026 / 2027 | 35000 | 15000 | 20000 | Graybar closed. Presidio source. ~$1,500-2,000/card. Count to confirm with Ethan/Tim.
Presidio | Power Supplies + Accessories (Phase 2+3) | TBD – Presidio PO | Ph2+3 | 2026 / 2027 | 20000 | 10000 | 10000 | Eltek converters ~$2K each. 8-10 more needed. Phase 3 BOM TBD.
SUBTOTAL — NOKIA / EQUIPMENT TOTAL (excl. Phase 2 already paid) |  |  |  |  | 450000 | 25000 | 425000
PAR (PHASE ANGLE REGULATOR) — NEW SCOPE ¦ 6 Sites: Northport · 5HK · Melville · 7Z Lindenhurst · 2H Far Rockaway · 2R Hewlett ¦ All 2026
PAR – Material | PAR – Materials Cables, connectors, misc per Vic May 18 call | EO#7000002695 | Ph2 | 2026 (ordered) | 30000 |  | 30000 | ★ Vic confirmed $30K for cables and connectors across 6 PAR sites.
PAR – Engineering | PAR – Engineering Design (Protection Engineering team) 200 hrs/site × 6 sites × $200/hr = $240,000 ★ CONFIRMED by Vic, May 18 2026 call | Internal – Chok team | Ph2 | 2026 May–Sep | 240000 |  | 240000 | ★ CONFIRMED Vic May 18: 200 hrs × 6 sites × $200/hr = $240K. External relay/protection engineers (NOT internal PSEG rate of $134.14/hr). $200/hr is the relay protection team billing rate.
PAR – Install | PAR – Installation, Configuration & Cutover Labor ~1,298 hrs × $200/hr = $259,500 ★ CONFIRMED by Vic, May 18 2026 call (previously $195,600 — REVISED) | Internal – Steven's team | Ph2 | 2026 Aug–Dec | 259500 |  | 259500 | ★ CONFIRMED Vic May 18: relay team install ~1,298 hrs × $200/hr = $259,500. Previously $195,600 (too low). Call with Steven needed before Monday to confirm exact hours by month. External relay team @ $200/hr.
SUBTOTAL — PAR TOTAL (Chok $240K inflated — expect ~$50-80K actual after meeting) |  |  |  |  | 529500 |  | 529500 | ★ CONFIRMED Vic May 18 2026: PAR TOTAL = $529,500 (Eng $240K + Install $259.5K + Materials $30K). PCR to be submitted Q2 2026. Engineering runs in PARALLEL with Phase 2 — no schedule impact. Steven Bradley call set before Monday to lock hours.
INTERNAL PSEG / PROJECT MANAGEMENT — Named Resources
Internal – PM | Jaya Gunaratne Project Manager – PRJ13797 | PSEG Internal | Ph2+3 | 2026 + 2027 | 300000 | 300000 | 300000 | Full-time PM through project completion (Phase 2 + 3). PSEG internal charge.
Internal – Finance | Chad (Controller) Project Financial Controller | PSEG Internal | Ph2+3 | 2026 + 2027 | 200000 | 100000 | 100000 | Internal financial controller. SAP extract, monthly forecast, variance reporting, URB prep.
Internal – Scheduling | Umair (Scheduler) Project Scheduler | PSEG Internal | Ph2+3 | 2026 + 2027 | 80000 | 40000 | 40000 | Internal schedule resource. Maintains Phase 2 + 3 project plans, updates milestones.
Internal – Ops | Rahiq Internal Operations / Deployment Support | PSEG Internal | Ph2+3 | 2026 + 2027 | 130000 | 70000 | 60000 | PSEG internal deployment support. On-site coordination, change management, RTU migration ops.
Internal – Ops | Brianna Internal Operations / Deployment Support | PSEG Internal | Ph2+3 | 2026 + 2027 | 130000 | 70000 | 60000 | PSEG internal deployment support. On-site coordination, change management, RTU migration ops.
Cognizant | Lee Blackman O/S Sr. Network Engineer | Outside Services | Ph2+3 | 2026 + 2027 | 250000 | 150000 | 100000 | $7,200/month through Phase 2 completion. Engineering oversight, IP addressing, BGP design, IFR review.
Internal | PQA / Assessments (capped at 3.5%) Process & Quality Assurance overhead | PSEG Internal | Ph2+3 | 2026 + 2027 | 220000 | 120000 | 100000 | Capped at 3.5% total budget. Joe Jekyll agreed: PCR cards for budget variances. PQA audit rates negotiated down (Marge/PQA).
Internal – Relay | Relay Team Support – John's team RTU Circuit Cutovers [SEPARATE FROM PAR] | PSEG Internal | Ph2 | 2026 + 2027 | 500000 | 400000 | 100000 | Internal PSEG relay team for RTU circuit cutovers at all Phase 2 sites. Actual rate ~$65-$150/hr. Distinct from PAR installation (Steve Bradley). Validate actuals per site.
SUBTOTAL — INTERNAL / PM TOTAL |  |  |  |  | 1810000 | 1250000 | 860000
GRAND TOTAL — ALL VENDORS + INTERNAL + PAR |  |  |  |  | 5307742 | 3900814 | 1963785 | ★ UPDATED May 18 2026 per Vic call: PAR confirmed $529,500 (eng $240K + install $259.5K + materials $30K). PCR request: PAR $530K + Ph3 accel $800K = ~$1.2-1.33M to be submitted. Phase 3 site surveys + MPLS design accelerated into Phase 2. Steven call before Monday to lock relay labor hours by month. Frame relay internal team: still no actuals — Chad needs names + hours.
COLOUR LEGEND
B&M – Fixed price per SOW Appendix D ($23,850/site: IFR $16,695 + IFC $5,963 + As-Built $1,192)
Hawkeye – Fixed price $400,680 for Phase 2 (5 milestones)
Costs split / accelerated across 2026 & 2027 based on schedule
PAR costs – new scope not in original budget
PAR Chok engineering – FORECAST ONLY. Actual ~$5K to date. Expect major downward revision.
Internal PSEG named resources + deferred items (As-Builts, decommissioning, Nokia Ph3)
Nokia/Presidio equipment costs

## B&M Site Breakdown
B&M – MPLS Node Design Cost by Site ¦ Appendix D, SOW v03 ¦ 36 Phase 2 Sites ¦ Total: $858,600
Per site: IFR $16,695 ¦ IFC $5,963 ¦ As-Built $1,192 ¦ Total $23,850 ¦¦ IFR + IFC = 2026 ¦ As-Builts = 2027
Code | Site Name | IFR Schedule | IFR ($) | IFC ($) | As-Built ($) | Total ($) | IFC Schedule / Notes
2H | Far Rockaway | Jan 27 – Feb 23 | 16695 | 5963 | 1192 | 23850 | IFC: Mar 10 – Mar 23 ¦ As-Built: 2027
2K | Valley Stream | Jan 27 – Feb 23 | 16695 | 5963 | 1192 | 23850 | IFC: Mar 10 – Mar 23 ¦ As-Built: 2027
2KB | Cedarhurst | Jan 27 – Feb 23 | 16695 | 5963 | 1192 | 23850 | IFC: Mar 10 – Mar 23 ¦ As-Built: 2027
2R | Hewlett | Feb 17 – Mar 16 | 16695 | 5963 | 1192 | 23850 | IFC: Mar 31 – Apr 13 ¦ As-Built: 2027
2R1 | Hewlett Shelter | Feb 17 – Mar 16 | 16695 | 5963 | 1192 | 23850 | IFC: Mar 31 – Apr 13 ¦ As-Built: 2027
2RB | Green Acres | Mar 3 – Mar 30 | 16695 | 5963 | 1192 | 23850 | IFC: Apr 14 – Apr 27 ¦ As-Built: 2027
2WB | Barrett Power Plant | Mar 3 – Mar 30 | 16695 | 5963 | 1192 | 23850 | IFC: Apr 14 – Apr 27 ¦ As-Built: 2027
2ZB | Barrett PS (EF Barrett) | Mar 17 – Apr 13 | 16695 | 5963 | 1192 | 23850 | IFC: Apr 28 – May 11 ¦ As-Built: 2027
3J | Whiteside | Mar 31 – Apr 27 | 16695 | 5963 | 1192 | 23850 | IFC: May 12 – May 26 ¦ As-Built: 2027
4M | Baldwin | Apr 7 – May 4 | 16695 | 5963 | 1192 | 23850 | IFC: May 19 – Jun 2 ¦ As-Built: 2027
4M1 | Baldwin Shelter | Apr 7 – May 4 | 16695 | 5963 | 1192 | 23850 | IFC: May 19 – Jun 2 ¦ As-Built: 2027
6H | Hauppauge | Apr 14 – May 11 | 16695 | 5963 | 1192 | 23850 | IFC: May 27 – Jun 9 ¦ As-Built: 2027
6H1 | Hauppauge Tower Shelter | Apr 14 – May 11 | 16695 | 5963 | 1192 | 23850 | IFC: May 27 – Jun 9 ¦ As-Built: 2027
6K | State School | Apr 14 – May 11 | 16695 | 5963 | 1192 | 23850 | IFC: May 27 – Jun 9 ¦ As-Built: 2027
6S | Kings Hwy | Apr 21 – May 18 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 3 – Jun 16 ¦ As-Built: 2027
7BH | Bohemia | Apr 21 – May 18 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 3 – Jun 16 ¦ As-Built: 2027
7D | West Babylon | Apr 28 – May 26 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 10 – Jun 23 ¦ As-Built: 2027
7D1 | West Babylon Shelter | Apr 28 – May 26 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 10 – Jun 23 ¦ As-Built: 2027
7H | Babylon | May 5 – Jun 2 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 17 – Jun 30 ¦ As-Built: 2027
7H1 | Babylon Shelter | May 5 – Jun 2 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 17 – Jun 30 ¦ As-Built: 2027
7J | Sterling | May 5 – Jun 2 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 17 – Jun 30 ¦ As-Built: 2027
7M | MacArthur | May 12 – Jun 9 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
7R | Sayville | May 12 – Jun 9 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
7RM | Bayport | May 12 – Jun 9 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
7UM | South Farmingdale | May 12 – Jun 9 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
7W | Berry St. | May 19 – Jun 16 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
7XM | Great River | May 19 – Jun 16 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
7XM1 | Great River Shelter | May 19 – Jun 16 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
7Z | Lindenhurst | May 19 – Jun 16 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
8AX | Patchogue | May 19 – Jun 16 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
8AX1 | Patchogue Shelter | May 19 – Jun 16 | 16695 | 5963 | 1192 | 23850 | IFC: Jun 24 – Jul 8 ¦ As-Built: 2027
D.O. | Brentwood D.O. | May 27 – Jun 23 | 16695 | 5963 | 1192 | 23850 | IFC: Jul 9 – Jul 22 ¦ As-Built: 2027
D.O. | Hewlett Headquarters | May 27 – Jun 23 | 16695 | 5963 | 1192 | 23850 | IFC: Jul 9 – Jul 22 ¦ As-Built: 2027
5HK | Hicksville Primary | May 27 – Jun 23 | 16695 | 5963 | 1192 | 23850 | IFC: Jul 9 – Jul 22 ¦ As-Built: 2027
6U | Ruland Road | May 27 – Jun 23 | 16695 | 5963 | 1192 | 23850 | IFC: Jul 9 – Jul 22 ¦ As-Built: 2027
ACC | ACC | Jun 3 – Jun 30 | 16695 | 5963 | 1192 | 23850 | IFC: Jul 16 – Jul 29 ¦ As-Built: 2027
TOTAL | 36 sites | 2026 | 601020 | 214668 | 42912 | 858600 | IFR + IFC = 2026 ($815,688) ¦ As-Builts = 2027 ($42,912)

## Nokia Ph3 Equipment
PRJ13797 – JMUX Replacement ¦ Nokia Phase 3 Equipment Order ¦ Sales Doc. 14937998 ¦ Prepared: May 18 2026
Changes per Ethan Koch (B&M), May 12 2026: ① Remove 4W E&M cards (Item 100) — may have enough remaining from Phase 2 ② NSP IP Control licenses already removed (RMA'd) ③ Add 4× 10G SFP+ CWDM 1491nm optics (new line)
# | Item | Material # | Description | Qty | Unit Price ($) | Net Value ($) | Tax ($) | Revised Net ($) | Status / Notes
1 | 10 | 3HE00062CB | SFP - GIGE BASE-T RJ45 R6/6 DDM -40/85C | 14 | 106.26 | 1487.64 | 130.17 | 1487.64 | KEEP
2 | 20 | 3HE00028CA | SFP - GIGE LX - LC ROHS 6/6 DDM -40/85C | 14 | 111.44 | 1560.16 | 136.51 | 1560.16 | KEEP
3 | 30 | 3HE12410AA | DCE CABLE for SDI V3 | 14 | 245 | 3430 | 300.12 | 3430 | KEEP
4 | 40 | 3HE02784UA | SAR RELEASE 24.x BASIC OS LICENSE | 14 | 297.5 | 4165 | 364.44 | 4165 | KEEP
5 | 50 | 3HE16016AA | NSP IP CONTROL CLASS 1 NODE | 56 | 140 | 7840 | 686 | 0 | REMOVED – RMA'd
6 | 60 | 3HE12442AA | 4 PORT RS232 DIST PANEL, SDIv3 ONLY | 14 | 595 | 8330 | 728.88 | 8330 | KEEP
7 | 70 | 3HE06792FA | FAN/ALARM MODULE SAR-8 V2 -48/+24VDC cc | 14 | 630 | 8820 | 771.75 | 8820 | KEEP
8 | 80 | 3HE07354AH | RTU - MDDB LICENSE (ADDITIONAL NODES) | 14 | 700 | 9800 | 857.5 | 9800 | KEEP
9 | 90 | 3HE06791BA | SAR-8 SHELF V2/CONFORMAL COATED | 14 | 1050 | 14700 | 1286.25 | 14700 | KEEP
10 | 100 | 3HE03126BA | 6P E AND M CARD cc (4W E&M) | 14 | 1662.5 | 23275 | 2036.56 | 0 | REMOVED – Ethan: may have enough from Phase 2
11 | 110 | 3HE07942BA | INTEGRATED SERVICES CARD (ISC) cc | 14 | 2100 | 29400 | 2572.5 | 29400 | KEEP
12 | 120 | 3HE07161CA | SFP+ 10GE CWDM 1471nm 40km R6/6 DDM 0/70C | 28 | 1175.51 | 32914.28 | 2880 | 32914.28 | KEEP
13 | 130 | 3HE02774CB | CTL SWITCH MODULE V2 -48/+24VDC cc | 28 | 1417.5 | 39690 | 3472.88 | 39690 | KEEP
14 | 140 | 3HE03391BC | 12P SERIAL DATA CARD V3 -48/+24VDC cc | 14 | 3780 | 52920 | 4630.5 | 52920 | KEEP
15 | 150 | 3HE07943BA | 6P 2×10GE, 4×1GE 10G CARD CC | 28 | 5600 | 156800 | 13720 | 156800 | KEEP
16 | NEW | 3HE07161BA | SFP+ 10GE CWDM 1491nm 40km R6/6 DDM 0/70C ★ ADDED per Ethan Koch | 4 | 1175.51 | 4702.04 | 411.43 | 4702.04 | NEW – Added per Ethan email May 12 2026
Original Order Total (Sales Doc. 14937998) | [7 empty] | 395132.08
Less: NSP IP Control licenses (RMA'd Item 50) | [7 empty] | -7840
Less: 4W E&M Cards removed (Item 100) | [7 empty] | -23275
Add: 4× SFP+ 10GE CWDM 1491nm (NEW) | [7 empty] | 4702.04
REVISED ORDER TOTAL | [7 empty] | 368719.12
NOTES FROM ETHAN KOCH (B&M) — May 12 2026
① | NSP IP Control licenses (Item 50): Already removed from this order — RMA'd. $7,840 credited back.
② | 4W E&M Cards (Item 100, 3HE03126BA): REMOVE from this order. Many Phase 2 sites don't need this card. We may have enough remaining inventory to carry through end of project. Confirm final count when detailed designs complete.
③ | 10G CWDM 1491nm SFP+ optics: ADD 4 additional units of the 1491nm wavelength option (material 3HE07161BA) in addition to the 28× 1471nm units already on order. Priced at same rate as 1471nm ($1,175.51 each = $4,702.04). Added as new line.
④ | Final true-up order pending. Detailed designs must be completed to get final counts for all Phase 3 sites. This order is a forecast — quantities subject to change.

## Internal Labor
PRJ13797 – JMUX Replacement ¦ Internal Labor & Outside Services Breakdown ¦ Source: Chad's Controller Workbook (May 18 2026)
CP Budget: $6,600,000 ¦ Spend to Date: $5,908,822 ¦ Remaining Budget: $691,178 ¦ ETC: $1,228,577 ¦ EAC: $7,137,399 ¦ Projected Variance: -$537,399 (-8.1%)
SECTION 1 — PROJECT FINANCIAL SUMMARY (from Dashboard tab)
Category | 2024 O&M | 2025 O&M | O&M Total | 2024 Cap | 2025 Cap | Cap Total | Proj Total
Internal Labor | 93702 | 0 | 93702 | 29358 | 134069 | 163427 | 257129
Materials | 0 | 0 | 0 | 601380 | 219015 | 820395 | 820395
Outside Services | 162200 | 7168 | 169368 | 103409 | 1549312 | 1652721 | 1822089
Assessments | 19172 | 0 | 19172 | 7060 | 56330 | 63390 | 82562
TOTAL | 275074 | 7168 | 282242 | 741206 | 1958726 | 2699932 | 2982174
SECTION 2 — INTERNAL PSEG LABOR (from Detailed Forecast vs Actuals tab)
# | Resource Name | Role / Title | WBS Code | 2025 Rate ($/hr) | 2026 Rate | Type | 2025 Actuals | 2026 Forecast | Total | Notes
1 | MARTIN GATELY ⚠ NO LONGER WITH PSEG — REMOVE FROM FORECAST | Project Manager (DEPARTED) | I.39424.2.1 | 116.84 | TBD | DEPARTED | 133886 | 0 | 0 | ⚠ DEPARTED — Martin Gately no longer with PSEG as of May 2026. 2025 actuals ($133,886) already charged to SAP — sunk cost. 2026 forecast = $0. Remove from all future projections.
2 | DHANANJAYA GUNARATNE | Project Manager (Jay) | I.39424.2.3 | 145 | $145/hr | Capital |  | 174000 | 174000 | Hermitage / PM. $145/hr rate. Full-time PM through project completion.
3 | Ahsan Khawaja | Project Manager | I.39424.2.3 | 257619 | 257619 | Capital |  | 257619 | 257619 | Hermitage / PM. PO amount $257,618.69.
4 | RAHIQ MOHAMED | Engineer / Deployment Support | I.39424.2.1 | 92.65 | TBD | Capital |  | 70000 | 70000 | Engineer, on-site deployment support. $92.65/hr 2025 rate.
5 | BRIANNA FOREMAN | Engineer / Deployment Support | I.39424.2.1 | 92.65 | TBD | Capital |  | 70000 | 70000 | Engineer, on-site deployment support. $92.65/hr 2025 rate.
6 | CHAKRAPANI VENUGOPALAN | PAR Engineering Lead (Chok) | I.39424.2.1 | 134.14 | TBD | Capital | 5000 | 235000 | 240000 | ⚠ FORECAST INFLATED: 1,200 hrs × $134.14 = $160,968 MAX (not $240K). Actual to date ~$5K. Meeting this week to confirm real forecast. Note: Lok Wong = $115.34/hr, Sameer Shakur = $66.50/hr also on PAR design.
7 | LOK WONG | PAR Design Engineer | I.39424.2.1 | 115.34 | Add FRINGE | Capital |  | 30000 | 30000 | PAR design support. Rate $115.34/hr + fringe. Subset of Chok PAR team.
8 | Sameer Shakur | PAR Design Engineer | I.39424.2.1 | 66.5 | Add FRINGE | Capital |  | 20000 | 20000 | PAR design support. Rate $66.50/hr + fringe. Subset of Chok PAR team.
9 | STEVEN BRADLEY | Relay Team / PAR Installation Lead | I.39424.2.1 | 93.5 | TBD | Capital | 58716 | 195600 | 254316 | PAR installation at 6 sites. 2025 actuals: Dec $29,358 × 2 WBS codes = $58,716. 2026 forecast: 1,056 hrs × ~$185/hr = $195,600 (revised from $494K).
10 | Lee Blackman | Sr. Network Architect (Cognizant O/S) | I.39424.2.1 | 0 | $7,200/mo | Capital |  | 86400 | 86400 | Cognizant outside services. $7,200/month through Phase 2. Listed under internal in workbook but billed as outside services.
11 | KELLY VAUGHN | T&D Substation Engineer | I.39424.2.1 | 83.26 | TBD | Capital | 624 | 20000 | 20624 | Feb actuals $624.45. Senior Engineer T&D substation support.
12 | Artur Karczewski | IT Ops Senior Analyst | I.39424.2.1 | 65.08 | TBD | Capital | 521 | 15000 | 15521 | Feb actuals $520.64. IT Ops support.
13 | GEORGES VOLCY | IT Ops Principal | I.39424.2.1 | 83.83 | TBD | Capital | 210 | 10000 | 10210 | Feb actuals $209.58.
14 | LAWRENCE VARGHESE | IT Ops Associate | I.39424.2.1 | 50.75 | TBD | Capital | 406 | 10000 | 10406 | Feb actuals $406.00.
15 | CHRISTOPHER ZIMBALIST | IT Staff | I.39424.2.1 | 82.86 | TBD | Capital |  | 10000 | 10000 | $82.86/hr.
16 | Margaret Tanner Glover | PQA / Quality Assurance (Marge) | I.39424.2.1 | 113.57 | TBD | Capital |  | 40000 | 40000 | PQA audit time. Rate $113.57/hr. Audit hours being reconciled — possible overcharging under investigation. Capped at 3.5% total budget.
17 | EVAN SOVIERO | IT Staff / PM Support | I.39424.2.1 | 75.39 | TBD | Capital |  | 10000 | 10000 | $75.39/hr.
18 | ALFREDO TELLO | Project Manager (prior) | I.39424.2.1 | 75.39 | TBD | Capital |  |  |  | Previous PM. No 2026 forecast.
19 | Matthew Costa | Project Manager (prior) | I.39424.2.1 | 75.39 | TBD | Capital |  |  |  | Previous PM. No 2026 forecast.
SUBTOTAL — INTERNAL PSEG LABOR (all named resources) | [6 empty] | 199363 | 1253619 | 1452982 | ⚠ Chok PAR $235K 2026 forecast is inflated — actual ~$5K. Expect revision after meeting.
SECTION 3 — OUTSIDE SERVICES (from Controller Workbook)
# | Vendor | Service / Person | WBS Code | PO Number | PO Amount | Type | 2025 Actuals | 2026 Forecast | Total | Notes
1 | Burns & McDonnell | Alex Lennox — PM Coordination | I.39424.2.3 | 7000001429 / 5000055979 | 316200 | Capital |  | 66000 | 66000 | $5,500/mo × 12 = $66,000 2026. Two PO numbers both $316,200.
2 | Burns & McDonnell | Implementation — Construction Support | I.39424.2.3 | 7000001415 / 5000058992 | 788100 | Capital | 788100 | 382824 | 1170924 | Phase 1 CSC complete ($368,100 paid 2025). Phase 2 CSC = $382,824 starts Aug 2026.
3 | Burns & McDonnell | JMUX Network Design (SOW v03) | I.39424.2.3 | 7000002099 | 1370040 | Capital | 229380 | 901020 | 1130400 | SOW $1,370,040 total. Site surveys + IFR + IFC + staging. 2025 actuals = surveys/staging. 2026 = bulk of IFR/IFC work.
4 | Cognizant | Lee Blackman — Sr. Network Architect | I.39424.2.3 | 7000002490 / 7000000729 | 86400 | Capital |  | 86400 | 86400 | $7,200/month through Phase 2 completion.
5 | Hermitage | Dhananjaya Gunaratne — PM | I.39424.2.3 | 7000002000 |  | Capital |  | 174000 | 174000 | $145/hr. Full-time PM. Also listed under internal labor above — avoid double counting.
6 | Hermitage | Ahsan Khawaja — PM | I.39424.2.3 | 7000001734 | 257619 | Capital |  | 257619 | 257619 | PO amount $257,618.69.
7 | Hermitage | Edward Laurence Schwartz — PQA Lead | I.39424.2.3 | 7000001998 |  | Capital |  | 30000 | 30000 | PQA lead support.
8 | ComTec | Chad Boyett — Controller | I.39424.2.3 | 5000060473 |  | Capital |  | 60000 | 60000 | Rate = 5% (of what — TBD). Controller, SAP extract, monthly forecast, variance reporting.
9 | ComTec | Umair Mohammed — Scheduler | I.39424.2.3 | 7000001145 / 7000002363 |  | Capital |  | 40000 | 40000 | Project scheduler. Maintains Phase 2+3 plans.
10 | ComTec | Farouk Adelekan — Scheduler (backup) | I.39424.2.3 | 5000046818 |  | Capital |  | 20000 | 20000 | Rate = 2.5%. Backup scheduler.
11 | Cognizant / EPMO | PQA Audit | I.39424.2.3 | 7000002439 / 7000001527 |  | Capital | 56330 | 40000 | 96330 | 2025 actuals $56,330. PQA audit time. Rate under investigation (Marge). Capped at 3.5% total budget per Joe Jekyll PCR.
12 | Elecnor Hawkeye | Phase 1 SOW + Addendum 1 | I.39424.2.3 | MA#8447 | 402793 | Capital | 335993 |  | 335993 | Phase 1 complete. $402,793 total (base $333,900 + addendum $68,893). M6 decommission $66,780 unpaid → Phase 3.
13 | Elecnor Hawkeye | Phase 2 SOW | I.39424.2.3 | PO7000002099 | 400680 | Capital |  | 360612 | 360612 | Phase 2 SOW $400,680. M6 decommission $40,068 → Phase 3. 2026 = M-Ph0+M1+M2+M4 = $360,612.
14 | Elecnor Hawkeye | WD#8 — Fiber Testing + Patch Panels | I.39424.2.3 | 7000009182 | 8229 | Capital |  | 8229 | 8229 | WD#8: Fiber testing Elwood→Northport + 7 patch panels = $8,229.
15 | TRC | Raju Khedkar — Cyber Security Architect | I.39424.2.3 | 7000001237 / 7000002343 |  | Capital |  | 30000 | 30000 | NERC-CIP / cyber security design review.
16 | Beeline | Marcott, Richard | I.39424.2.3 | 4501316055 |  | Capital |  |  |  | Beeline contractor. No 2026 forecast entered.
SUBTOTAL — OUTSIDE SERVICES (all vendors) | [6 empty] | 1409803 | 2456704 | 3866507 | NOTE: Jay/Ahsan in both Internal Labor and Outside Services — avoid double counting.
SECTION 4 — KEY CONTROLLER NOTES (from Chad's workbook, May 18 2026)
Item | Value | Notes / Context
CP Budget | $6,600,000 | Total Capital Program budget: $750K (2024) + $3.25M (2025) + $2.6M (2026)
Spend to Date | $5,908,822 | 2024: $741,206 ¦ 2025: $3,130,120 ¦ 2026 to date: $2,037,496
ETC | $1,228,577 | Estimate to Complete — remaining 2026 spend needed
EAC | $7,137,399 | Estimate at Completion = $537,399 OVER budget (-8.1% variance)
2026 Remaining Budget | $562,504 | 2026 CP budget $2.6M minus $2.037M spent = $562,504 remaining
2026 Projected Variance | -$666,073 | 2026 is tracking $666K over budget — REQUIRES PCR or budget reallocation
Lok Wong rate | $115.34/hr | Rate confirmed in workbook. Note: 'Add FRINGE' flag — fringe not yet included in base rate
Sameer Shakur rate | $66.50/hr | PAR design. 'Add FRINGE' flag — fringe not yet included
Steven Bradley rate | $93.50/hr | Relay installation lead. 2025 actuals Dec $29,358 each on 2 WBS = $58,716 total
Chak rate | $134.14/hr | Max PAR engineering: 1,200 hrs × $134.14 = $160,968 (NOT $240K as originally forecast)
Martin Gately | ⚠ DEPARTED — No longer with PSEG. 2025 actuals Dec $12,093 + Jan $13,270 + Feb $8,144 = $33,507 already in SAP (sunk cost). 2026 forecast = $0. | Acting PM prior to Jay. 2025 actuals: Dec $12,093 + Jan $13,270 + Feb $8,144 = $33,507 confirmed
Jay Gunaratne | $145/hr | PM rate per Hermitage PO 7000002000. Full-time through project completion

## Phase 2 Monthly Forecast
PRJ13797 — JMUX REPLACEMENT ¦ PHASE 2 MONTHLY PLAN & FORECAST ¦ May–Dec 2026
Construction Start: Aug 5 2026 ¦ Deployment Complete: Sep 28 2026 ¦ Final IFR: Jun 29 2026 ¦ Final IFC: Jul 13 2026 ¦ 36 Sites ¦ As of May 18 2026 ¦ Source: Chad's workbook + B&M SOW + Vic call
▶ SECTION 1 — PHASE 2 MILESTONE SCHEDULE BY MONTH
# | Workstream | Milestone / Deliverable | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Target Date | Notes / Owner
E1 | Engineering | Complete remaining Phase 2 IFRs (15 of 36 still outstanding) | [8 empty] | Jun 29 2026 | ~20 IFRs still to submit. Baldwin (4M/4M1) OVERDUE. Lindenhurst OVERDUE. B&M (Ethan Koch) responsible. $601,020 fixed fee. | bar: May to Dec
E2 | Engineering | Complete all Phase 2 IFCs (PE-sealed) (23 of 36 still outstanding) | [8 empty] | Jul 13 2026 | IFC follows IFR by ~2 weeks per site. All 36 must be sealed by Jul 13 to enable Aug 5 construction start. $214,668 fixed fee. | bar: May to Dec
E3 | Engineering | B&M Phase 2 Site Surveys complete (Hawkeye pre-construction survey) | [8 empty] | Jun 2026 | Vinny (Hawkeye) started May 18. Surveys run parallel with IFCs. Cable lengths, power, rack space per IFC. Hawkeye SOW M1 = $100,170. | bar: May to Dec
E4 | Engineering | Phase 3 MPLS Design (accelerated into Ph2) B&M — 31 Phase 3 sites | [8 empty] | Sep 2026 | Pulled from Phase 3 into Phase 2 as part of PCR recovery. Recovers 5-month schedule impact. Part of $800K PCR request. | bar: May to Dec
E5 | Engineering | Phase 3 Site Surveys (accelerated into Ph2) Hawkeye — 31 sites | [8 empty] | Aug 2026 | 31 Phase 3 sites surveyed now instead of 2027. Part of $800K PCR request. Rate TBD with Hawkeye. | bar: May to Dec
P1 | Procurement | Confirm Phase 2 equipment BOM (CWDM cards, Eltek PSUs — Presidio) | [8 empty] | May/Jun 2026 | Nokia Phase 2 equipment delivered ($733,293). Remaining: ~8-10 CWDM cards ($15K) + Eltek PSUs ($10K). Confirm count with Ethan once IFCs reviewed. | bar: May to Dec
P2 | Procurement | Iniven RC-30 delivery — PAR (6 sites) (8-week lead time from PO date) | [8 empty] | ~Jun 2026 | PO placed. 8-week lead time. Delivery ~Jun 2026. Drives Steven Bradley/relay team installation schedule. | bar: May to Dec
P3 | Procurement | Order RJ45→DB25 patch panel cables (7 production + 1 spare = 8 units) | [8 empty] | May 2026 | Can only order AFTER Hicksville serial test confirms pinout. Cables Unlimited supplier. Transmit/receive crossover confirmed. | bar: May to Dec
H1 | Construction | Hawkeye Staging & Assembly 36 Phase 2 Nokia nodes — lab burn-in & test | [8 empty] | Jun–Aug 2026 | Hawkeye SOW M-Ph0 = $100,170. B&M provides card slotting + connectivity reqs. All 36 nodes assembled and tested before shipping to substations. | bar: May to Dec
H2 | Construction | Hawkeye Installation — All 36 Phase 2 Sites Nokia SAR-8, CWDM, Eltek, RS-232 panel, fiber | [8 empty] | Aug 5 – Sep 28 2026 | Hawkeye SOW M2 = $80,136. 3 mobilisations per site. Construction START Aug 5 2026. TARGET COMPLETE Sep 28 2026. | bar: May to Dec
N1 | NMS / NSP | Remote Node Verification — all 31 Ph1 sites (NSP GUI login, configs, connectivity) | [8 empty] | OVERDUE — was May 9 | OVERDUE. Must complete before production cutover scheduling. Lee/Rahiq/Brianna to action immediately. | bar: May to Dec
N2 | NMS / NSP | Build Phase 2 Nodes into NSP GUI (36 Phase 2 Nokia nodes configured) | [8 empty] | Jul–Aug 2026 | Same process as Phase 1 (31 nodes completed Apr 23). Can start as soon as IFCs finalized — no need to wait for physical installation. | bar: May to Dec
R1 | RTU Migration | Complete Hicksville RTU serial test (RJ45→DB25 beta cable installed) | [8 empty] | OVERDUE — week of May 18 | Beta cable delivered by Cables Unlimited. QAS 6U RTU ready (George). Test MUST complete this week. Blocks all Phase 1 production cutovers. | bar: May to Dec
R2 | RTU Migration | Develop MOP — Production RTU Migration (5K SIOS pilot cutover procedure) | [8 empty] | OVERDUE — was May 16 | Ethan Koch (B&M) to draft. Covers: substation, Hicksville control room, ACC. Change mgmt ticket required. Follow up immediately. | bar: May to Dec
R3 | RTU Migration | Phase 1 Production RTU Cutovers (All Phase 1 JMUX-supported circuits → Nokia) | [8 empty] | Jun 23 2026 | Cannot start until: serial test ✅, MOP approved ✅, node verification ✅. Exception: 5DA Duffy Ave + 5R Bellmore (4W→RS-232 conversion first). | bar: May to Dec
R4 | RTU Migration | Phase 2 RTU Circuit Cutovers (All Phase 2 JMUX circuits → Nokia MPLS) | [8 empty] | Aug–Oct 2026 | After Hawkeye installs each site, relay team migrates circuits. Runs parallel to Phase 2 construction. Cannot retire JMUX until ALL phases done. | bar: May to Dec
A1 | PAR | PAR Engineering Design — Chok team 6 sites: Northport, 5HK, Melville, 7Z, 2H, 2R | [8 empty] | Jun–Aug 2026 | ⚠ URGENT: Chok has not confirmed design status. Meeting this week. $240K confirmed (200hrs×6×$200/hr). Runs PARALLEL with Ph2 — no schedule impact. | bar: May to Dec
A2 | PAR | PAR Installation — Relay team (Steven/Johnny) 6 sites — install + test Iniven RC-30 | [8 empty] | Aug–Oct 2026 | Cannot start until: Chok design done ✅ + RC-30 delivered ✅ (~Jun). $259,500 (1,298hrs×$200/hr) + $30K materials. Call Steven before Monday. | bar: May to Dec
W1 | Network | Two-Way Radio Pilot (Phase 1) Hicksville HE + Melville HE + Syosset pilot | [8 empty] | Jun 23 2026 | Phase 1 pilot only. Remaining sites Phase 2/3. Headend configuration at Hicksville + Melville required first. | bar: May to Dec
W2 | Network | FEMA-DA Pilot (Phase 1) Hicksville HE + Melville HE + Syosset pilot | [8 empty] | Jun 23 2026 | 1 pilot site in Phase 1. Rest Phase 2/3. | bar: May to Dec
W3 | Network | Substation Security Pilot (Phase 1) Hicksville HE + Melville HE + Ruland Road | [8 empty] | Jun 23 2026 | 1 pilot site (Ruland Road) in Phase 1. Rest Phase 2/3. | bar: May to Dec
W4 | Network | Phase 2 Network Pilots — scale out (Two-Way Radio, FEMA-DA, Sub Security) | [8 empty] | Sep–Oct 2026 | After Phase 1 pilots confirm template. Phase 2 rolls out at scale across 36 sites. | bar: May to Dec
G1 | Go-Live | Phase 2 Go-Live Sign-Off (Hawkeye M4) 36 sites installed + relay migration complete | [8 empty] | Sep–Oct 2026 | Hawkeye SOW M4 = $80,136. Formal sign-off by Vic/PSEG. After sign-off: Hawkeye invoices M4, B&M invoices final construction support. | bar: May to Dec
G2 | Go-Live | Nokia runs in PARALLEL with JMUX ★ ALL circuits verified before any decommission | [8 empty] | Aug–Dec 2026 | KEY PRINCIPLE: Nokia and JMUX run simultaneously. All circuits confirmed working on Nokia before JMUX is powered down. Decommission = Phase 3 only. | bar: May to Dec
LEGEND: ✅ Complete ¦ 🔄 In Progress / Active this month ¦ 📅 Due / Deliverable ¦ 🔴 OVERDUE / At Risk ¦ ⬜ Not yet started
▶ SECTION 2 — MONTHLY COST FORECAST ¦ Phase 2 Remaining 2026 ¦ Source: Chad's Workbook + SOW Milestones
# | Vendor / Category | Line Item | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2026 TOTAL | Notes
★ ACTUALS JAN–APR 2026 (already spent): Jan $575,203 ¦ Feb $275,852 ¦ Mar $919,089 ¦ Apr $295,000 ¦ TOTAL SPENT JAN–APR: $2,065,144 (Source: Chad workbook Monthly Summary)
1 | B&M | IFR Submissions — remaining sites (~20 sites × $16,695/site rolling) | 148938 | 89445 | — | — | — | — | 42912 | — | 281295 | From Chad workbook actuals column — B&M SOW M4 rolling IFR payments. May = $148,938 (actuals). Jun = $89,445. Nov = $42,912 (As-Builts deferred Ph3).
2 | B&M | IFC Submissions — remaining sites (included in M4 SOW milestone per site) | — | 50000 | 50000 | — | — | — | — | — | 100000 | IFC payments ~$5,963/site. Rolling Jun–Jul. Included in $214,668 M4 total. Final IFC deadline Jul 13 2026.
3 | B&M | Phase 2 Construction Support Coordinator Ethan Koch — on-site Aug–Dec | — | — | — | 61350 | 61350 | 61350 | 61350 | 61350 | 306750 | B&M SOW M2-Ph2 = $382,824 total (~$61,350/mo × 6 months Aug–Jan 2027). Invoiced monthly. On-site daily field coordination.
4 | B&M | PM Service — Alex Lennox $5,500/mo Jul–Dec 2026 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 44000 | From Chad workbook: $5,500/mo actuals. Jan–Apr already paid ($22,000).
5 | B&M | Phase 3 Site Surveys (accelerated — PCR) 31 sites — pulled into Phase 2 | — | 43000 | 43000 | — | — | — | — | — | 86000 | Part of $800K PCR request. ~$2,774/site × 31 = ~$86K. Pending PCR approval. Accelerated from Phase 3 to recover schedule.
6 | B&M | Phase 3 MPLS Design (accelerated — PCR) 31 sites pulled into Phase 2 | — | — | 120000 | 120000 | 120000 | — | — | — | 360000 | Part of $800K PCR request. ~$360K for 31-site design + Phase 3 detail engineering. Pending PCR approval.
7 | Hawkeye | Phase 2 Site Surveys (M1) Vinny — pre-construction on-site | 50085 | 50085 | — | — | — | — | — | — | 100170 | Hawkeye SOW M1 = $100,170. Started May 18. Running parallel with IFC completion. 50% May, 50% Jun.
8 | Hawkeye | Phase 2 Staging & Assembly (M-Ph0) 36 Nokia nodes — lab burn-in | — | — | 50085 | 50085 | — | — | — | — | 100170 | Hawkeye SOW M-Ph0 = $100,170. B&M provides card slotting requirements. Lab assembly Jul–Aug before shipping to substations.
9 | Hawkeye | Phase 2 Installation — 36 sites (M2) Nokia SAR-8, CWDM, Eltek, fiber, patch | — | — | — | 40068 | 40068 | — | — | — | 80136 | Hawkeye SOW M2 = $80,136. Construction Aug 5 – Sep 28. 3 mobilisations/site. Energise, basic test, notify relay team.
10 | Hawkeye | Phase 2 Go-Live Sign-Off (M4) All 36 sites complete + relay migration done | — | — | — | — | 40068 | 40068 | — | — | 80136 | Hawkeye SOW M4 = $80,136. Sep–Oct 2026 target. Formal PSEG sign-off required before Hawkeye can invoice.
11 | Presidio / Nokia | CWDM Cards + Eltek PSUs ~8-10 cards + accessories | — | 25000 | — | — | — | — | — | — | 25000 | Graybar closed — sourcing via Presidio. ~$1,500-2,000/card. BOM to be confirmed with Ethan once first IFC packages reviewed.
12 | External Relay Team | PAR Engineering Design — 6 sites 200hrs × 6 × $200/hr = $240K | 40000 | 80000 | 80000 | 40000 | — | — | — | — | 240000 | CONFIRMED Vic May 18. External protection engineering team @ $200/hr. Runs parallel with Phase 2 — NO schedule impact. Chok meeting needed URGENTLY to confirm monthly spread.
13 | External Relay Team | PAR Installation + Cutover — 6 sites ~1,298hrs × $200/hr = $259,500 | — | — | — | 64875 | 64875 | 64875 | 64875 | — | 259500 | CONFIRMED Vic May 18. Cannot start until: Chok design done + RC-30 delivered. Steven Bradley call before Monday to confirm hours by month.
14 | Procurement | PAR Materials Cables, connectors — 6 sites | — | — | 30000 | — | — | — | — | — | 30000 | CONFIRMED Vic May 18. $30K for cables and connectors across all 6 PAR sites.
15 | PSEG Internal | Internal Labor — all named resources (Jay, Rahiq, Brianna, Chok, Lok, Sameer, et al.) | 14684 | 14684 | 14684 | 14684 | 14684 | 14684 | 14684 | 14684 | 117472 | From Chad workbook Monthly Summary: $13,537/mo forecast for labor. Rounded up to $14,684 to include fringe. Martin Gately = $0 (departed).
16 | PSEG / ComTec | Assessments, PQA, Controller, Scheduler (Chad, Umair, Marge, PQA audit) | 6067 | 7567 | 5307 | 4567 | 4567 | 4567 | 4267 | 5067 | 41976 | From Chad workbook Monthly Summary. Includes ComTec (Chad $8,400/mo, Umair $5,416/mo), PQA audit, assessments.
17 | Cognizant | Lee Blackman — Sr. Network Architect $7,200/mo | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 57600 | Cognizant outside services. $7,200/month through Phase 2 completion. PO 7000002490.
| MONTHLY FORECAST TOTAL (Phase 2 remaining 2026) |  | 272474 | 372481 | 405776 | 408329 | 358312 | 198244 | 200788 | 93801 | 2310205 | ⚠ PCR items (Ph3 accel $363K + PAR $334,500) pending approval. Frame relay internal labor not yet included — Steven call needed.
| CUMULATIVE 2026 SPEND (Jan–Apr actuals + May–Dec forecast) |  | 2337618 | 2710099 | 3115875 | 3524204 | 3882516 | 4080760 | 4281548 | 4375349 | 4375349 | CP Budget 2026: $2,600,000 ¦ Projected EAC: $4,375,349 ¦ Variance: $-1,775,349 (OVER budget)
▶ SECTION 3 — PCR REQUEST SUMMARY (Two-Part — Submission Target: May/Jun 2026)
PCR # | Category | Basis | May: Amount; Jun: Year |  | Notes
PCR 1 | PAR — Engineering |  | May: 200 hrs × 6 sites × $200/hr; Jun: $240,000; Jul: 2026; Aug: External relay/protection engineers. Runs PARALLEL with Phase 2. No schedule impact.
PCR 1 | PAR — Installation |  | May: ~1,298 hrs × $200/hr; Jun: $259,500; Jul: 2026; Aug: External relay team. Starts after RC-30 delivery (~Jun) and Chok design complete.
PCR 1 | PAR — Materials |  | May: Cables, connectors (6 sites); Jun: $30,000; Jul: 2026; Aug: Confirmed by Vic May 18 2026 call.
PCR 1 | PAR TOTAL |  | Jun: $529,500; Jul: 2026; Aug: CONFIRMED total per Vic/Jay May 18 call.
PCR 2 | Ph3 Site Surveys (accelerated) |  | May: 31 sites × ~$2,774/site; Jun: ~$86,000; Jul: 2026; Aug: Pulled from Phase 3 into Phase 2. Recovers 5-month schedule impact from PAR discovery.
PCR 2 | Ph3 MPLS Design (accelerated) |  | May: 31 sites — B&M detail design; Jun: ~$714,000; Jul: 2026; Aug: B&M Phase 3 design pulled into Phase 2. Enables project completion Nov 2027 vs May 2028.
PCR 2 | Ph3 ACCELERATED TOTAL |  | Jun: ~$800,000; Jul: 2026; Aug: Pending PCR approval. Brings Phase 3 work forward to prevent 5-month slip.
TOTAL | COMBINED PCR REQUEST |  | May: PAR $530K + Ph3 Accel $800K; Jun: ~$1.33M; Jul: 2026; Aug: Vic confirmed range $1.2–1.33M. Submit as two separate PCRs but present together to CIO.