## Slide 1: PRJ13797: JMUX Replacement Update Project Manager : Dhananjaya Gunaratne
March 2026

## Slide 2
Goals & Objectives
JMUX Replacement: Private Field Area Network
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Modernize PSEG LI's substation communications by replacing legacy JMUX with MPLS nodes to deliver a reliable, scalable, and future-ready network.
🔧 Engineering Services
✅
Detailed site surveys at all substations
✅
Rack elevations, power design & supplemental docs
✅
✅
All substations aligned to PSEG LI standards
Phase 2 surveys: Completed during Phase 1
Phase 2 IFRs: Being issued by BMcD
Phase 2 IFCs: In progress
📦 Procurement & Staging
✅
All Phase 1 equipment purchased by PSEG LI
✅
✅
Phase 1 staging completed: Sept 29, 2025
✅
Nokia Phase 2 equipment delivered: Feb 19, 2026
Equipment safely stored at Hawkeye warehouse
🏗 Construction & Installation
✅
BMcD on-site coordination throughout Phase 1
✅
✅
31/31 Phase 1 sites installed & commissioned
SSP documentation: Submitted & approved
Remote connectivity to nodes: In progress
✅
PROGRAM SCOPE SUMMARY
Total Substations
MPLS Sites
DF RTU Sites
Radio Shelter Sites
Nokia MPLS Nodes
✅ Phase 1
49
26
17
6
31
Phase 2
45
26
12
7
26
Phase 3
35
22
7
6
22
TOTAL
129
74
36
19
79
OTDR testing from Hicksville to Syosset
🟡
🟡
🟡
🟡

## Slide 3
Phase 1 Accomplishments
31 Substations | Complete
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
KEY ACCOMPLISHMENTS
Staging completed at Hawkeye Warehouse - Work Completed - 9/29/2025
Nokia equipment for Phase 2 has been delivered – Work Completed - 2/19/2026
Complete CWDM cutover at Hicksville and ACC - Work completed
Install routers in the primary & secondary cabinet – Work Completed
NSP installed racked & powered up in Melville and Hicksville – Work Completed
Staging CMDB document updated and added to CMDB database – Work Completed
OTDR testing from Hicksville to Syosset – Work Completed
PHASE 1 AT A GLANCE - Completion
31 / 31
Sites Complete
~65%
Phase 1 Complete
2
Network Ring - 1 & 6
Deployment & Cutover
non-tie and tie sites
Jan 2026
Final Phase 1 Cutover
$4.44M
Spent to Date
✅
✅
✅
✅
✅
✅
✅
✅
✅
Wave 1 – non-tie sites – Ring 6
Wave 2 – non-tie sites – Ring 1
PHASE 1 — MICRO-PHASE BREAKDOWN | Vik Vohra directive · Mar 16, 2026
# | MICRO-PHASE | STATUS | WHAT VIK SAID · DETAIL | OWNER / DUE
1 | Engineering & Design | ✅ 100% | "Engineering 100% done" — Vik confirmed. Site surveys, IFRs, IFCs, HLD all complete for 31 sites. | B&M ✅ Complete
2 | Procurement & Staging | ✅ 100% | Equipment purchased, staged & tested (9/29/25). Ph2 Nokia equip delivered 2/19/26. Identify Phase 1 leftover equipment with Vinnie before Ph2 procurement. | PSEG LI / Hawkeye ✅
3 | Construction & Installation | ✅ 100% | 31/31 sites installed. CWDM cutovers Oct–Jan. Cat6 done 3/4. "What's done is done — don't report on it." BGP design approved today 3/16 ✅ | Hawkeye ✅ Complete
4 | Deployment / Pre-Cutover | 🔴 ~5% | "Deployment only 5% done." BGP ✅ approved 3/16. BLOCKED on NSP software install — Nokia critical path. Connectivity to production apps not yet established. Target: Jun 2026. | Nokia → Lee B. 🔴 Jun 2026
5 | Application Layer 3 Cutover | 🔴 0% | 5 apps: 2-way radio, DA radio, dSCADA, MicroPAQ, Security. "Accelerate app cutover PREP into Phase 2." Production traffic migration stays Phase 3. Pilot: Syosset first. | B&M + App Owners 🔴
6 | RTU / Layer 2 Cutover | 🔴 0% | On-site only — physical cable migration. "RTU and security/radio aspects are part of Phase 1, not separate phases." ~32 days effort. Sequential: must follow Layer 3. | PSEG LI Relay 🔴
7 | As-Builts & Decommission | ⏳ 2027 | "Funding for app transitioning and decommissioning is in 2027." Exclude as-built dates from weekly report — too many changes. JMUX Ring 1 decommission = post-Phase 3. | B&M / Hawkeye ⏳ 2027
 | PHASE 1 OVERALL | 🟡 ~65% | "Phase One needs to be broken into micro-phases. The entire phase is not complete." — Vik Vohra · Mar 16, 2026 ¦ Target: June 2026 ¦ Critical path: NSP (Nokia) | PM: Jaya · SPI: 0.76

## Slide 4
Phase 2 Status
34 Sites | Engineering Design Underway | Burns & McDonnell SOW: $1.37M
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Site Surveys
COMPLETE
Nokia Equip. Delivery
COMPLETE
IFR Design (B&McD)
IN PROGRESS
IFC Design
IN PROGRESS
Construction
NOT STARTED
Cutover
NOT STARTED
Milestone
Contract Date
Status
Notes
Substation Site Surveys (Phase 2)
2/27/2026
✅ Complete
Completed during Phase 1 — ahead of schedule
MPLS Network Node Design — IFR
Wave 1: 2/23/26
🟡 In Progress
Wave 1 (3 sites) ✅ Approved & IFC uploaded. Wave 2 in progress.
MPLS Network Node Design — IFC
Wave 1: 3/23/26
Wave 1 IFC COMPLETE ✅ — Far Rockaway, Valley Stream, Cedarhurst uploaded to shared drive
Construction & Installation
Aug–Dec 2026
⏳ Not Started
Pending IFC completion
Nokia equipment for Phase 2 has been delivered – Work Completed - 2/19/2026
2/19/2026
✅ Complete
🟡 In Progress

## Slide 5
Schedule Status
Overall: 🟡 Yellow | Recovery Plan in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Root Causes:
• SSP documentation delays (security review queue)
• CMDB update coordination time
• Inclement weather affecting field work
• Crown Castle fiber issue at Hicksville (OTDR testing pending)
Recovery Actions:
ILO config (Bill/Rahiq — #1 BLOCKER) → BGP config Hicksville & Melville (Lee) → Remote access config 31 routers → App cutovers → RTU cutovers → Phase 1 close Jun 2026
SPI = 0.76 (Yellow). ILO config is #1 critical path blocker — Bill (B&M) working with Rahiq to resolve console cable & firmware. Northport DC power RESOLVED ✅. Phase 1 construction 100% done; deployment micro-phase ~5%. June 2026 revised target.
Phase 2 IFR/IFC design on track.
PROGRAM TIMELINE
Apr 2024 — Project Start
Oct 2024 — RFP Award & SOW Executed
Jan 2025 — Phase 1 Detailed Design Start
Sep 2025 — Staging Complete (Hawkeye)
Oct 2025 — Phase 1 Construction Start
Dec 2025 – Jan 2026 — Wave 1 & 2 Cutovers Complete
Feb 2026 — Nokia Phase 2 Equipment Delivered
Mar 2026 — Phase 2 IFR Design in Progress ◀ NOW
Mar–Jul 2026 — Phase 2 IFC Design & Review
Aug–Dec 2026 — Phase 2 Construction
Jul 2027 — Program Completion (Target)
SCHEDULE PERFORMANCE INDEX (SPI)
0.00
0.50
0.75
1.00
1.25
1.50
2.00
●
Below 0.70 — Critical
●
0.70–0.90 — Yellow
●
0.90–1.10 — On Track
●
Above 1.10 — Ahead
--- February 2026 : 0.75 (Orange)
╌╌ January 2026 : 1.00 (Gray)
--- March 2026 : 0.76 (Yellow ↓)
✅
✅
✅
✅
✅
✅
✅

## Slide 6
Phase-1
Engineering Services
Procurement and Staging
  Staging completed at Hawkeye Warehouse - Work Completed - 9/29/2025
  Nokia equipment for Phase 2 has been delivered – Work Completed - 2/19/2026
Construction and Installation Support
  Installing equipment at substations. – 31/31 sites completed
  ACC cabling and fiber panel installed – 1/7/26
  Throwover from Hicksville to ACC will happen - 1/13/2026
    J-mux eqpt. Will be moved on the primary & secondary cabinet to
    make room for the MPLS routers. – 1/13/26 - Work Completed
    Complete CWDM cutover at Hicksville and ACC - Work completed
    Install routers in the primary & secondary cabinet – Work Completed
    NSP installed racked & powered up in Melville and Hicksville – Work Completed
    CMDB document updated and added to CMDB database – Work Completed
    Cat 6 cables needs to be run to NSP in Hicksville – Work Completed
    OTDR testing from Hicksville to Syosset – Work Completed
Deployment & Cutover
  Cutover of CWDM started at Bagatelle, Melville, Pilgrim -11/19- 11/20/2025 – we ran into fiber panel issues. - Work Completed
  Wave 1 - 12/8/2025 – 12/18/2025 (non-tie sites) – Decided to start with the no tie sites. – Work Completed
  WAVE 2 - 01/06/2026 – 1/08/2026 (tie-in-sites) – with experience cutting over the tie sites, we felt comfortable to complete the tie sites. – Work Completed
.
Burns & Mac - Phase 1 | Total | Completed
IFR - Issued for review design | 31 | 31
IFC - Issued for construction | 31 | 31
Highlight Project Accomplishments
Total Phase 1 scope | 
Initiation & Planning | 100%
Site Surveys | 100%
Test Plan | 100%
HLD | 100%
IFR/IFC | 100%
Procurement | 100%
Staging | 100%
Field Installation | 100%
Deployment - CWDM | 100%
Pre-Deployment Deployment - Security & Radio | 5%
Deployment - Relay/RTU Cutover | not started
⚠ Vik (Mar 16): "Sub-phases of Phase 1 aren't being documented and separated — leading to inaccurate reporting. Phase 1 has several micro-phases. Even though we've completed some, the entire phase is NOT complete. People don't come back and say '31 is all done — everything about 31 is done.' It's not that kind of project."

## Slide 7
Phase 1 – Layer 1-3 configuration – Next steps
Mobilization | Description | Responsible Stakeholder | Present On Site | Estimated Duration/Site
Initial Installation | • Install power feeds - Completed • Power MPLS router - Completed • Install new communication cables - Completed | Hawkeye | Hawkeye, BMcD, PSEGLI | 5 days
Fiber Integration | • JMUX OC-48 Circuits & Nokia MPLS over CWDM filters - Completed • Establish new MPLS parallel links - Completed • Establish Nokia parallel network & connectivity - Completed | PSEGLI | BMcD, PSEGLI | 1 Week
Layer 3 Connect | • Establish Ethernet circuits with Nokia MPLS in paralled with JMUX where possible • Security • FEMA DA • Two-way Radio • DSCADA • MicroPAQ | BMcD, PSEGLI | BMcD | 5 days
Layer 1 | • Cutover of relay and RTU circuits from JMUX to MPLS • Cutover any other circuits (PAR, DRD, etc.) as possble • Only RTUs/Circuits with no dependency on other JMUX rings | PSEGLI (Relay) | BMcD, PSEGLI | 5 days

## Slide 8: JMUX Replacement
Progress Current Period (past 2 weeks)- Milestones/Key Deliverables with Dates
CAT6 cable run completed by Hawkeye 03/04/2026
OTDR testing completed from Hicksville to Syosset , found bad filter 03/09/2026
First batch of IFR(3) have been converted to IFC and uploaded to shared drive 03/09/2026
 | Status* | Trends*
Schedule Health | Yellow | 
Financial Health | Green | 
Scope Health | Green | 
Risk Health | Green | 
Resource Health | Green | 
Status Date: 03/13/2026
IT/Cyber: IT
Director: Irving Landesbaum
GPM: Vikas Vohra
Program Manager Jay Gunaratne
Time Management
Proj Plan (Baseline) Start 03-01-2024
Proj Actual Start 04-18-2024
Go-Live/In Service/Next Sprint Release 01-01-2024
Proj Plan (Baseline) End 04-08-2027
Proj Actual Target End 07-08-2027
Project Financials / Budget
WBS Code: I.39424.1.x
LIPA approved total project budget: $6,600,000.00
URB approved funding to date: $6,600,000.00
Spend to date: $4,437,070.00
Estimate to complete: $2,162,930.00
Estimate at completion: $6,600,000.00
Over (+) / Under (-) LIPA approved budget: +/- $00.00
Benefit
Due to GE announcing End of Life for the GE Jungle Mux system as of EOY 2025, the benefits for project is to allow the Systems Integrator to select the most appropriate ‘Equipment Vendor’ via the RFP process to replace the GE JMUX equipment.
Scope (65%-Complete)
The purpose of this project is to install new Multiprotocol Label Switching (MPLS) nodes, remove existing GE Jungle MUX (JMUX) equipment, and design new circuits from the existing substation .
Major Steps (next 2 weeks): Milestones/Key Deliverables with Dates
✅ BGP design APPROVED Mar 16, 2026 — Lee Blackman to begin change documentation for Melville & Hicksville Nokia integration.
Receiving new set of IFRs on 03/13 03/13/2026
Fiber termination to the NSP will be completed by 3/13 by Hawkeye. 03/13/2026
🔴 ILO configuration — Bill (B&M) coordinating with Rahiq. Console cable & firmware issue identified. CRITICAL PATH BLOCKER #1. 🔴 BGP config at Hicksville & Melville (Lee) — pending ILO completion. 🔴 Remote access config — 31 routers pending BGP completion.
corporate directly into the managed servers) 03/16/2026
Risk Management- Top 3 (in descending order of possible impact)
Vendor installation delays – inclement weather
Legacy JMUX equipment old and need to be very careful when doing cutovers.
Other projects and work being done at the substation simultaneously
Issue Management- Top 3 (in descending order of actual impact)
Accelerating phase 2 site surveys by getting them completed in Phase 1.
Working closely with vendors and tracking installation.
Equipment procurement and delays in SCM.
Scope/Change Management (most recent approved)
Adding 7 additional nodes to the original 25 Phase 1 nodes. The additional 7 nodes completes both ring 1 and ring 2 in this Phase 1 effort.
PRJ (ServiceNow): PRJ13797
Repository Link : JMUX Repository
Lifecycle Phase:
Execution
Current Period (past 2 weeks) Status Narrative:
CAT6 cable run completed on 03/04
Fiber termination to the NSP will be completed by 3/13 by Hawkeye.
✅ BGP design approved Mar 16 — Lee Blackman to proceed with Melville & Hicksville change docs. NSP = critical path.
✅ Northport DC power RESOLVED — Relay team ran new feed to fuse, eliminating tripping issue (3/18/2026).
Receiving new set of IFRs on 03/13
Remediation (For Non-Green Statuses)
Schedule : Plan to complete all the remote configuration of the routers and complete testing to bring the schedule back to green
Project Description
The Systems Integrator will create, facilitate, and execute the process for generating an RFP to select an ‘Equipment Vendor’ to replace the existing Private Network vendor – GE Jungle MUX. In parallel, the Systems Integrator will conduct ‘high-level’ design activities for the MPLS Private Network, including site surveys at 88 COMPANY substations to assess specific structural and infrastructure modifications required for the new equipment.
Dependency Management |  | 
Project | Deliverable | Date
NA |  | 
Overall Health This Period Last Period
Version 3.0

## Slide 9
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Survey | IFR | IFC | Construction | Deployment
1 | 7RM Bayport | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
2 | 7R Sayville | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/23/26
3 | 7XM Great River | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
4 | 7XM Great River Radio Shelter | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
5 | 6H Hauppauge | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
6 | 6H Hauppauge Tower | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Mon 9/14/26
7 | 6S Kings Hwy | Complete | Mon 4/27/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
8 | Brentwood DO | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 9/2/26 | Fri 9/25/26
9 | 7H Babylon | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Mon 9/21/26
10 | 7H Babylon Radio Shelter | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/12/26 | Tue 9/22/26
11 | 7D West Babylon | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/12/26 | Mon 9/21/26
12 | 7D West Babylon Radio Shelter | Complete | Mon 5/4/26 | Tue 6/2/26 | Wed 8/19/26 | Mon 9/21/26
13 | 7W Berry St | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/19/26 | Mon 9/23/26
14 | 3J Whiteside | Complete | Mon 4/6/26 | Mon 5/4/26 | Wed 8/12/26 | Mon 9/14/26
15 | 2K Valley Stream | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26

## Slide 10
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
16 | 2RB Green Acres | Complete | Mon 3/9/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
17 | Hewlett DO | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Fri 9/25/26
18 | 2ZB EF Barrett PS Inside | Complete | Mon 3/23/26 | Mon 4/20/26 | Wed 8/5/26 | Mon 9/14/26
19 | 2WB Barrett Outside | Complete | Mon 3/23/26 | Mon 4/6/26 | Wed 8/5/26 | Mon 9/14/26
20 | 5HK Hicksville | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26
21 | 2H Far Rockaway | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
22 | 2KB Cedarhurst | Complete | Tue 2/23/26 | Mon 3/9/26 | Wed 8/5/26 | Mon 9/14/26
23 | 2R Hewlett | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
24 | 2R Hewlett Shelter | Complete | Mon 2/23/26 | Mon 3/23/26 | Wed 8/5/26 | Mon 9/14/26
25 | 4M Baldwin | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
26 | 4M1 Baldwin Shelter | Complete | Mon 4/13/26 | Mon 5/11/26 | Wed 8/12/26 | Mon 9/14/26
27 | 6K State School | Complete | Mon 4/20/26 | Mon 5/18/26 | Wed 8/12/26 | Fri 9/17/26
28 | 7BH Bohemia | Complete | Mon 4/27/26 | Tue 5/26/26 | Wed 8/12/26 | Fri 9/18/26
29 | 7M MacArthur | Complete | Mon 5/18/26 | Tue 6/16/26 | Wed 8/26/26 | Mon 9/22/26

## Slide 11
2025 Phase-1 Substation Schedule 31 Sites (2 of 2)
Phase 2 Site Surveys: ✅ Complete
# | Substation | Site Surveys | IFR | IFC | Construction | Deployment
30 | 8AX Patchogue | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
31 | 8AX Patchogue Shelter | Complete | Tue 6/9/26 | Wed 7/8/26 | Wed 9/2/26 | Fri 9/25/26
32 | 7Z Lindenhurst | Complete | Tue 6/2/26 | Tue 6/30/26 | Wed 9/2/26 | Thu 9/24/26
33 | 7J Sterling | Complete | Mon 5/11/26 | Tue 6/9/26 | Wed 8/26/26 | Mon 9/22/26
34 | 7UM South Farmingdale | Complete | Tue 5/26/26 | Tue 6/23/26 | Wed 8/26/26 | Mon 9/23/26
35 | ACC | Complete | Tue 6/9/26 | Wed 7/8/26 | Tue 9/8/26 | Mon 9/28/26
36 | 6U Ruland | Complete | Tue 6/2/26 | Tue 6/30/26 | Tue 9/8/26 | Mon 9/28/26

## Slide 12
Current Risk
  Legacy JMUX equipment old and delicate. Potential for Outage.
      Ran into faulty connectors that are over25 years old and not readily available with vendors.
      Potential brittle fiber patch panels, Face plates, connectors and cables.
  Weather delay and delay in installing the equipment at sub-station (tracking weekly).
  Other major substation project conflicts.
Next Steps
✅ Cat6 COMPLETE (3/4) · ✅ OTDR COMPLETE (3/9) · ✅ BGP APPROVED (3/16) · ✅ Northport DC RESOLVED (3/18) (change ticket planned 03/03).
🔴 ILO configuration — Bill (B&M) working with Rahiq/Brianna to resolve console cable & firmware. This is the #1 critical path blocker. (planned 03/04) to confirm whether the low DB level is internal vs carrier-side (Crown Castle); validate filter/wavelength behavior.
🔴 BGP config at Hicksville & Melville — Lee to begin once ILO is complete. after cabling/OTDR so we can shift to “remote-first” execution.
🔴 Remote access config — Lee to configure all 31 routers once BGP is done at both hub sites. on the powered routers for Ring 1 and Ring 6 (remote workstream), with standard config + validation.

## Slide 13
Risks & Issues
Active Risks | Mitigations in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
⚠ ACTIVE RISKS
🔧 ACTIVE ISSUES / IN RESOLUTION
HIGH
Legacy Equipment Fragility
JMUX equipment 25+ yrs old. Faulty connectors, brittle fiber panels. Potential for unplanned outage during cutover.
Mitigation: Careful cutover planning; dedicated B&McD on-site support. Phase 1 complete — risk reduced going into Ph2.
MEDIUM
Substation Access Delays
Weather, scheduling conflicts, or escort availability can delay field work.
Mitigation: Verify weekly before mobilizing. Adjust site plan if specific sites inaccessible.
MEDIUM
Phase 2 Schedule Slippage
IFR/IFC design cycle (4-wk IFR + 2-wk review + 2-wk IFC) leaves limited buffer.
Mitigation: Phase 2 surveys done early. B&McD running concurrent site designs. Weekly status calls tracking.
RESOLVED
Crown Castle Fiber Issue (Hicksville)
Low dB levels on fiber — may be Crown Castle's network, not PSEG LI.
RESOLVED ✅ — OTDR confirmed bad filter 03/09/2026. Issue cleared, no Crown Castle escalation needed.
COMPLETE ✅
Cat 6 Cabling — Hicksville NSP
COMPLETE ✅ — Confirmed by Vinny (Hawkeye) 03/13/2026.
COMPLETE ✅
OTDR Testing — Hicksville
COMPLETE ✅ — 03/09/2026. Bad filter identified and resolved. Crown Castle fiber issue cleared.
IN PROGRESS
Remote Access — Phase 2 Nodes
✅ BGP APPROVED 3/16/2026 — Lee Blackman to begin change documentation. 🔴 ILO configuration is NOW the #1 critical path blocker — Rahiq/Brianna missing console cable & firmware. Bill (B&M) stepping in to resolve. ILO → BGP config → Remote access 31 routers → Phase 1 close Jun 2026.
COMPLETE
Phase 2 SSP / Security Reviews
Architecture review, security assessment, compliance readiness all approved 2/10/2026.

## Slide 14
Next Steps & Path to Completion
March 2026 — July 2027
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
IMMEDIATE (Next 30 Days)
Mar 16
✅ BGP design approved 3/16 — Lee Blackman to proceed with Melville & Hicksville change documentation
Mar 16
Mar 2026
ILO config (🔴 BLOCKER — Bill/Rahiq resolving) → BGP config Hicksville & Melville (Lee) → Remote access 31 routers → App cutover PREP → RTU cutovers → Phase 1 close Jun 2026
Mar 2026
Wave 1 IFRs (Far Rockaway, Valley Stream, Cedarhurst) — COMPLETE ✅ Converted to IFC & uploaded to shared drive
Mar 9
Wave 1 IFC approved by PSEG LI ✅ — Wave 2 IFR packages in progress
Mar 23
✅ Wave 1 IFC complete — Far Rockaway, Valley Stream, Cedarhurst approved & uploaded
Ongoing
Weekly status calls with B&McD; monthly schedule updates
PATH TO COMPLETION
Q1 2026
Phase 1 Operational (Jun 2026)* | Phase 2 IFR/IFC design underway
Q2 2026
Phase 2 IFC completion (all 36 sites)
Q2–Q3 2026
Phase 2 construction mobilization
Q3–Q4 2026
Phase 2 installations at all 36 sites
Q4 2026
Phase 2 cutovers — Waves 3 & 4
Q1 2027
As-built documentation complete
Jul 2027
🏁 Program Complete
* Vik Vohra (Mar 16, 2026): "Phase One needs to be broken into micro-phases. Even though we've completed some, the entire phase is not complete." Micro-phase status → Engineering ✅ 100% | Procurement ✅ 100% | Construction ✅ 100% | Deployment 🔴 ~5% | App Cutover 🔴 0% | RTU Cutover 🔴 0% | As-Builts/Decommission ⏳ 2027

## Slide 15
PRJ13797 — JMUX Replacement | Critical Path: Next 10 Steps
As of March 18, 2026 | Phase 1 Close Target: June 2026
01
ILO Console Cable & Firmware Resolution
📅 Mar 19–20, 2026 👤 Bill (B&M) + Rahiq
Bill calls Rahiq to resolve missing console cable & firmware. #1 blocker — unlocks everything downstream.
02
ILO Port Activation & Configuration
📅 Mar 21–24, 2026 👤 Rahiq / Brianna / Bill
Configure ILO management ports at Hicksville & Melville. Change ticket to be opened.
03
Wire Drops to Equipment (Parallel)
📅 Mar 19–21, 2026 👤 Jay + Hawkeye
Walk-through with Hawkeye to complete drops from LGX panels to equipment. SFPs & change order needed for final termination.
04
Nokia Training
📅 Mar 19, 2026 — 3:00 PM 👤 Jay / Rahiq / PSEG LI Team
Glenn (Nokia) + PSEG LI technical team. Confirmed on calendar.
05
Phase 2 BOM & Inventory Reconciliation
📅 Week of Mar 23, 2026 👤 Jay + Vinny
Visit Hawkeye trailer — inventory Phase 2 Nokia equipment vs BOM. Identify supply chain gaps before ordering.
06
BGP Configuration — Hicksville & Melville
📅 Mar 24–28, 2026 👤 Lee Blackman
BGP config at both hub sites after ILO complete. Change documentation submitted. Remote access into routers.
07
IFR Submissions — Green Acres & Berry Street
📅 Mar 30, 2026 👤 BMcD (Ethan Koch)
BMcD submits IFR packages for 2RB Green Acres and 7W Berry Street. Currently on track.
08
Remote Access Config — All 31 Routers
📅 Apr 1–18, 2026 👤 Lee Blackman
Lee configures all 31 routers remotely once Hicksville & Melville BGP is validated.
09
NSP Software Install & Layer 3 Services
📅 Mid–Late Apr 2026 👤 Nokia / Lee
Nokia activates NSP and Layer 3. Start Hicksville & Melville, then site by site. 2 SFPs needed at Melville.
10
Application & RTU Cutovers Begin
📅 May 2026 👤 PSEG LI / BMcD / Hawkeye
First wave of app cutovers at lead sites. RTU cutovers follow. Phase 1 close target: June 2026.
🔴 Critical 🟠 In Progress / Parallel 🟡 Pending Prior Step 🟢 On Track 🔵 Future Phase
PRJ13797 | Confidential | Mar 18, 2026