## JMUX URB Request
PRJ13797 — JMUX REPLACEMENT ¦ URB FUNDING REQUEST ¦ 98 Sites: Ph1=31 ✅ Ph2=36 🔵 Ph3=31 ⭕
PURPOSE: Show total project cost by phase → approved budget → scope offsets → net new funding needed = $1,400,000
# | CATEGORY | LINE ITEM | VENDOR | STATUS | PHASE 1 31 Sites ✅ | PHASE 2 36 Sites 🔵 | PHASE 3 31 Sites ⭕ | TOTAL
A ─ FULL PROJECT COST BREAKDOWN BY PHASE (before adjustments)
1 | Equipment | Nokia SAR-8 Routers + SFPs + Licenses | Nokia / Presidio | Ph1 ✅ Actual | 1412400 | 733293 | 1412400 | 3558093
2 | Equipment | Cables, Connectors, Fiber Jumpers | Graybar(Ph1)/TBD | Ph1 ✅ Actual | 241073 | 279956 | 241073 | 762102
3 | Engineering | B&M IFR Design ($16,695/site) | Burns & McDonnell | Ph1✅ Ph2🔵 Ph3⭕ | 517545 | 601020 | 517545 | 1636110
4 | Engineering | B&M IFC Design ($5,963/site) | Burns & McDonnell | Ph1✅ Ph2🔵 Ph3⭕ | 184853 | 214668 | 184853 | 584374
5 | Engineering | B&M As-Built Drawings ($1,192/site) → ALL to Ph3 | Burns & McDonnell | All phases → Ph3 ⭕ | 36952 | 42912 | 36952 | 116816
6 | Engineering | B&M Site Surveys (Ph3 surveys pulled into Ph2) | Burns & McDonnell | Ph1✅ Ph2✅ Ph3→Ph2 | 99800 | 86040 | 0 | 185840
7 | Engineering | B&M Staging Support | Burns & McDonnell | Ph1✅ Ph2🔵 Ph3⭕ | 57300 | 57300 | 57300 | 171900
8 | Engineering | B&M Construction Support Coordinator | Burns & McDonnell | Ph1✅ Ph2🔵 Ph3⭕ | 368100 | 368100 | 245400 | 981600
9 | Engineering | B&M Project Management ($5,500/mo) | Burns & McDonnell | Ongoing | 66000 | 44000 | 22000 | 132000
10 | Installation | Hawkeye Pre-Construction Survey | Elecnor Hawkeye | Ph1✅ Ph2🔵 Ph3⭕ | 0 | 100170 | 100170 | 200340
11 | Installation | Hawkeye Staging (rack, burn-in, test) | Elecnor Hawkeye | Ph1✅ Ph2🔵 Ph3⭕ | 100170 | 100170 | 100170 | 300510
12 | Installation | Hawkeye Substation Installation (3 visits/site) | Elecnor Hawkeye | Ph1✅ Ph2🔵 Ph3⭕ | 302623 | 80136 | 402793 | 785552
13 | Installation | Hawkeye Go-Live Sign-Off | Elecnor Hawkeye | Ph2🔵 Ph3⭕ | 0 | 80136 | 100000 | 180136
14 | Installation | Hawkeye Decommissioning (ALL phases → Ph3) | Elecnor Hawkeye | All phases → Ph3 ⭕ | 0 | 0 | 141351 | 141351
15 | PM/Controls | PM + Controls + Scheduler | Hermitage / ComTec | Ongoing | 121360 | 649459 | 116600 | 887419
16 | Int. Labor | PSEG Internal + Cognizant (Lee Blackman) | PSEG / Cognizant | Ongoing | 82421 | 436389 | 90000 | 608810
17 | PQA/NERC | PQA, Assessments, Cyber Security | EPMO/TRC/PSEG | Ongoing | 79228 | 142737 | 35000 | 256965
TOTAL PROJECT EAC — ALL PHASES (A) |  |  |  |  | 3669825 | 4016486 | 3803607 | 11489918
B ─ APPROVED BUDGET (already authorized — no new ask here)
2024 Actuals — already spent (sunk cost) |  |  |  |  | 741206 | — | — | 741206
2025 Approved Capital Budget |  |  |  |  | 3250000 | — | — | 3250000
2026 Approved Capital Budget |  |  |  |  | — | 2600000 | — | 2600000
TOTAL APPROVED BUDGET (B) |  |  |  |  | 3991206 | 2600000 | 0 | 6591206
C ─ SCOPE OFFSETS (budget repositioned between phases — nets to $0, no new money)
Ph1 As-Built Drawings → deferred to Phase 3 |  |  | Already in budget, just shifts to 2027 |  | ($36,952) | — | +$36,952 | —
Ph2 As-Built Drawings → deferred to Phase 3 |  |  | Already in budget, just shifts to 2027 |  | — | ($42,912) | +$42,912 | —
Ph3 Site Surveys → accelerated into Phase 2 window |  |  | Pulled forward, same cost, no increase |  | — | +$86,000 | ($86,000) | —
NET OFFSET (C) — offsets cancel = $0 net new cost |  |  |  |  | — | — | — | $0
D ─ NEW SCOPE ★ PCR REQUIRED — This is the $1.4M ask
# | PCR ITEM | DESCRIPTION | VENDOR | STATUS | PHASE 1 | PHASE 2 | PHASE 3 | TOTAL
D1 | PAR Equipment | Iniven RC-30 ×6 units ($8,750/ea) 6 PAR sites: Northport, 5HK, Melville, 7Z, 2H, 2R | Nokia/Presidio | PO confirmed ✅ | — | 52500 | — | 52500
D2 | PAR Engineering | Relay Eng Design — 200hrs × 6 sites × $200/hr | Chak's Team | Verbal confirmed | — | 240000 | — | 240000
D3 | PAR Installation | Relay Install + Configure + Cutover ~1,298 hrs × $200/hr | Steven Bradley | Verbal confirmed | — | 259500 | — | 259500
D4 | PAR Materials | Custom cables, C37.94 connectors, rack hardware | Various | Verbal confirmed | — | 30000 | — | 30000
D5 | Ph3 Acceleration | Ph3 IFR+IFC design (31 sites) pulled into Ph2 window Avoids 5-month schedule slip | Burns & McDonnell | PCR pending | — | 800000 | — | 800000
★ PCR TOTAL (D) = PAR $582,000 + Phase 3 Acceleration $800,000 |  |  |  |  | 0 | 1382000 | 0 | 1382000
E ─ URB FUNDING SUMMARY
Total Project EAC — All 3 Phases (A) |  |  |  |  | 3669825 | 4016486 | 3803607 | 11489918
Approved Budget Already Authorized (B) |  |  |  |  | -3991206 | -2600000 | $0 | -6591206
Scope Offsets — net zero, just repositioned (C) |  |  |  |  | $0 | $0 | $0 | $0
New Scope / PCR Items (D) |  |  |  |  | $0 | 1382000 | $0 | 1382000
★★ NET NEW FUNDING REQUIRED — URB ASK |  |  |  |  | 1400000
NOTE: Scope offsets net to $0 (As-Builts deferred to Ph3 + Ph3 Site Surveys accelerated into Ph2 — money already in budget, just repositioned). The entire $1.4M URB ask is attributable to 2 new items: PAR Phase Angle Regulator migration $582,000 + Phase 3 design acceleration $800,000.