## Project Financial Summary
PRJ13797 — JMUX REPLACEMENT ¦ PROJECT FINANCIAL SUMMARY
All Phases (1 · 2 · 3) ¦ Source: Chad Controller Workbook + SOW + Vic call May 18 2026 ¦ ★PCR = pending approval
# | CONTRACTOR | LINE ITEM / SCOPE | 2025 | 2026 | 2027 | TOTAL
1 | MATERIAL
2 | Nokia/Presidio | Nokia MPLS Equipment (SAR-8 nodes + licenses) | 1412400 | 733293 | 963000 | 3108693
3 | Graybar/Presidio | CWDM Cards |  | 25000 | 20000 | 45000
4 | Various | Other (Power Supplies / Connectors) |  | 30000 | 10000 | 40000
| MATERIAL SUBTOTAL |  | 1412400 | 788293 | 993000 | 3193693
5 | B&M (Burns & McDonnell)
6 | B&M | PM Service — Alex Lennox ($5,500/mo) | 66000 | 66000 | 22000 | 154000
7 | B&M | Site Survey — Phase 1 (complete ✅) | 86040 |  |  | 86040
8 | B&M | Site Survey — Phase 2
9 | B&M | Site Survey — Phase 3 (31 sites) ★PCR |  |  | 86000 | 86000
10 | B&M | Staging Support | 51250 |  |  | 51250
11 | B&M | Node Design (IFR+IFC) — Phase 1+2 | 601020 | 214668 |  | 815688
12 | B&M | Node Design (IFR+IFC) — Phase 3 ★PCR |  |  | 450000 | 450000
13 | B&M | Node Design (AS-BUILDs) — Phase 1+2 |  | 42912 |  | 42912
14 | B&M | Node Design (AS-BUILDs) — Phase 3 |  |  | 37200 | 37200
15 | B&M | Construction Support — Phase 1 CSC ✅ | 368100 |  |  | 368100
16 | B&M | Construction Support — Phase 2 CSC |  | 382824 |  | 382824
17 | B&M | Construction Support — Phase 3 CSC ★PCR |  |  | 264000 | 264000
18 | B&M | Phase 3 MPLS Design (accelerated into Ph2) ★PCR |  | 360000 |  | 360000
| B&M SUBTOTAL |  | 1172410 | 1066404 | 859200 | 3098014
19 | HAWKEYE (Hawk Eye Communications)
20 | Hawkeye | Implementation — Phase 1 (SOW complete ✅) | 402793 |  |  | 402793
21 | Hawkeye | Implementation — Phase 2 |  | 361476 |  | 361476
22 | Hawkeye | Implementation — Phase 3 ★PCR |  |  | 320000 | 320000
23 | Hawkeye | Decommissioning — ALL Phases (Phase 3 only) |  |  | 141351 | 141351
24 | Hawkeye | WD#8 Fiber Testing + Patch Panels |  | 8229 |  | 8229
| HAWKEYE SUBTOTAL |  | 402793 | 369705 | 461351 | 1233849
25 | PM / CONTROLLER / SCHEDULER
26 | Hermitage | PM — Dhananjaya Gunaratne |  | 174000 | 58000 | 232000
27 | Hermitage | PM — Ahsan Khawaja |  | 257619 |  | 257619
28 | ComTec | Controller — Chad Boyett | 67200 | 100800 | 33600 | 201600
29 | ComTec | Scheduler — Umair Mohammed | 54160 | 67040 | 13400 | 134600
30 | ComTec | Scheduler — Farouk Adelekan |  | 20000 | 6600 | 26600
31 | Hermitage | O/S Sr. Engineer — Ed Schwartz |  | 30000 | 5000 | 35000
| PM / CONTROLS SUBTOTAL |  | 121360 | 649459 | 116600 | 887419
32 | INTERNAL LABOR
33 | PSEG | Internal Labor — all named resources | 82421 | 154989 | 60000 | 297410
34 | Cognizant | Lee Blackman — Sr. Network Architect |  | 86400 |  | 86400
35 | PSEG | Relay Team Support — Steven Bradley (internal, ZERO actuals to date — call before Mon) |  | 195000 | 30000 | 225000
| INTERNAL LABOR SUBTOTAL |  | 82421 | 436389 | 90000 | 608810
36 | PQA / ASSESSMENTS
37 | Cognizant/EPMO | PQA Audit | 56330 | 40000 | 10000 | 106330
38 | PSEG | Assessments (overhead) | 19172 | 72737 | 20000 | 111909
| PQA / ASSESSMENTS SUBTOTAL |  | 75502 | 112737 | 30000 | 218239
PAR | PAR (Phase Angle Regulator) ★ NEW SCOPE — PCR REQUIRED
a | Nokia/Presidio | Material — Iniven RC-30 (6 units × $8,750) |  | 52500 |  | 52500
b | Chak's Team | Relay Engineering (Chak) 200 hrs × 6 sites × $200/hr = $240,000 ★CONFIRMED Vic |  | 240000 |  | 240000
c | Steven Bradley | Relay Support — Installation & Cutover ~1,298 hrs × $200/hr = $259,500 ★CONFIRMED Vic |  | 259500 |  | 259500
d | Various | PAR Materials (cables, connectors) $30,000 ★CONFIRMED Vic May 18 |  | 30000 |  | 30000
| PAR SUBTOTAL ★PCR★ (CONFIRMED $529,500 + RC-30 $52,500) |  |  | 582000 |  | 582000
T | TRC (Cyber Security)
T1 | TRC | Raju Khedkar — Security Architect | 3726 | 30000 | 5000 | 38726
| TRC SUBTOTAL |  | 3726 | 30000 | 5000 | 38726
★ | GRAND TOTAL — ALL CONTRACTORS |  | 3270612 | 4034987 | 2555151 | 9860750
| CP BUDGET (approved) |  | 3250000 | 2600000 | 1000000 | 6850000
| VARIANCE (Budget − EAC) ⚠ Negative = OVER BUDGET |  | -20612 | -1434987 | -1555151 | -3010750
★PCR items (highlighted green): PAR $582K + Ph3 B&M $800K + Ph3 Hawkeye $320K = ~$1.70M pending PCR approval ¦ Phase 3 site surveys stay in Phase 3 ¦ All decommissioning in Phase 3
PAR confirmed by Vic May 18 2026: Eng $240K (Chak) + Install $259.5K (Steven Bradley) + Materials $30K + RC-30 $52.5K = $582K ¦ Martin Gately DEPARTED — $0 in 2026