## Financial Summary v6
PRJ13797 — JMUX REPLACEMENT ¦ FINANCIAL SUMMARY v6 ¦ CORRECTED: Ph1=31 ¦ Ph2=36 ¦ Ph3=31 sites ¦ May 19 2026
Sources: B&M SOW Ph1 $306K + Ph2 $1,370,040 (Appendix D: $16,695 IFR / $5,963 IFC / $1,192 As-Built per site) ¦ Hawkeye Ph2 SOW $400,680 ¦ Chad WB actuals $5.9M ¦ Graybar POs $241K Ph1 ¦ Vic May 18 2026 ¦ ★PCR pending
# | CONTRACTOR | STEP / DELIVERABLE (SOW-sourced) | P1 | P2 | P3 | 2025 | 2026 | 2027 | TOTAL | SOURCE / NOTE
| ★ ACTUALS TO DATE (Chad Workbook): 2024 = $741,206 ¦ 2025 = $3,130,120 ¦ Jan–Apr 2026 = $2,037,496 ¦ TOTAL SPENT = $5,908,822 | [8 empty] | Chad WB Row 3
1 | MATERIAL — Nokia Equipment
2 | Nokia / Presidio | Nokia SAR-8 MPLS Nodes + licenses + SFPs + CSM cards Ph1: 31 sites COMPLETE ✅ ($1,412,400 actual) Ph2: 36 sites ($733,293 per Chad forecast) Ph3: 31 sites ($1,412,400 est. — same scale as Ph1) | ✓ | ✓ | ✓ | 1412400 | 733293 | 1412400 | 3558093 | Ph1: PO 7000001857+5000059268 ¦ Ph3: est=Ph1 rate
3 | Presidio / Graybar | CWDM Cards per IFC (mux/demux per site) | ✓ | ✓ | ✓ |  | 25000 | 20000 | 45000 | Chad forecast
| MATERIAL SUBTOTAL |  |  |  |  | 1412400 | 758293 | 1432400 | 3603093
4 | CABLES & CONNECTORS (Graybar Electric) — ★ NEW LINE ITEM
5 | Graybar Electric | Phase 1 — Cables, Connectors, Fiber Jumpers 31 sites COMPLETE ✅ Fiber patch cords (2 SM per site), CAT6 (2 per site), serial (RJ45→DB25), 4-wire VF, conduit, fittings, connectors. 4 POs: $24,759 + $115,004 + $55,287 + $46,023 Actual: $241,073 = $7,777/site (31 sites) | ✓ |  |  | 241073 |  |  | 241073 | Graybar POs 7000001767/1811/1841/2119
6 | Graybar Electric | Phase 2 — Cables, Connectors, Fiber Jumpers 36 sites Same per-Hawkeye-SOW cable types: 2× SM fiber, CAT6, serial, 4-wire VF, conduit. Estimate: $7,777/site × 36 sites = $279,956 (PO TBD after IFC issued) |  | ✓ |  |  | 279956 |  | 279956 | Est: $7,777/site × 36 (Graybar Ph1 rate ÷ 31 sites)
7 | Graybar Electric | Phase 3 — Cables, Connectors, Fiber Jumpers 31 sites ★PCR Same scope. Estimate: $7,777/site × 31 sites = $241,073 (PO TBD 2027) |  |  | ✓ |  |  | 241073 | 241073 | Est: $7,777/site × 31 ★PCR
| CABLES & CONNECTORS SUBTOTAL |  |  |  |  | 241073 | 279956 | 241073 | 762102
8 | B&M (Burns & McDonnell) — Ph1 SOW $306K + Ph2 SOW $1,370,040 (Appendix D rates)
9 | B&M — Alex Lennox | Step 1: PM Service $5,500/month Ph1 Sep 2024–Jan 2026 (17 mo) + Ph2 Feb–Sep 2026 (8 mo) + Ph3 2027 (4 mo) Weekly status, meeting minutes, schedule, PSEG PDLC compliance. | ✓ | ✓ | ✓ | 66000 | 66000 | 22000 | 154000 | Ph1 SOW M4 + Ph2 SOW PO 316200 $5,500/mo
10 | B&M — Ph1 SI | Step 2: Ph1 Systems Integrator COMPLETE ✅ ($152,300) M1 Network equipment specs $36,250 + M2 Vendor RFP $16,250 + M3 Surveys $99,800 | ✓ |  |  | 152300 |  |  | 152300 | Ph1 SOW total $306K (paid ✅)
11 | B&M — Ethan Koch | Step 3a: Site Surveys Ph2 COMPLETE ✅ (SOW CPS M3 = $86,040) Visual inspection 36 sites. Digital photos + video. Feeds IFR design. Paid Feb 27 2026. |  | ✓ |  |  | 86040 |  | 86040 | Ph2 SOW M3 = $86,040 (paid ✅)
12 | B&M — Ethan Koch | Step 3b: Site Surveys Ph3 ★PCR (31 sites, ~$86,000) Starts Aug 2026 tied to Ph2 staging start. PSEG escort required. |  |  | ✓ |  |  | 86000 | 86000 | Est ~$86K per Ph2 SOW M3 rate ★PCR
13 | B&M — Ethan Koch | Step 4a: Staging Support Ph1 COMPLETE ✅ (SOW M1 = $57,300 ★ 1 WEEK) Card slotting + SFP plan, fiber connectivity matrix, chassis labeling. Full staging test plan: firmware, IGP, BGP, BFD, SyncE, NMS, VPRN/Epipe/Cpipe, failure tests. | ✓ |  |  | 57300 |  |  | 57300 | Ph2 SOW CPS M1 = $57,300 (paid ✅)
14 | B&M — Ethan Koch | Step 4b: Staging Support Ph2 (SOW ~$25,625 ★ 1 WEEK — not 2 per SOW) Same test plan scope. 36 nodes. Jul 2026. |  | ✓ |  |  | 25625 |  | 25625 | Prorated from Ph1 $57,300 × 36/31
15 | B&M — Ethan Koch | Step 4c: Staging Support Ph3 ★PCR (1 week, 31 nodes, ~$25,625) |  |  | ✓ |  |  | 25625 | 25625 | Estimate ★PCR
16 | B&M — Nick Cianciolo | Step 5a: MPLS Node Design IFR Ph1 COMPLETE ✅ $16,695/site × 31 sites = $517,545 Per site: floor plan (AutoCAD), rack elevation (Visio), power one-line (Visio), cable schedule (Excel), BOM (Excel), site scope of work (Word). | ✓ |  |  | 517545 |  |  | 517545 | Ph2 SOW App D: $16,695 × 31 sites (paid ✅)
17 | B&M — Nick Cianciolo | Step 5b: MPLS Node Design IFR Ph2 (rolling Feb–Jun 29 2026) $16,695/site × 36 sites = $601,020 Same deliverable package per site. Final IFR deadline Jun 29 2026. PSEG has 10 business days to review each IFR before B&M issues IFC. |  | ✓ |  |  | 601020 |  | 601020 | Ph2 SOW App D: $16,695 × 36 sites
18 | B&M — Nick Cianciolo | Step 5c: MPLS Node Design IFC Ph2 (final IFC Jul 13 2026) $5,963/site × 36 sites = $214,668 PE-sealed. Issued for construction. Triggers Hawkeye cable orders + construction. |  | ✓ |  |  | 214668 |  | 214668 | Ph2 SOW App D: $5,963 × 36 sites
19 | B&M — Nick Cianciolo | Step 5d: MPLS Node Design IFR+IFC+As-Built Ph3 ★PCR (31 sites) IFR: $16,695 × 31 = $517,545 ¦ IFC: $5,963 × 31 = $184,853 As-Built: $1,192 × 31 = $36,952 ¦ TOTAL: $23,850 × 31 = $739,350 Ph3 design accelerated into Ph2 window per recovery plan. |  |  | ✓ |  |  | 739350 | 739350 | Ph2 SOW App D rate × 31 sites ★PCR
20 | B&M — Nick Cianciolo | Step 6a: AS-BUILT Drawings Ph1 COMPLETE ✅ ($1,192 × 31 = $36,952) | ✓ |  |  | 36952 |  |  | 36952 | Ph2 SOW App D: $1,192 × 31 sites
21 | B&M — Nick Cianciolo | Step 6b: AS-BUILT Drawings Ph2 ($1,192 × 36 = $42,912) Issued 1 month after construction complete. Red-line record drawings. |  | ✓ |  |  | 42912 |  | 42912 | Ph2 SOW App D: $1,192 × 36 sites
22 | B&M — Ethan Koch | Step 7a: Construction Support Coordinator Ph1 COMPLETE ✅ (SOW M2 = $368,100) On-site daily. $61,350/mo × 6 mo Aug 2025–Jan 2026. Field coordination, daily reports, RFI log, cutover/commissioning support. | ✓ |  |  | 368100 |  |  | 368100 | Ph2 SOW M2 = $368,100 (paid ✅)
23 | B&M — Ethan Koch | Step 7b: Construction Support Coordinator Ph2 $61,350/mo × ~6 mo (Aug 2026–Jan 2027) = $368,100 (in 2026 forecast) Pre-construction planning, on-site coordination, RFI log, daily field reports, cutover/commissioning support, Go-Live verification. |  | ✓ |  |  | 382824 |  | 382824 | Ph2 SOW M2 invoiced monthly
24 | B&M — Ethan Koch | Step 7c: Construction Support Coordinator Ph3 ★PCR ~$264,000 est. (~4 months × $61,350). |  |  | ✓ |  |  | 264000 | 264000 | Est $61,350/mo × 4 mo ★PCR
25 | B&M | Step 8: Ph3 MPLS Detail Design (accelerated into Ph2) ★PCR 31-site full design pulled from 2027→2026 to recover 5-month schedule. $360,000 est. (PCR pending). |  | ✓ |  |  | 360000 |  | 360000 | PCR recovery plan ★PCR
| B&M SUBTOTAL |  |  |  |  | 1198197 | 1779089 | 1136975 | 4114261
26 | HAWKEYE (Elecnor Hawkeye) — Ph1 PO $402,793 ¦ Ph2 SOW $400,680
27 | Hawkeye — Vinny M. | Step 1: Pre-Construction Survey (per site after IFC issued) Ph1 complete ✅. Ph2: Vinny visits each substation, measures cable runs, confirms rack location per IFC, photos existing JMUX, generates site BOM. Cannot order cables until survey done. Ph2 SOW M1 = $100,170. | ✓ | ✓ | ✓ |  | 100170 |  | 100170 | Hawkeye Ph2 SOW M1 = $100,170
28 | Hawkeye | Step 2a: Staging Ph1 COMPLETE ✅ (★ 1 WEEK — Ph2 SOW M-Ph0 = $100,170) Rack + slot 31 Nokia SAR-8 nodes per B&M card plan, install SFPs, power-on, execute B&M staging test plan, label chassis. | ✓ |  |  | 100170 |  |  | 100170 | Hawkeye Ph2 SOW M-Ph0 = $100,170 (paid ✅)
29 | Hawkeye | Step 2b: Staging Ph2 (★ 1 WEEK, Jul–Aug 2026 — SOW M-Ph0 = $100,170) Same scope. 36 nodes. B&M provides card-slotting + connectivity matrix. |  | ✓ |  |  | 100170 |  | 100170 | Hawkeye Ph2 SOW M-Ph0 = $100,170
30 | Hawkeye | Step 2c: Staging Ph3 ★PCR (1 week, 31 nodes, ~$100,170) |  |  | ✓ |  |  | 100170 | 100170 | Est = Ph2 SOW rate ★PCR
31 | Hawkeye — 3 visits | Step 3a: Substation Installation Ph1 COMPLETE ✅ (Ph1 PO = $402,793 / 31 sites) Visit 1: deliver, rack SAR-8, run conduit, pull cables, install Eltek PSU Visit 2: terminate fiber (2 SM per site), CWDM, RS-232 patch panel, CAT6, 4-wire VF Visit 3: energize node, basic checklist, notify B&M CSC + relay team | ✓ |  |  | 302623 |  |  | 302623 | Ph1 PO 7000002054 = $402,793 (paid ✅)
32 | Hawkeye — 3 visits | Step 3b: Substation Installation Ph2 (Ph2 SOW M2 = $80,136) Same 3-visit scope. 36 sites. Construction window: Aug 5 – Sep 28 2026. Install: Nokia SAR-8, CWDM, Eltek PSU, RS-232 patch panel, fiber, CAT6, serial, 4-wire VF, ground bar, conduit, inner duct. Checkout checklist + record docs per site. |  | ✓ |  |  | 80136 |  | 80136 | Hawkeye Ph2 SOW M2 = $80,136
33 | Hawkeye — 3 visits | Step 3c: Substation Installation Ph3 ★PCR (31 sites, ~$402,793) Same 3-visit scope. Est = Ph1 PO rate: $12,993/site × 31 = $402,793 |  |  | ✓ |  |  | 402793 | 402793 | Est: Ph1 rate $12,993/site × 31 ★PCR
34 | Hawkeye | Step 4a: Go-Live Sign-Off Ph2 (SOW M4 = $80,136) After relay team completes RTU cutover: confirm all Nokia circuits live, no JMUX traffic, B&M CSC punch list clear. PSEG formal acceptance. |  | ✓ |  |  | 80136 |  | 80136 | Hawkeye Ph2 SOW M4 = $80,136
35 | Hawkeye | Step 4b: Go-Live Sign-Off Ph3 ★PCR (~$100,000 est.) |  |  | ✓ |  |  | 100000 | 100000 | Estimate ★PCR
36 | Hawkeye | Step 5: Decommissioning — ALL Phases (Ph3 window only, SOW M6) Cannot start until Nokia LIVE on all 3 phases. De-rack, remove JMUX cabling, palletize + ship to PSEG warehouse, restore substation. 98 sites total (31+36+31). $141,351 est. |  |  | ✓ |  |  | 141351 | 141351 | Hawkeye Ph2 SOW M6=$40,068 Ph2 + Ph1/Ph3 est.
37 | Hawkeye | WD#8 Fiber Testing — Elwood to Northport + 7 patch panels | ✓ |  |  |  | 8229 |  | 8229 | PO 7000009182 = $8,229
| HAWKEYE SUBTOTAL |  |  |  |  | 402793 | 368841 | 744314 | 1515948
PAR | PAR (Phase Angle Regulator) ★ NEW SCOPE — PCR REQUIRED ¦ 6 sites
a | Nokia / Presidio | Step 1: Iniven RC-30 Equipment (6 units × $8,750 = $52,500) Serial→C37.94 converter. PO placed. 8-week lead. Target delivery Jun 2026. Sites: Northport, 5HK Hicksville, Melville, 7Z Lindenhurst, 2H Far Rockaway, 2R Hewlett. |  | ✓ |  |  | 52500 |  | 52500 | PO 7000002695 ★PCR
b | Chak's Team | Step 2: Relay Engineering Design (200 hrs × 6 sites × $200/hr = $240,000) CONFIRMED Vic May 18. Review PAR scheme, design C37.94 interface, relay settings, MOP, NERC-CIP compliance, coordinate with B&M on IFC drawings. Jun–Aug 2026. |  | ✓ |  |  | 240000 |  | 240000 | CONFIRMED Vic May 18 2026 ★PCR
c | Steven Bradley | Step 3: Relay Install, Configure & Cutover (~1,298 hrs × $200/hr = $259,500) CONFIRMED Vic May 18. Install RC-30, wire to PAR relay contacts, configure C37.94, end-to-end protection test, NERC-CIP commissioning, cutover from legacy serial path. ★ Call Steven before Mon May 25 — get names + hours by month. |  | ✓ |  |  | 259500 |  | 259500 | CONFIRMED Vic May 18 2026 ★PCR
d | Various | Step 4: PAR Materials ($30,000 — CONFIRMED Vic May 18) Custom serial cables, C37.94 connectors, rack hardware across 6 sites. |  | ✓ |  |  | 30000 |  | 30000 | CONFIRMED Vic May 18 2026 ★PCR
| PAR SUBTOTAL ★PCR★ ($52.5K RC-30 + $240K Eng + $259.5K Install + $30K Materials) |  |  |  |  | 0 | 582000 | 0 | 582000
38 | PM / CONTROLLER / SCHEDULER
39 | Hermitage — Jay G | PM — Dhananjaya Gunaratne | ✓ | ✓ | ✓ |  | 174000 | 58000 | 232000 | Chad forecast
40 | Hermitage — Ahsan | PM — Ahsan Khawaja |  | ✓ |  |  | 257619 |  | 257619 | PO 7000001734
41 | ComTec — Chad | Controller Chad Boyett $8,400/mo | ✓ | ✓ | ✓ | 67200 | 100800 | 33600 | 201600 | Chad forecast
42 | ComTec — Umair | Scheduler Umair Mohammed $5,416/mo | ✓ | ✓ | ✓ | 54160 | 67040 | 13400 | 134600 | PO 7000001145/2363
43 | ComTec — Farouk | Scheduler Farouk Adelekan |  | ✓ | ✓ |  | 20000 | 6600 | 26600 | PO 5000046818
44 | Hermitage — Ed S | O/S Sr. Engineer Edward Schwartz $2,512/mo | ✓ | ✓ | ✓ |  | 30000 | 5000 | 35000 | PO 7000001998
| PM / CONTROLS SUBTOTAL |  |  |  |  | 121360 | 649459 | 116600 | 887419
45 | INTERNAL LABOR (PSEG + Cognizant)
46 | PSEG — Multiple | PSEG Internal Labor (Rahiq, Brianna, Chok, Lok, Sameer et al.) | ✓ | ✓ | ✓ | 82421 | 154989 | 60000 | 297410 | Chad forecast
47 | Cognizant — Lee | Lee Blackman — Sr. Network Architect $7,200/mo | ✓ | ✓ |  |  | 86400 |  | 86400 | PO 7000002490
48 | PSEG — Steven B | Relay Team — Steven Bradley ★ ZERO SAP actuals. $195K forecast. Names + hrs needed before Mon May 25. | ✓ | ✓ | ✓ |  | 195000 | 30000 | 225000 | Chad forecast — UNVERIFIED
| INTERNAL LABOR SUBTOTAL |  |  |  |  | 82421 | 436389 | 90000 | 608810
49 | PQA / ASSESSMENTS / TRC
50 | Cognizant / EPMO | PQA Audit — Margaret Tanner Glover | ✓ | ✓ | ✓ | 56330 | 40000 | 10000 | 106330 | Chad forecast
51 | PSEG | Assessments (PSEG IT overhead) | ✓ | ✓ | ✓ | 19172 | 72737 | 20000 | 111909 | Chad forecast
52 | TRC — Raju K | Raju Khedkar — Cyber Security / NERC-CIP | ✓ | ✓ | ✓ | 3726 | 30000 | 5000 | 38726 | PO 7000001237/2343
| PQA / ASSESSMENTS / TRC SUBTOTAL |  |  |  |  | 79228 | 142737 | 35000 | 256965
★ | GRAND TOTAL — ALL PHASES (Ph1=31 ¦ Ph2=36 ¦ Ph3=31 = 98 sites) |  |  |  |  | 3537472 | 4996764 | 3796362 | 12330598 | Full EAC incl. 2024: $13,071,804
| APPROVED CP BUDGET (Chad WB: 2024 $750K + 2025 $3.25M + 2026 $2.6M) |  |  |  |  | 3250000 | 2600000 |  | 6600000 | No 2027 budget approved
FUNDING GAP = $6,471,804 ¦ URB ASK (+ $400K contingency) = $6,871,804
SITES: Ph1=31 ¦ Ph2=36 ¦ Ph3=31 ¦ TOTAL=98 ¦ B&M per-site rates (App D): IFR $16,695 ¦ IFC $5,963 ¦ As-Built $1,192 ¦ Total $23,850 ¦ Cable est: $7,777/site (Graybar Ph1 $241,073 ÷ 31 sites) ¦ Hawkeye Ph3 est: $12,993/site (Ph1 PO $402,793 ÷ 31 sites) ¦ ★PCR = green highlights ¦ Staging = 1 WEEK not 2
PAR CONFIRMED Vic May 18: $582K total ¦ Steven Bradley ZERO SAP actuals — call before Mon May 25 ¦ Martin Gately DEPARTED — $0 2026+ ¦ 2027 entirely unfunded — $3,796,362 needed from URB

## URB Ask
PRJ13797 JMUX — URB FUNDING REQUEST ¦ CORRECTED: Ph1=31 ¦ Ph2=36 ¦ Ph3=31 ¦ May 19 2026
ITEM | AMOUNT | CUMULATIVE EAC | NOTES
WHAT HAS BEEN SPENT (Actuals — locked in SAP)
2024 Actuals | 741206 | 741206 | Nokia equip, B&M surveys, initial work
2025 Actuals | 3130120 | 3871326 | Ph1 delivery: Nokia, Hawkeye, B&M, PM
Jan–Apr 2026 Actuals | 2037496 | 5908822 | Ph2 engineering underway
TOTAL SPENT | 5908822 | 5908822 | vs $6.6M approved budget = $691K remaining
REMAINING WORK (ETC — what we still have to spend)
ETC May–Dec 2026 (base contracted) | 2959268 |  | B&M IFR/IFC, Hawkeye install, CSC, PM, internal labor
Cables & Connectors Ph2 (36 sites × $7,777) | 279956 |  | Graybar — not in original estimate
PAR — Full scope ★PCR | 582000 |  | CONFIRMED Vic May 18: RC-30 $52.5K + Eng $240K + Install $259.5K + Mat $30K
B&M Ph3 Design acceleration ★PCR | 360000 |  | 31-site MPLS design into 2026 to recover schedule
2026 EAC TOTAL | 4996764 |  | vs 2026 budget $2.6M → gap = $2,396,764
2027 Nokia Ph3 (31 sites × $45,561/site) | 1412400 |  | ENTIRELY UNFUNDED — no 2027 budget approved
2027 Cables & Connectors Ph3 ★PCR | 241073 |  | 31 sites × $7,777/site
2027 B&M Ph3 (IFR+IFC+As-Built+Surveys+Staging+CSC) | 1114975 |  | $23,850×31 + surveys $86K + staging $25.6K + CSC $264K
2027 Hawkeye Ph3 (install + decom + Go-Live) ★PCR | 644144 |  | Install 31 sites + decom all 98 + Go-Live sign-off
2027 PM / Controls / Labor / PQA / TRC | 263600 |  | PM Jay, Chad, Umair, Farouk, Ed, PSEG internal
2027 EAC TOTAL | 3796362 |  | ALL UNFUNDED — entire Phase 3
THE NUMBER
Full Project EAC (2024+2025+2026+2027) | 13071804 | 13071804 | All phases complete
Approved Budget (2024+2025+2026) | 6600000 | 6600000 | No 2027 budget. Source: Chad WB Row 2.
★★★ URB FUNDING GAP = $6,471,804 + $400,000 contingency buffer RECOMMEND ASKING URB FOR: $6,871,804
WHY WE ARE OVER BUDGET (your URB talking points)
PAR — scope not in original estimate | 582000 | Phase Angle Regulator migration discovered in Ph2 surveys. Was $30-40K placeholder. CONFIRMED at $582K (Vic May 18). 6 substations: Northport, Hicksville, Melville, Lindenhurst, Far Rockaway, Hewlett. NERC-CIP compliant Iniven RC-30 solution.
Phase 3 — ENTIRELY unfunded | 3796362 | No 2027 budget was ever approved. Phase 3 (31 sites) costs $3,796,362. Largest single driver of the funding gap.
Ph3 design acceleration ★PCR | 360000 | 31-site MPLS design pulled from 2027 into 2026 to recover 5-month schedule impact from PAR discovery. Critical path recovery — no choice.
Cables & connectors — missed in original budget | 521029 | Ph1 Graybar actuals = $241,073 for 31 sites ($7,777/site). Ph2 (36 sites): $279,956. Ph3 (31 sites): $241,073. Not separately budgeted in original estimate.
Nokia Ph3 equipment | 1412400 | 31 sites at same Ph1 rate ($45,561/site). Part of unfunded Phase 3.