## PCR Summary v7
PRJ13797 — JMUX REPLACEMENT ¦ PROJECT CHANGE REQUEST (PCR) SUMMARY ¦ Net New Funding Ask: $1,400,000
May 21 2026 ¦ Ph1=31 sites COMPLETE ✅ ¦ Ph2=36 sites IN PROGRESS ¦ Ph3=31 sites PENDING ¦ Total 98 sites
STEP 1 — APPROVED PROJECT BUDGET (what PSEG has already authorized)
# | DESCRIPTION | VENDOR | PHASE 1 | PHASE 2 | PHASE 3 | TOTAL | SOURCE
1 | Nokia MPLS Equipment + SFPs + licenses | Nokia/Presidio | 1412400 | 733293 | 1412400 | 3558093 | POs 7000001857/1175/1748 + forecast
2 | Cables & Connectors (all phases) | Vendor TBD (Ph1=Graybar) | 241073 | 279956 | 241073 | 762102 | Ph1 actual 4 POs; Ph2/Ph3 vendor TBD
3 | B&M Engineering + PM + Construction Support | Burns & McDonnell | 1161245 | 1428428 | 1229914 | 3819587 | Ph1 SOW $306K + Ph2 SOW $1,370,040
4 | Hawkeye Installation + Staging + Go-Live | Elecnor Hawkeye | 402793 | 368841 | 744314 | 1515948 | Ph1 PO $402,793 + Ph2 SOW $400,680
5 | PM / Controls / Scheduler | Hermitage/ComTec | 121360 | 649459 | 116600 | 887419 | POs + Chad forecast
6 | Internal Labor (PSEG + Cognizant) | PSEG/Cognizant | 82421 | 436389 | 90000 | 608810 | Chad forecast + POs
7 | PQA / Assessments / NERC-CIP | Cognizant/PSEG/TRC | 79228 | 142737 | 35000 | 256965 | Chad forecast + POs
TOTAL APPROVED PROJECT EAC (excl. 2024 actuals $741K) |  |  | 3500520 | 4039103 | 3869301 | 11408924
STEP 2 — SCOPE OFFSETS (budget shifting between phases — NO new money required)
# | DESCRIPTION | DIRECTION | PHASE 1 | PHASE 2 | PHASE 3 | NET IMPACT | NOTE
A | Ph1 As-Built Drawings — deferred to Phase 3 | Ph1 → Ph3 | -36952 | — | 36952 | — | B&M SOW App D $1,192×31 sites — already in budget, just moves
B | Ph2 As-Built Drawings — deferred to Phase 3 | Ph2 → Ph3 | — | -42912 | 42912 | — | B&M SOW App D $1,192×36 sites — already in budget, just moves
C | Ph3 Site Surveys — accelerated into Phase 2 | Ph3 → Ph2 | — | 86000 | -86000 | — | B&M SOW M3 rate ~$86K — pulled forward, no new cost
NET OFFSET IMPACT (these cancel — no new money) |  |  | -36952 | 43088 | -6088 | $0 — nets to zero | Offsets net to $0 — money already in budget, just repositioned
STEP 3 — NEW SCOPE (PCR REQUIRED — this is the $1.4M ask)
# | DESCRIPTION | VENDOR | PHASE 1 | PHASE 2 | PHASE 3 | TOTAL | SOURCE / NOTE
1 | PAR — Iniven RC-30 Equipment (6 units × $8,750) 6 sites: Northport, 5HK, Melville, 7Z, 2H, 2R | Nokia/Presidio | — | 52500 | — | 52500 | PO 7000002695 — CONFIRMED Vic May 18 2026
2 | PAR — Relay Engineering Design 200 hrs × 6 sites × $200/hr | Chak's Team | — | 240000 | — | 240000 | CONFIRMED Vic May 18 2026 — no SOW yet
3 | PAR — Relay Install, Configure & Cutover ~1,298 hrs × $200/hr | Steven Bradley | — | 259500 | — | 259500 | CONFIRMED Vic May 18 2026 — call Steven before May 25
4 | PAR — Materials (cables, connectors, rack hardware) | Various | — | 30000 | — | 30000 | CONFIRMED Vic May 18 2026
5 | Phase 3 Design Acceleration into Phase 2 window 31-site IFR+IFC design pulled from 2027→2026 | Burns & McDonnell | — | 800000 | — | 800000 | Schedule recovery plan — PCR pending
PCR SUBTOTAL (PAR $582K + Ph3 Acceleration $800K) |  |  | — | 1382000 | — | 1382000
STEP 4 — FUNDING SUMMARY
Total Project EAC (all phases, excl. 2024) |  |  |  |  | 11408924 | Full cost to complete the project
Already Spent (2024 + 2025 + Jan–Apr 2026) |  |  |  |  | 5908822 | Chad workbook actuals confirmed
Approved CP Budget (2025 + 2026) |  |  |  |  | 5850000 | PSEG authorized budget
Scope Offsets (net zero — budget repositioned) |  |  |  |  | Nets to $0 | As-Builts deferred + Ph3 surveys accelerated
NEW SCOPE — PAR ($582K) + Ph3 Accel ($800K) |  |  |  |  | 1382000 | ★ This is the PCR ask
URB ASK — NET NEW FUNDING REQUIRED |  |  |  |  | 1400000 | ★★ ROUND NUMBER FOR URB PRESENTATION
NOTE: Scope offsets (As-Builts moved to Ph3 + Ph3 Site Surveys pulled into Ph2) net to $0 — existing budget repositioned, no new money. The $1.4M URB ask is entirely attributable to: (1) PAR Phase Angle Regulator new scope $582K + (2) Phase 3 design acceleration $800K.