PRJ13797 — JMUX Replacement CIO Presentation — Oral Talking Points Jay Gunaratne · March 2026 · Audience: CIO, SVP, Project Team

| SLIDE 1 · COVER / OPENING ⏱ ~3 minutes |  |
| --- | --- |

OBJECTIVE: Set the tone — confident, prepared, no surprises.

"Good [morning/afternoon] everyone. I'm Jay Gunaratne, Program Manager for the JMUX Replacement project — PRJ13797. Thank you for making time today."

Tell them you'll cover: accomplishments, current status, critical path, financials, risks, and path to completion.

"I want to be direct — we have one active blocker right now. I'll address it head-on in the schedule section and show you exactly what the recovery plan looks like."

Pause. Make eye contact. Let them settle in before advancing.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 2 · GOALS & OBJECTIVES ⏱ ~4 minutes |  |
| --- | --- |

OBJECTIVE: Frame the why — remind leadership this is not optional.

GE announced end-of-life for the legacy Jungle MUX at end of 2025 — replacing 25-year-old infrastructure is mandatory.

Program scope: 129 substations total — 31 Phase 1, 45 Phase 2, 35 Phase 3. 79 Nokia MPLS nodes across the full program.

Engineering: All Phase 1 surveys, rack elevations, power designs done and approved. Phase 2 surveys completed proactively during Phase 1 — big win.

Procurement: All Phase 1 equipment purchased, staged, and delivered. Nokia Phase 2 equipment arrived February 19th — ahead of schedule.

Construction: All 31 Phase 1 sites installed and commissioned. SSP documentation submitted and approved.

One item in progress: remote connectivity to the nodes — covered on the schedule slide.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 3 · PHASE 1 ACCOMPLISHMENTS ⏱ ~4 minutes |  |
| --- | --- |

OBJECTIVE: Show the wins clearly. Construction is done — own it.

Phase 1 construction: all 31 substations installed and commissioned. 100% done.

Staging complete at Hawkeye warehouse — September 29, 2025, on schedule.

Nokia Phase 2 equipment delivered February 19, 2026 — ahead of when it was needed.

CWDM cutover at Hicksville and ACC complete. Routers installed in primary and secondary cabinets. NSP racked and powered at Melville and Hicksville.

CMDB updated. OTDR testing Hicksville to Syosset — complete. ✅ OTDR trace files sent to Burns & McDonnell.

Wave 1 non-tie cutovers: Dec 8–18, 2025. Wave 2 tie-in cutovers: Jan 6–8, 2026. Both done.

Be honest with leadership: Per Vik's March 16 directive — Phase 1 has micro-phases. Construction is 100%. Deployment is ~5%. App and RTU cutovers not yet started. Phase 1 close target: June 2026.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 4 · PHASE 2 STATUS ⏱ ~4 minutes |  |
| --- | --- |

OBJECTIVE: Forward-looking story — we are not waiting on Phase 2.

Phase 2: 45 sites. Burns & McDonnell SOW: $1.37M for engineering design.

Site surveys — complete ✅. Nokia equipment delivered — complete ✅.

IFR Wave 1 (Far Rockaway, Valley Stream, Cedarhurst) — converted to IFC, uploaded to shared drive. ✅

IFC Wave 1 — complete and approved. Wave 2 IFR design in progress with B&McD.

Construction and cutover — not started. Target August–December 2026, pending IFC completion. On track.

Key message: Phase 2 design is running in parallel with Phase 1 close-out. We are not waiting.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 5 · SCHEDULE STATUS ⏱ ~5 minutes |  |
| --- | --- |

OBJECTIVE: Own the yellow status. Pivot immediately to the recovery plan.

SPI is 0.76 — yellow band. Last month was 0.75 — we have stabilized but are not yet green.

Root causes: SSP documentation delays (security review queue), CMDB coordination time, inclement weather, Crown Castle fiber issue at Hicksville (now resolved).

Number one blocker: ILO configuration. Bill from B&M is working directly with Rahiq to resolve a console cable and firmware issue. Expected to be unblocked in 24–48 hours.

✅ Northport DC power issue — FULLY RESOLVED. New cable run, issue confirmed closed.

Recovery sequence: ILO complete → BGP config Hicksville & Melville (Lee Blackman) → Remote access 31 routers → App cutovers → RTU cutovers → Phase 1 close June 2026.

Program history on screen: started April 2024, Phase 1 construction complete, now in March 2026 deployment phase. Program completion target remains July 2027.

Speak slowly here. This is the most important slide. Own the yellow, pivot to the plan.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 6 · CRITICAL PATH — NEXT 10 STEPS ⏱ ~5 minutes |  |
| --- | --- |

OBJECTIVE: Show you have a detailed, owned, step-by-step recovery plan.

Step 1 — ILO Console Cable & Firmware (Mar 19–20): Bill calls Rahiq, cables being sourced. This is the gate that unlocks everything downstream. #1 blocker.

Step 2 — ILO Port Activation (Mar 21–24): Rahiq and Brianna configure ILO management ports at Hicksville & Melville. Change ticket to be opened.

Step 3 — Wire Drops (Mar 19–21, parallel): Jay + Hawkeye completing wire drops from LGX panels to equipment. SFPs and change order needed.

Step 4 — Nokia Training (Mar 19, 3PM): Glenn (Nokia) + PSEG LI team. ✅ Done.

Step 5 — Phase 2 BOM & Inventory (week of Mar 23): Jay + Vinny at Hawkeye — reconcile Phase 2 Nokia equipment vs BOM, identify supply chain gaps.

Step 6 — BGP Configuration (Mar 24–28): Lee Blackman configures BGP at Hicksville & Melville after ILO complete. Change documentation submitted.

Step 7 — IFR Submissions (Mar 30): BMcD (Ethan Koch) submits IFR packages for Green Acres & Berry Street. On track.

Step 8 — Remote Access Config (Apr 1–18): Lee configures all 31 routers remotely once BGP validated at hub sites.

Step 9 — NSP Software Install (Mid–Late Apr): Nokia activates NSP and Layer 3. Starts at Hicksville & Melville, then site by site.

Step 10 — App & RTU Cutovers (May 2026): First wave begins. Phase 1 close target: June 2026.

This is your showstopper slide. Walk through each step. Ownership is assigned, timeline is clear.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 7 · PHASE 1 HIGHLIGHT ACCOMPLISHMENTS (DETAIL) ⏱ ~3 minutes |  |
| --- | --- |

OBJECTIVE: Detailed evidence slide — let the checkmarks speak.

Hawkeye staging complete September 29, 2025. Nokia Phase 2 equipment arrived February 19, 2026.

All 31 sites installed. ACC cabling and fiber panel complete. CWDM cutover done. Routers installed. NSP racked and powered. CMDB updated.

Wave 1 non-tie cutovers: Dec 8–18, 2025. Wave 2 tie-in cutovers: Jan 6–8, 2026. Both complete.

Reiterate Vik's point: Phase 1 ~65% complete overall. Construction 100%, deployment ~5%, app/RTU cutovers 0%. June 2026 target for full Phase 1 close.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 8 · PHASE 1 — LAYER 1-3 CONFIGURATION NEXT STEPS ⏱ ~3 minutes |  |
| --- | --- |

OBJECTIVE: Technical overview for the team members on the call.

Layer 1 (physical): Wire drops and fiber terminations are the last physical items in progress.

Layer 2 & 3: ILO, BGP, and remote access work. Once ILO unblocked and BGP configured at both hub sites, Lee configures all 31 routers remotely.

NSP and Layer 3 services follow from Nokia once remote access is validated.

Configuration work is well-defined, ownership is clear. Only dependency is the ILO cable resolution — actively being worked.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 9 · PROJECT STATUS REPORT — PMO FORMAT ⏱ ~4 minutes |  |
| --- | --- |

OBJECTIVE: Financials — no surprises. At budget.

Total LIPA-approved budget: $6.6 million.

Spend to date: $4.44 million. Estimate to complete: $2.16 million. Estimate at completion: $6.6 million.

NO variance to report. We are tracking at budget.

Scope: 65% complete as of this reporting period.

Timeline: planned baseline end April 2027. Current actual target July 2027 — 3-month extension reflecting micro-phase complexity.

BGP approved March 16 — Lee Blackman proceeding with change docs. ILO is active critical path blocker.

✅ Northport DC power — FULLY RESOLVED. New cable run, confirmed closed.

Remediation for yellow schedule: complete remote config of all 31 routers and testing.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 10–12 · PHASE 1 SUBSTATION SCHEDULE (3 PAGES) ⏱ ~2–3 minutes each |  |
| --- | --- |

OBJECTIVE: Visual evidence. Let the slides do the work — keep commentary brief.

All 31 sites marked complete on the construction side — 18 months of coordinated field work.

Phase 2 site surveys also shown — completed proactively during Phase 1. Paying off now.

Remote configuration and cutover work for these sites is what remains — April through June workstream.

No field mobilization required for remaining Phase 1 work — all remote configuration from here.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 13 · CURRENT RISKS & NEXT STEPS ⏱ ~4 minutes |  |
| --- | --- |

OBJECTIVE: Acknowledge reds clearly. Show you are on top of it.

Legacy equipment fragility: 25+ year-old JMUX, faulty connectors, brittle fiber panels. Mitigation: careful planning, B&McD on-site. Phase 1 construction done — risk reduced going into Phase 2.

Weather/access delays: medium risk, tracked weekly, plans adjusted as needed.

Recent wins to highlight first: Cat 6 complete Mar 4 ✅. OTDR complete Mar 9 ✅. OTDR trace files sent to B&M ✅. BGP approved Mar 16 ✅. Northport DC power — new cable run, FULLY RESOLVED ✅.

Three red items remaining — all connected: ILO → BGP config → Remote access 31 routers. Bill is personally engaged on ILO. Tracking daily.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 14 · RISKS & ISSUES REGISTER ⏱ ~4 minutes |  |
| --- | --- |

OBJECTIVE: Show the risk register is current and actively managed.

HIGH — Legacy equipment fragility: 25+ yr JMUX, faulty connectors, brittle fiber. Mitigation: B&McD on-site, careful cutover planning. Phase 1 construction done reduces this significantly.

MEDIUM — Substation access delays: weather, scheduling, escort availability. Weekly verification before mobilizing.

MEDIUM — Phase 2 schedule slippage: 4-wk IFR + 2-wk review + 2-wk IFC cycle, limited buffer. Mitigation: concurrent B&McD site design, weekly tracking.

RESOLVED ✅ — Crown Castle fiber (Hicksville): OTDR confirmed bad filter March 9. No escalation needed. Closed.

RESOLVED ✅ — Cat 6 cabling Hicksville NSP: confirmed by Vinny March 13. Closed.

RESOLVED ✅ — OTDR testing Hicksville: complete March 9. Trace files sent to B&M. Closed.

RESOLVED ✅ — Northport DC power: new cable run confirmed. Fully closed.

IN PROGRESS 🔴 — Remote access Phase 2 nodes: BGP approved March 16. ILO is #1 blocker — Bill/Rahiq resolving.

COMPLETE ✅ — Phase 2 SSP/security reviews: all approved February 10, 2026.

───────────────────────────────────────────────────────────────────────────────────────────────

| SLIDE 15 · NEXT STEPS & PATH TO COMPLETION — CLOSING ⏱ ~5 minutes |  |
| --- | --- |

OBJECTIVE: Leave them with the plan, not the problem. Strong close.

Immediate 30 days: BGP docs with Lee underway. ILO blocker being resolved by Bill & Rahiq. Wave 1 IFCs complete. Wave 2 IFRs in progress. Weekly B&McD calls continuing.

Q1 2026 → Phase 1 Operational (June 2026)*

Q2 2026 → Phase 2 IFC completion (all 36 sites)

Q2–Q3 2026 → Phase 2 construction mobilization

Q3–Q4 2026 → Phase 2 installations at all 36 sites

Q4 2026 → Phase 2 cutovers, Waves 3 & 4

Q1 2027 → As-built documentation complete

July 2027 → 🏁 Program Complete

CLOSING STATEMENT:

"This is a complex multi-phase program across 129 substations on critical utility infrastructure. The team has executed Phase 1 construction flawlessly — 31 sites, on time, on budget. We have one active blocker being resolved. The recovery plan is detailed, ownership is clear, and I'm confident in the June 2026 Phase 1 close. Happy to take any questions."

Confident tone. End on the plan, not the problem. Pause after closing — let them ask questions.

PRJ13797  ·  JMUX Replacement  ·  Jay Gunaratne  ·  March 2026  ·  PSEG Long Island  ·  CONFIDENTIAL