## Slide 1
JMUX Replacement Program
CIO Briefing | Phase 1 Complete · Phase 2 Underway · Path to Completion
PRJ13797 | Program Manager: Dhananjaya Gunaratne | March 12, 2026
PSEG Long Island | IT Infrastructure
CONFIDENTIAL

## Slide 2
Executive Summary
JMUX Replacement Program — Status as of March 12, 2026
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
✅ Phase 1 COMPLETE
31 substations cutover to MPLS All Wave 1 & Wave 2 cutovers done NSP installed at Melville & Hicksville SSP & CMDB documentation approved Minor close-outs in progress (Hicksville cabling, OTDR)
🟡 Phase 2 IN PROGRESS
36-site engineering design underway Site surveys completed during Phase 1 Burns & McDonnell issuing IFRs & IFCs Nokia Phase 2 equipment delivered 2/19 Schedule: Yellow (2.5-wk delay, recovering)
📋 CIO Actions REQUIRED
Awareness: Schedule is yellow, recovery plan in place Approval: Confirm Phase 2 vendor engagement continues Decision: Resource support for SSP/security reviews Support: Crown Castle fiber issue at Hicksville

## Slide 3
Phase 1 Accomplishments
31 Substations | Complete
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
KEY ACCOMPLISHMENTS
All 31 substation sites installed & commissioned
Wave 1 cutover (12/8–12/18/25) — non-tie sites complete
Wave 2 cutover (1/6–1/8/26) — tie sites complete
CWDM cutover complete at Hicksville & ACC
Nokia NSP racked & powered at Melville & Hicksville
Staging completed at Hawkeye Warehouse — 9/29/25
SSP documentation approved by security team
CMDB inventory updated & confirmed — 2/24/26
Phase 2 site surveys completed during Phase 1 (ahead of schedule)
7 additional nodes added to complete Ring 1 & Ring 2
PHASE 1 AT A GLANCE
31 / 31
Sites Complete
100%
Cutover Done
2
Network Rings Closed
Sept 2025
Staging Complete
Jan 2026
Final Cutover
$4.44M
Spent to Date

## Slide 4
Phase 2 Status
36 Sites | Engineering Design Underway | Burns & McDonnell SOW: $1.37M
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Site Surveys
COMPLETE
Nokia Equip. Delivery
COMPLETE
IFR Design (B&McD)
IN PROGRESS
IFC Design
IN PROGRESS
Construction
NOT STARTED
Cutover
NOT STARTED
Milestone
Contract Date
Status
Notes
Phase 1 Staging Support
8/22/2025
✅ Complete
$57,300 paid
Phase 1 Construction Coordinator
Aug 2025–Jan 2026
✅ Complete
$368,100 — monthly invoiced
Substation Site Surveys (Phase 2)
2/27/2026
✅ Complete
Completed during Phase 1 — ahead of schedule
MPLS Network Node Design — IFR
Wave 1: 2/23/26
🟡 In Progress
B&McD issuing IFRs; PSEG LI review 2-wk window
MPLS Network Node Design — IFC
Wave 1: 3/23/26
⏳ Upcoming
IFC follows PSEG LI review & comment
Construction & Installation
Aug–Dec 2026
⏳ Not Started
Pending IFC completion

## Slide 5
Schedule Status
Overall: 🟡 Yellow | Recovery Plan in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Root Causes:
• SSP documentation delays (security review queue)
• CMDB update coordination time
• Inclement weather affecting field work
• Crown Castle fiber issue at Hicksville (OTDR testing pending)
Recovery Actions:
All approvals received. Remaining Phase 1 close-out is remote configuration — no physical site access needed. Phase 2 IFR/IFC design on track.
PROGRAM TIMELINE
Apr 2024 — Project Start
Oct 2024 — RFP Award & SOW Executed
Jan 2025 — Phase 1 Detailed Design Start
Sep 2025 — Staging Complete (Hawkeye)
Oct 2025 — Phase 1 Construction Start
Dec 2025 – Jan 2026 — Wave 1 & 2 Cutovers Complete
Feb 2026 — Nokia Phase 2 Equipment Delivered
Mar 2026 — Phase 2 IFR Design in Progress ◀ NOW
Mar–Jul 2026 — Phase 2 IFC Design & Review
Aug–Dec 2026 — Phase 2 Construction
Jul 2027 — Program Completion (Target)
SCHEDULE PERFORMANCE INDEX (SPI)
0.00
0.50
0.75
1.00
1.25
1.50
2.00
0.75
Current Month
1.00
Last Month
●
Below 0.70 — Critical
●
0.70–0.90 — Yellow
●
0.90–1.10 — On Track
●
Above 1.10 — Ahead
━━ Current Month: 0.75 (Orange)
╌╌ Last Month: 1.00 (Gray)

## Slide 6
Financial Status
Program Budget: $6,600,000 | Status: ON BUDGET ✅
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
$6,600,000
Total URB Approved Budget
$4,437,070
Spent To Date (67%)
$2,162,930
Estimate to Complete
$0
Over / Under Budget
Budget Utilization
67% Spent
33% Remaining
PO #
Supplier
PO Value
Invoiced
Remaining
Status
7000001429
Burns & McDonnell
$137,500
$49,500
$88,000
🟡 Active
7000001415
Burns & McDonnell
$869,235
$798,665
$70,570
🟡 Active
7000002099
Burns & McDonnell (Ph2)
$1,370,040
$388,740
$981,300
🟡 Active
7000001857
Nokia of America
$1,899,030
$532,525
$1,366,505
🟡 Active
7000002054
Elecnor Hawkeye
$402,793
$257,619
$145,174
🟡 Active
7000001175
Nokia of America
$190,575
$190,575
$0
✅ Paid in Full
7000001748
Presidio Networked Sol.
$40,955
$40,955
$0
✅ Paid in Full
7000001767
Graybar Electric
$24,759
$24,759
$0
✅ Paid in Full

## Slide 7
Risks & Issues
RAG Status | Active Risks & Issues | Mitigations in Place
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
RED — High Impact
AMBER — Medium
GREEN — Low / Resolved
⚠ RISKS
🔧 ISSUES
RED
Legacy Equipment Fragility
JMUX equipment 25+ yrs old. Faulty connectors, brittle fiber — potential for unplanned outage during Phase 2 cutovers.
↳ Mitigation: Careful cutover sequencing. B&McD on-site technical support for all Phase 2 cutovers.
RED
2026 Budget Overrun
Known 2026 ETC of $2.92M exceeds $2.6M budget by $1.17M (-45%). Hawkeye Phase 2 SOW ($632K) and Nokia PO ($753K) are primary drivers.
↳ Mitigation: Budget augmentation request to CIO. Phase 3 spend timing may be deferred to 2027 to reduce 2026 exposure.
AMBER
Phase 2 Schedule Slippage
IFR/IFC design cycle leaves limited buffer. SPI currently at 0.75 (down from 1.00 last month).
↳ Mitigation: Phase 2 surveys completed early. B&McD running concurrent site designs. Weekly tracking calls.
AMBER
Substation Access / Weather Delays
Escort availability, weather, or other site conflicts can delay field work and trigger Hawkeye cost impacts.
↳ Mitigation: Verify availability weekly before mobilizing. Adjust site sequencing if specific sites are inaccessible.
AMBER
Hicksville Cabling (NSP)
Cat 6 cables ordered. Hawkeye completing cabling for Nokia NSP at Hicksville.
↳ Target: 3/3/2026
AMBER
OTDR Testing — Hicksville Fiber
Low dB levels on fiber at Hicksville. Crown Castle may be the root cause. OTDR testing planned.
↳ Target: 3/3–3/4/2026
AMBER
Remote Access to Phase 2 Nodes
Remote connectivity to NSP nodes at Hicksville & Melville required before router config can begin.
↳ Target: In Progress
GREEN
Phase 1 SSP / Security Reviews
Architecture review, security assessment, and compliance readiness all approved by SSP team.
↳ Target: Completed 2/10/2026
GREEN
CMDB Inventory Update
CMDB inventory spreadsheet completed and confirmed in database.
↳ Target: Completed 2/24/2026

## Slide 8
CIO Actions Required
3 Items for Decision or Awareness
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
1
AWARENESS
Schedule Recovery — Yellow Status
Context: Phase 1 experienced a 2.5-week delay due to SSP documentation processing and inclement weather. The SPI stands at 0.75 for February.
Detail: Recovery plan is in place. Remaining Phase 1 close-out items are remote (no site access required). Phase 2 engineering is running concurrently. Overall program target end date remains July 2027.
➤ No action required — for awareness only.
2
APPROVAL
Continue Phase 2 Vendor Engagement
Context: Burns & McDonnell Phase 2 SOW ($1.37M) is active. IFR design has commenced for 36 sites. Nokia equipment delivered to staging. Phase 2 is on track to hit IFC milestones per SOW schedule.
Detail: Confirm continued engagement of B&McD and Elecnor Hawkeye for Phase 2 construction support as design packages are issued.
➤ Approval requested to proceed with Phase 2 construction mobilization once IFC packages are complete (expected Q2 2026).
3
SUPPORT
Crown Castle Fiber Issue — Hicksville
Context: OTDR testing revealed low dB levels on fiber at Hicksville substation. This may be a Crown Castle infrastructure issue outside PSEG LI's control.
Detail: OTDR testing was scheduled for 3/3–3/4/2026. If confirmed as Crown Castle issue, formal escalation to Crown Castle will be required, which may impact Phase 2 schedule at that site.
➤ Request CIO support if vendor escalation to Crown Castle is needed to expedite resolution.

## Slide 9
Next Steps & Path to Completion
March 2026 — July 2027
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
IMMEDIATE (Next 30 Days)
Mar 3
Hawkeye completes Cat 6 cabling for NSP at Hicksville
Mar 3–4
OTDR testing at Hicksville — resolve Crown Castle fiber issue
Mar 2026
Remote router configuration begins (Layer 1-3 setup)
Mar 2026
B&McD continues Wave 1 IFR submissions (Far Rockaway, Valley Stream, Cedarhurst)
Mar 9
PSEG LI review window opens for Wave 1 IFR packages
Mar 23
Wave 1 IFC target completion
Ongoing
Weekly status calls with B&McD; monthly schedule updates
PATH TO COMPLETION
Q1 2026
Phase 1 close-out & Phase 2 IFR design
Q2 2026
Phase 2 IFC completion (all 36 sites)
Q2–Q3 2026
Phase 2 construction mobilization
Q3–Q4 2026
Phase 2 installations at all 36 sites
Q4 2026
Phase 2 cutovers — Waves 3 & 4
Q1 2027
As-built documentation complete
Jul 2027
🏁 Program Complete

## Slide 10
Goals & Objectives
JMUX Replacement: Private Field Area Network
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Modernize PSEG LI's substation communications by replacing legacy JMUX with MPLS nodes to deliver a reliable, scalable, and future-ready network.
🔧 Engineering Services
Detailed site surveys at all substations
Rack elevations, power design & supplemental docs
As-builts for each completed site
All substations aligned to PSEG LI standards
Phase 1 As-Builts: BMcD in progress
Phase 2 surveys: Completed during Phase 1
Phase 2 IFRs: Being issued by BMcD
Phase 2 IFCs: In progress
📦 Procurement & Staging
All Phase 1 equipment purchased by PSEG LI
Equipment shipped & delivered to Hawkeye staging facility
Phase 1 staging completed: Sept 29, 2025
Nokia Phase 2 equipment delivered: Feb 19, 2026
Equipment safely stored at Hawkeye warehouse
🏗 Construction & Installation
BMcD on-site coordination throughout Phase 1
Technical support & commissioning oversight
31/31 Phase 1 sites installed & commissioned
SSP documentation: Submitted & approved
Remote connectivity to nodes: In progress
Phase 2 construction: Pending IFC completion
PROGRAM SCOPE SUMMARY
Phase
Total Substations
MPLS Sites
DF RTU Sites
Radio Shelter Sites
Nokia MPLS Nodes
Phase 1
49
26
17
6
31
Phase 2
45
26
12
7
26
Phase 3
35
22
7
6
22
TOTAL
129
74
36
19
79

## Slide 11
2026 Financial Exposure
Full picture including Hawkeye Phase 2 SOW ($632K) — Updated March 12, 2026
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
$2,600,000
2026 Capital Budget
$851,055
Spent to Date (33%)
$2,921,137
Total ETC (Known)
-$1,172,192 (-45%)
2026 Projected Variance
2026 Budget Utilization & Exposure
▲ Spent: $851K (33%)
▲ ETC: $2.92M — EXCEEDS BUDGET by $1.17M
Budget $2.6M
⚠ 2026 COST DRIVERS
Burns & McDonnell Phase 2 SOW (reduced)
$859,520
Burns & McDonnell Phase 3 (2026 portion)
$588,011
Nokia PO 7000001857 (added March 2026)
$753,000
Hawkeye Phase 2 Construction (36 sites)
$632,303
Phase 1 Outstanding WDs (WD8-13)
$88,303
TOTAL KNOWN ETC
$2,921,137
📅 HAWKEYE PH2 MILESTONE SCHEDULE
WD #8–13 Outstanding WDs
In Progress
$88,303
M1 Services & Deliverables
3/30/2026
$99,000
M2 Services & Deliverables
4/30/2026
$89,000
M3 Services & Deliverables
5/30/2026
$89,000
M3 Services & Deliverables
6/30/2026
$89,000
M4 Services & Deliverables
8/30/2026
$89,000
M5 Decommission Phase 2 Equip
TBD
$89,000
TOTAL
$632,303
⚠ Note: 2026 ETC of $2.92M exceeds remaining budget of $1.75M by $1.17M. CIO approval required for budget augmentation. Phase 3 2026 exposure ($588K) pending confirmation.

## Slide 12
Phase 2 & 3 Master Schedule
Burns & McDonnell | Live MPP Data | As of March 12, 2026
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Jan 26
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan 27
Feb
▼TODAY
PHASE 2 — Engineering & Construction
9%
PO Received
100%
Construction Support Coordinator
75%
Site Surveys (Ph2 — 36 sites)
100%
MPLS Node Design (all 36 sites)
4%
Wave 1: Far Rockaway/Valley Stm/Cedarhurst
50%
Wave 2: Hewlett / Green Acres / Barrett
Wave 3: Whiteside/Baldwin/Hauppauge
Wave 4: Babylon/Sterling/MacArthur/Sayvill
Wave 5: Bayport/S.Farmingdale/Patchogue
DO Offices / Hicksville / Ruland / ACC
Staging & Testing
Construction & Installation (Hawkeye)
Site Acceptance Testing
Cutover (Phase 2)
PHASE 3 — Engineering Design
PO Received
Site Surveys (Phase 3 — 35 sites)
MPLS Node Design (Phase 3)
■ Complete
■ In Progress
■ Planned
■ Construction/Cutover
▼ Today 3/12/26

## Slide 13
Vendor Summary
3 Active Vendors | Roles, Contracts & Status as of March 12, 2026
PSEG Long Island | JMUX Replacement Program | Confidential | March 2026
Burns & McDonnell EGS, P.C.
Network Engineering & Design
AMBER
Contract: RITM336401 | MA00007834
Value: $1,370,040 | Start: July 28, 2025
Target Completion: September 2026
Scope of Work:
• MPLS network node design — 36 sites (IFR → IFC → As-Built)
• Phase 1 Staging Support (complete)
• Phase 1 Construction Support Coordinator (Aug 2025–Jan 2026)
• Phase 2 Substation Site Surveys (36 sites, complete 2/27/26)
• Weekly status calls & schedule management
Milestone Payments:
M1 Staging Support: $57,300 ✓ Complete
M2 Construction Coord: $368,100 (monthly, in progress)
M3 Site Surveys: $86,040 ✓ Complete
M4 MPLS Node Design: $858,600 (in progress, 4%)
Key Contact:
Alex Lenox (PM) | alenox@burnsmcd.com | (636) 248-0351
Status: Design 4% complete. SPI 0.75.
Elecnor Hawkeye LLC
Construction & Installation
AMBER
Contract: Phase 2 SOW — Dated March 9, 2026
Value: $632,303 | Start: March 9, 2026
Target Completion: Late 2026 (post IFC)
Scope of Work:
• Pre-site visit, installation, demo equipment & staging (36 sites)
• WD #8: Fiber testing Elwood/Northport + 7 patch panels $8,229
• WD #10: Oakwood/Northport patch panel install $15,089
• WD #11: Fiber & CAT5E supply/install Hicksville $60,070
• WD #12: Fiber enclosures Hicksville $2,515
• WD #13: Fiber testing Syosset/Hicksville $2,400
Milestone Payments:
M1: $99,000 due 3/30/2026 ← IMMINENT
M2: $89,000 due 4/30/2026
M3: $89,000 due 5/30/2026 & 6/30/2026
M4: $89,000 due 8/30/2026 | M5 Decommission: $89,000
Key Contact:
Robert M. Kenney (Electrical Supervisor) | (631) 291-2166
Status: WDs in progress. M1 due 3/30.
Nokia
Network Equipment Supply
AMBER
Contract: PO 7000001857
Value: $1,900,000+ | Start: 2025
Target Completion: Equipment Delivered Feb 2026
Scope of Work:
• Supply Nokia 7705 SAR routers for all Phase 2 sites
• Equipment staged and delivered February 2026 ✓
• NSP (Network Services Platform) software & licensing
• Firmware synchronized on all CSM cards
PO Details:
PO 7000001857: $753,000 (added March 2026)
Previous PO total: ~$1,147,000
Total Nokia exposure: ~$1,900,000
Current Issues:
NSP remote access to Hicksville & Melville nodes pending
Cat 6 cabling for NSP at Hicksville in progress (Hawkeye)
Key Contact:
Nokia Account Team | PSEG Long Island
Status: Equipment delivered. NSP access pending.