## Project Financial Summary
PRJ13797 — JMUX REPLACEMENT ¦ PROJECT FINANCIAL SUMMARY BY CONTRACTOR
All Phases (1 · 2 · 3) ¦ Source: Chad Controller Workbook + SOW + Vic call May 18 2026 ¦ ★PCR = pending PCR approval
CONTRACTOR | SCOPE / LINE ITEM | 2025 | 2026 | 2027 | TOTAL
MATERIAL
| Nokia MPLS Equipment (SAR-8 nodes) | 1412400 | 733293 | 963000 | 3108693
| CWDM Cards |  | 25000 | 20000 | 45000
| Other (Power Supplies / Connectors) |  | 30000 | 10000 | 40000
MATERIAL TOTAL |  | 1412400 | 788293 | 993000 | 3193693
B&M
| PM Service (Alex Lennox $5,500/mo) | 66000 | 66000 | 22000 | 154000
| Site Surveys — Phase 1 (complete ✅) | 86040 |  |  | 86040
Site Surveys — Phase 2
| Site Surveys — Phase 3 (31 sites) ★PCR |  |  | 86000 | 86000
| Staging Support | 51250 |  |  | 51250
| Node Design IFR+IFC (Phase 1+2) | 601020 | 214668 |  | 815688
| Node Design IFR+IFC (Phase 3) ★PCR |  |  | 450000 | 450000
| Node Design As-Builts (Ph1+2) |  | 42912 |  | 42912
| Node Design As-Builts (Phase 3) |  |  | 37200 | 37200
| Construction Support Ph1 CSC ✅ | 368100 |  |  | 368100
| Construction Support Ph2 CSC |  | 382824 |  | 382824
| Construction Support Ph3 CSC ★PCR |  |  | 264000 | 264000
| Phase 3 MPLS Design (accelerated) ★PCR |  | 360000 |  | 360000
B&M TOTAL |  | 1172410 | 1066404 | 859200 | 3098014
HAWKEYE
| Implementation — Phase 1 (SOW complete ✅) | 402793 |  |  | 402793
| Implementation — Phase 2 |  | 361476 |  | 361476
| Implementation — Phase 3 ★PCR |  |  | 320000 | 320000
| Decommissioning — ALL phases (Phase 3 only) |  |  | 141351 | 141351
| WD#8 Fiber Testing + Patch Panels |  | 8229 |  | 8229
HAWKEYE TOTAL |  | 402793 | 369705 | 461351 | 1233849
PAR (Ext. Relay)
| Engineering Design ★PCR (200hrs×6×$200/hr) |  | 240000 |  | 240000
| Installation & Cutover ★PCR (~1,298hrs×$200/hr) |  | 259500 |  | 259500
| Materials ★PCR (cables, connectors) |  | 30000 |  | 30000
PAR TOTAL ★PCR★ |  |  | 529500 |  | 529500
PM / CONTROLS
| PM — Dhananjaya Gunaratne (Hermitage) |  | 174000 | 58000 | 232000
| PM — Ahsan Khawaja (Hermitage) |  | 257619 |  | 257619
| Controller — Chad Boyett (ComTec) | 67200 | 100800 | 33600 | 201600
| Scheduler — Umair Mohammed (ComTec) | 54160 | 67040 | 13400 | 134600
| Scheduler — Farouk Adelekan (ComTec) |  | 20000 | 6600 | 26600
| PQA Lead — Edward Schwartz (Hermitage) |  | 30000 | 5000 | 35000
PM / CONTROLS TOTAL |  | 121360 | 649459 | 116600 | 887419
INTERNAL LABOR
| PSEG Internal Labor (all named resources) | 82421 | 154989 | 60000 | 297410
| Lee Blackman — Sr. Network Architect (Cognizant) |  | 86400 |  | 86400
INTERNAL LABOR TOTAL |  | 82421 | 241389 | 60000 | 383810
PQA / ASSESSMENTS
| PQA Audit — Cognizant / EPMO | 56330 | 40000 | 10000 | 106330
| Assessments (PSEG overhead) | 19172 | 72737 | 20000 | 111909
PQA / ASSESSMENTS TOTAL |  | 75502 | 112737 | 30000 | 218239
TRC — Cyber Security
| Raju Khedkar — Security Architect | 3726 | 30000 | 5000 | 38726
TRC TOTAL |  | 3726 | 30000 | 5000 | 38726
★ GRAND TOTAL — ALL CONTRACTORS (excl. 2024 actuals) |  | 3270612 | 3787487 | 2525151 | 9583250
CP Budget: 2025 $3,250,000 ¦ 2026 $2,600,000 ¦ 2027 $1,000,000 ¦ ★PCR items pending: PAR $529,500 + Ph3 MPLS $360,000 + Ph3 CSC $264,000 + Ph3 Surveys $86,000 = ~$1.24M
Decommissioning ALL phases in Phase 3 only ¦ Phase 3 site surveys stay in Phase 3 ¦ Martin Gately departed — 2026 forecast $0