## Financial Summary v5
PRJ13797 — JMUX REPLACEMENT ¦ PROJECT FINANCIAL SUMMARY v5 ¦ URB FUNDING REQUEST ¦ May 19 2026
Sources: B&M SOW Ph1 ($306K) + Ph2 ($1.37M) ¦ Hawkeye SOW Ph1 ($402K) + Ph2 ($400K) ¦ Chad Workbook (EAC $7.14M, actuals $5.91M) ¦ Graybar POs ($241K Ph1) ¦ Vic call May 18 2026 ¦ ★PCR = pending
# | CONTRACTOR | STEP / DELIVERABLE (SOW-sourced) | P1 | P2 | P3 | 2025 | 2026 | 2027 | TOTAL | SOURCE
| ★ ACTUALS TO DATE (from Chad's workbook): 2024 = $741,206 ¦ 2025 = $3,130,120 ¦ Jan–Apr 2026 = $2,037,496 ¦ TOTAL SPENT: $5,908,822 | [8 empty] | Chad Workbook
1 | MATERIAL (Nokia Equipment)
2 | Nokia / Presidio | Nokia SAR-8 nodes + licenses + SFPs + CSM cards Ph1: 39 nodes COMPLETE ✅ ¦ Ph2: 36 nodes ¦ Ph3: ~31 nodes | ✓ | ✓ | ✓ | 1412400 | 733293 | 963000 | 3108693 | Nokia PO 7000001857 + 5000059268
| MATERIAL SUBTOTAL |  |  |  |  | 1412400 | 733293 | 963000 | 3108693
3 | CABLES & CONNECTORS (Graybar Electric + other)
4 | Graybar Electric | Phase 1 — Cables, Connectors, Fiber Jumpers COMPLETE ✅ Fiber patch cords, CAT6, serial cables (RJ45→DB25), conduit, fittings. Actual from 4 POs: $24,759 + $115,004 + $55,287 + $46,023 = $241,073 ~$6,181/site for 39 sites | ✓ |  |  | 241073 |  |  | 241073 | Graybar POs 7000001767/1811/1841/2119
5 | Graybar Electric | Phase 2 — Cables, Connectors, Fiber Jumpers (36 sites) Scope: fiber patch cords (2 per site per Hawkeye SOW), CAT6 (2 per site), serial patch cables (1 per site), 4-wire VF (1 per site), conduit + fittings. Estimate: $6,181/site × 36 sites = $222,529 (PO TBD) |  | ✓ |  |  | 222529 |  | 222529 | Estimate: Graybar Ph1 rate × 36 sites
6 | Graybar Electric | Phase 3 — Cables, Connectors, Fiber Jumpers (31 sites) ★PCR Same cable types. Estimate: $6,181/site × 31 sites = $191,622 (PO TBD) |  |  | ✓ |  |  | 191622 | 191622 | Estimate: Graybar Ph1 rate × 31 sites
7 | Nokia / Presidio | CWDM Cards (mux/demux per site per IFC) Ordered per IFC release. Ph2 $25K + Ph3 $20K. | ✓ | ✓ | ✓ |  | 25000 | 20000 | 45000 | Chad forecast
| CABLES & CONNECTORS SUBTOTAL |  |  |  |  | 241073 | 247529 | 211622 | 700224
8 | B&M (Burns & McDonnell) — Engineering & PM ¦ Ph1 SOW $306K + Ph2 SOW $1,370,040
9 | B&M — Alex Lennox | Step 1: PM Service $5,500/month Ph1 Sep 2024–Jan 2026 (17 mo) + Ph2 Feb–Sep 2026 (8 mo) + Ph3 2027 (4 mo) Scope: weekly status calls, meeting minutes, schedule tracking, PSEG PDLC compliance. | ✓ | ✓ | ✓ | 66000 | 66000 | 22000 | 154000 | Ph1 SOW M4 $154K + Ph2 SOW PO 316200
10 | B&M — Phase 1 SI work | Step 2: Ph1 Systems Integrator work COMPLETE ✅ M1 Network equipment specs + vendor scope: $36,250 M2 Vendor RFP: $16,250 M3 Site surveys (134 sites): $99,800 All paid 2024–2025. | ✓ |  |  | 152300 |  |  | 152300 | Ph1 SOW total $306K (paid ✅)
11 | B&M — Ethan Koch | Step 3: Site Surveys Ph2 COMPLETE ✅ ($86,040 — SOW M3) Visual inspection at 36 sites. Digital photos + video. Feeds IFR design. Completed Feb 27 2026. Paid. |  | ✓ |  |  | 86040 |  | 86040 | Ph2 SOW CPS M3 = $86,040 (paid ✅)
12 | B&M — Ethan Koch | Step 4: Site Surveys Ph3 ★PCR (31 sites, $86,000 est.) Starts Aug 2026 (tied to Ph2 staging start). PSEG escort required. |  |  | ✓ |  |  | 86000 | 86000 | Estimate ~$86K per Ph2 rate
13 | B&M — Ethan Koch | Step 5a: Staging Support Ph1 COMPLETE ✅ (★ 1 week, SOW M1 = $57,300) Card slotting plan, fiber connectivity matrix, chassis labeling. Staging test plan: firmware, IGP/BGP/BFD, SyncE, NMS, VPRN/Epipe/Cpipe, failure tests. | ✓ |  |  | 57300 |  |  | 57300 | Ph2 SOW CPS M1 = $57,300 (paid ✅)
14 | B&M — Ethan Koch | Step 5b: Staging Support Ph2 (1 week, $25,625) Same scope. 36 nodes. Jul 2026. ★ 1 WEEK only — SOW states 2 weeks but Ph1 actual was 1 week. |  | ✓ |  |  | 25625 |  | 25625 | Prorated from Ph1 $57,300 × 36/39 sites
15 | B&M — Ethan Koch | Step 5c: Staging Support Ph3 ★PCR (1 week, $25,625) |  |  | ✓ |  |  | 25625 | 25625 | Estimate per Ph2 rate
16 | B&M — Nick Cianciolo | Step 6a: MPLS Node Design IFR — Ph1 COMPLETE ✅ $16,695/site × 36 sites (Ph1) = $601,020. Includes: floor plan, rack elevation, power one-line, cable schedule, BOM, site-specific scope of work. | ✓ |  |  | 601020 |  |  | 601020 | Ph2 SOW App D: $16,695/site (paid ✅)
17 | B&M — Nick Cianciolo | Step 6b: MPLS Node Design IFR — Ph2 (rolling Feb–Jun 29 2026) $16,695/site × 36 sites = $601,020 Per site: floor plan, rack elev, power one-line, cable schedule, BOM, scope of work. PSEG has 10 business days to review each IFR. Final IFR deadline: Jun 29 2026. |  | ✓ |  |  | 601020 |  | 601020 | Ph2 SOW App D: $16,695 × 36 sites
18 | B&M — Nick Cianciolo | Step 6c: MPLS Node Design IFC — Ph2 (final IFC Jul 13 2026) $5,963/site × 36 sites = $214,668 PE-sealed, issued for construction. Triggers Hawkeye cable orders + construction. |  | ✓ |  |  | 214668 |  | 214668 | Ph2 SOW App D: $5,963 × 36 sites
19 | B&M — Nick Cianciolo | Step 6d: MPLS Node Design IFR+IFC — Ph3 ★PCR (31 sites) $23,850/site × 31 = $739,350 total ¦ IFR $517,545 + IFC $184,953 + As-Built $36,952 Ph3 design accelerated into Ph2 window per recovery plan. |  |  | ✓ |  |  | 450000 | 450000 | Ph2 SOW App D rate × 31 sites ★PCR
20 | B&M — Nick Cianciolo | Step 7: AS-BUILT Drawings — Ph1+2 ($1,192/site × 36 = $42,912) Issued 1 month after construction complete. Red-line mark-up record drawings. | ✓ | ✓ |  |  | 42912 |  | 42912 | Ph2 SOW App D: $1,192 × 36 sites
21 | B&M | Step 7b: AS-BUILT Drawings — Ph3 ★PCR ($1,192 × 31 = $36,952) |  |  | ✓ |  |  | 36952 | 36952 | Ph2 SOW rate × 31 sites ★PCR
22 | B&M — Ethan Koch | Step 8a: Construction Support Coordinator — Ph1 COMPLETE ✅ (SOW CPS M2) On-site daily at each substation. $61,350/mo × 6 mo (Aug 2025–Jan 2026) = $368,100 Scope: field coordination, daily reports, RFI log, cutover support, commissioning. | ✓ |  |  | 368100 |  |  | 368100 | Ph2 SOW CPS M2 = $368,100 (paid ✅)
23 | B&M — Ethan Koch | Step 8b: Construction Support Coordinator — Ph2 $61,350/mo × 6 mo (Aug–Jan 2027) = $368,100 (incl in 2026 $382,824 forecast) Pre-construction planning, on-site coordination, RFI management, daily field reports to PSEG PM, cutover/commissioning support, Go-Live verification. |  | ✓ |  |  | 382824 |  | 382824 | Ph2 SOW M2 invoiced monthly
24 | B&M — Ethan Koch | Step 8c: Construction Support Coordinator — Ph3 ★PCR ~$264,000 est. (~4 months × $61,350). |  |  | ✓ |  |  | 264000 | 264000 | Est. $61,350/mo × 4 mo ★PCR
25 | B&M | Step 9: Ph3 MPLS Detail Design (accelerated into Ph2) ★PCR 31-site full design pulled forward 2027→2026 to recover 5-month schedule. $360,000 est. |  | ✓ |  |  | 360000 |  | 360000 | PCR recovery plan ★PCR
| B&M SUBTOTAL |  |  |  |  | 1244720 | 1778089 | 884577 | 3907386
26 | HAWKEYE (Elecnor Hawkeye) — Ph1 SOW $402,793 ¦ Ph2 SOW $400,680
27 | Hawkeye — Vinny M. | Step 1: Pre-Construction Survey (per site, after each IFC issued) Ph1 complete ✅ ¦ Ph2: measures cable runs, confirms rack location, photos existing JMUX, generates site-specific BOM. Per Hawkeye SOW M1 = $100,170 Cannot order cables until survey done. | ✓ | ✓ | ✓ |  | 50085 | 50085 | 100170 | Hawkeye Ph2 SOW M1 = $100,170
28 | Hawkeye | Step 2a: Staging — Ph1 COMPLETE ✅ (★ 1 WEEK — Ph2 SOW M-Ph0 = $100,170) Rack + slot Nokia SAR-8 nodes per B&M card plan, install SFPs, power-on, execute B&M test plan (connectivity, firmware, BGP, BFD, SyncE, VPRN/Epipe/Cpipe, link/node failure), label chassis. | ✓ |  |  | 100170 |  |  | 100170 | Hawkeye Ph2 SOW M-Ph0 = $100,170 (paid ✅)
29 | Hawkeye | Step 2b: Staging — Ph2 (★ 1 WEEK, Jul–Aug 2026 — SOW M-Ph0-Ph2 = $100,170) Same scope. 36 nodes. B&M provides card-slotting + connectivity matrix. |  | ✓ |  |  | 100170 |  | 100170 | Hawkeye Ph2 SOW M-Ph0 = $100,170
30 | Hawkeye | Step 2c: Staging — Ph3 ★PCR (1 week, 31 nodes, $100,170 est.) |  |  | ✓ |  |  | 100170 | 100170 | Estimate per Ph2 SOW rate ★PCR
31 | Hawkeye — 3 visits/site | Step 3a: Substation Installation — Ph1 COMPLETE ✅ (SOW M2 = $302,623) Visit 1: Deliver, rack SAR-8, run conduit, pull cables, install Eltek PSU Visit 2: Terminate fiber (2 SM patch cords per site), install CWDM, connect serial patch panel, terminate CAT6, 4-wire VF, install ground bar Visit 3: Energize, basic checklist, notify B&M CSC + relay team | ✓ |  |  | 302623 |  |  | 302623 | Hawkeye Ph1 PO 7000002054 = $402,793
32 | Hawkeye — 3 visits/site | Step 3b: Substation Installation — Ph2 (SOW M2 = $80,136) Same 3-visit scope. 36 sites. Construction Aug 5 – Sep 28 2026. Install: Nokia SAR-8, CWDM, Eltek PSU, RS-232 patch panel, fiber, CAT6, serial, 4-wire VF, ground bar, conduit, inner duct. Record docs + checkout checklist per site. |  | ✓ |  |  | 80136 |  | 80136 | Hawkeye Ph2 SOW M2 = $80,136
33 | Hawkeye — 3 visits/site | Step 3c: Substation Installation — Ph3 ★PCR Same scope. ~31 sites. 2027. ~$220,000 est. |  |  | ✓ |  |  | 220000 | 220000 | Est. per Ph2 SOW rate × 31 sites ★PCR
34 | Hawkeye | Step 4a: Go-Live Sign-Off — Ph2 (SOW M4 = $80,136) After relay team completes RTU cutover: Hawkeye confirms all Nokia circuits live, no JMUX traffic, B&M CSC punch list resolved. PSEG formal acceptance. |  | ✓ |  |  | 80136 |  | 80136 | Hawkeye Ph2 SOW M4 = $80,136
35 | Hawkeye | Step 4b: Go-Live Sign-Off — Ph3 ★PCR (~$100,000 est.) |  |  | ✓ |  |  | 100000 | 100000 | Estimate ★PCR
36 | Hawkeye | Step 5: Decommissioning — ALL phases (Ph3 window, SOW M6 = $40,068 Ph2 only) After ALL phases live on Nokia. Per site: de-rack JMUX, remove cabling, palletize + ship to PSEG warehouse, restore substation to pre-JMUX condition. 134 total sites (39+36+31+shelters). $141,351 total est. |  |  | ✓ |  |  | 141351 | 141351 | Hawkeye Ph2 SOW M6=$40,068 + Ph1/Ph3 est.
37 | Hawkeye | WD#8 Fiber Testing (Elwood to Northport + 7 patch panels) | ✓ |  |  |  | 8229 |  | 8229 | PO 7000009182 = $8,229
| HAWKEYE SUBTOTAL |  |  |  |  | 402793 | 318756 | 611606 | 1333155
PAR | PAR (Phase Angle Regulator) ★ NEW SCOPE — PCR REQUIRED ¦ 6 Sites
a | Nokia / Presidio | Step 1: Iniven RC-30 Equipment (6 units × $8,750 = $52,500) Serial→C37.94 converter. PO placed. 8-wk lead. Delivery ~Jun 2026. Sites: Northport, 5HK Hicksville, Melville, 7Z Lindenhurst, 2H Far Rockaway, 2R Hewlett. |  | ✓ |  |  | 52500 |  | 52500 | PO 7000002695 = $52,500 ★PCR
b | Chak's Team | Step 2: Relay Engineering Design ($240,000 — CONFIRMED Vic May 18) 200 hrs/site × 6 sites × $200/hr. Review PAR protection scheme, design C37.94 interface, relay settings, MOP, NERC-CIP compliance review, coordinate with B&M on IFC drawings. |  | ✓ |  |  | 240000 |  | 240000 | Vic call May 18 2026 ★PCR CONFIRMED
c | Steven Bradley (Relay) | Step 3: Relay Install, Configure & Cutover ($259,500 — CONFIRMED Vic May 18) ~1,298 hrs × $200/hr. Install RC-30, wire to PAR relay contacts, configure C37.94 settings, end-to-end protection test, NERC-CIP commissioning, cutover from legacy serial. ★ Call Steven before Mon May 25. Get names + hours by month. |  | ✓ |  |  | 259500 |  | 259500 | Vic call May 18 2026 ★PCR CONFIRMED
d | Various | Step 4: PAR Materials ($30,000 — CONFIRMED Vic May 18) Custom serial cables, C37.94 connectors, rack hardware across 6 sites. |  | ✓ |  |  | 30000 |  | 30000 | Vic call May 18 2026 ★PCR CONFIRMED
| PAR SUBTOTAL ★PCR★ ($52.5K RC-30 + $240K Eng + $259.5K Install + $30K Materials) |  |  |  |  | 0 | 582000 | 0 | 582000
38 | PM / CONTROLLER / SCHEDULER / O/S ENGINEER
39 | Hermitage — Jay G | PM Dhananjaya Gunaratne — overall delivery, CIO reporting, PCR | ✓ | ✓ | ✓ |  | 174000 | 58000 | 232000 | Chad forecast
40 | Hermitage — Ahsan | PM Ahsan Khawaja — Ph2 support |  | ✓ |  |  | 257619 |  | 257619 | PO 7000001734 = $257,619
41 | ComTec — Chad | Controller Chad Boyett $8,400/mo — SAP, forecast, PCR prep | ✓ | ✓ | ✓ | 67200 | 100800 | 33600 | 201600 | Chad forecast
42 | ComTec — Umair | Scheduler Umair Mohammed $5,416/mo — MS Project, SPI | ✓ | ✓ | ✓ | 54160 | 67040 | 13400 | 134600 | PO 7000001145/2363
43 | ComTec — Farouk | Scheduler Farouk Adelekan |  | ✓ | ✓ |  | 20000 | 6600 | 26600 | PO 5000046818
44 | Hermitage — Ed S | O/S Sr. Engineer Edward Schwartz $2,512/mo | ✓ | ✓ | ✓ |  | 30000 | 5000 | 35000 | PO 7000001998
| PM / CONTROLS SUBTOTAL |  |  |  |  | 121360 | 649459 | 116600 | 887419
45 | INTERNAL LABOR (PSEG + Cognizant)
46 | PSEG — Multiple | PSEG Internal Labor (Rahiq, Brianna, Chok, Lok, Sameer et al.) NSP config, RTU cutovers, BGP, network testing. | ✓ | ✓ | ✓ | 82421 | 154989 | 60000 | 297410 | Chad forecast
47 | Cognizant — Lee | Lee Blackman — Sr. Network Architect $7,200/mo | ✓ | ✓ |  |  | 86400 |  | 86400 | PO 7000002490
48 | PSEG — Steven B | Relay Team Support — Steven Bradley (★ ZERO actuals in SAP) $195K in 2026 forecast. Names + hrs by month needed before Mon May 25. | ✓ | ✓ | ✓ |  | 195000 | 30000 | 225000 | Chad forecast — unverified
| INTERNAL LABOR SUBTOTAL |  |  |  |  | 82421 | 436389 | 90000 | 608810
49 | PQA / ASSESSMENTS / TRC
50 | Cognizant / EPMO | PQA Audit — Margaret Tanner Glover | ✓ | ✓ | ✓ | 56330 | 40000 | 10000 | 106330 | Chad forecast
51 | PSEG | Assessments (PSEG IT overhead ~3.5%) | ✓ | ✓ | ✓ | 19172 | 72737 | 20000 | 111909 | Chad forecast
52 | TRC — Raju K | Raju Khedkar — Cyber Security / NERC-CIP Architect | ✓ | ✓ | ✓ | 3726 | 30000 | 5000 | 38726 | PO 7000001237/2343
| PQA / ASSESSMENTS / TRC SUBTOTAL |  |  |  |  | 79228 | 142737 | 35000 | 256965
★ | GRAND TOTAL — ALL CONTRACTORS (Phases 1 + 2 + 3) |  |  |  |  | 3583995 | 4888252 | 2912405 | 11384652
| APPROVED CP BUDGET (from Chad workbook) |  |  |  |  | 3250000 | 2600000 |  | 6600000 | Chad WB Row 2
| VARIANCE vs BUDGET ⚠ URB FUNDING GAP |  |  |  |  | -333995 | -2288252 | -2912405 | -5525858
B&M SOW Appendix D: IFR $16,695 ¦ IFC $5,963 ¦ As-Built $1,192 ¦ Site Total $23,850/site ¦ 36 Ph2 sites × $23,850 = $858,600 ¦ Hawkeye Ph2 SOW Total = $400,680 ¦ Cable/connector estimate: $6,181/site (Graybar Ph1 actual ÷ 39 sites) ¦ ★PCR items highlighted green ¦ Staging = 1 WEEK (not 2 per SOW) ¦ Ph3 surveys in Phase 3 only
PAR CONFIRMED Vic May 18: RC-30 $52.5K + Chak Eng $240K + Steven B Install $259.5K + Materials $30K = $582K ¦ Steven Bradley: ZERO SAP actuals — call before Mon May 25 ¦ Martin Gately DEPARTED — $0 2026+ ¦ 2027 budget TBD at URB

## URB Ask Summary
PRJ13797 JMUX — URB FUNDING REQUEST ¦ HOW MUCH TO ASK FOR ¦ May 19 2026
Source: Chad workbook actuals + B&M SOW + Hawkeye SOW + Graybar POs + Vic May 18
ITEM | AMOUNT | CUMULATIVE | VS BUDGET | NOTES
WHAT HAS BEEN SPENT (ACTUALS — LOCKED)
Actuals 2024 | 741206 | 741206 | 750000 | Locked in SAP — cannot change
Actuals 2025 | 3130120 | 3871326 | 3250000 | Locked in SAP — cannot change
Actuals Jan–Apr 2026 | 2037496 | 5908822 | 2600000 | Locked in SAP — cannot change
TOTAL SPENT TO DATE | 5908822 | 5908822 | 6600000 | Against $6.6M total budget
WHAT IS STILL TO COME (EAC — remaining work)
ETC May–Dec 2026 (base contracted work) | 2850756 |  |  | B&M IFR/IFC, CSC, Hawkeye install, PM, labor
Cables & Connectors Ph2 (Graybar — NEW) | 222529 |  |  | 36 sites × $6,181/site — Graybar Ph1 rate
PAR Engineering + Install + Materials ★PCR | 582000 |  |  | CONFIRMED Vic May 18: Chak $240K + Steven $259.5K + Mat $30K + RC-30 $52.5K
B&M Ph3 MPLS Design (accelerated) ★PCR | 360000 |  |  | 31-site design pulled into 2026 to recover 5-month schedule
2026 EAC TOTAL | 4888252 |  | 2600000 | vs 2026 budget $2.6M — gap = $2,288,252
2027 Base work (Nokia Ph3, PM, controls, PQA) | 1438036 |  |  | Nokia equipment, PM, controls, decom — contracted
Cables & Connectors Ph3 (Graybar — NEW) ★PCR | 191622 |  |  | 31 sites × $6,181/site
Hawkeye Ph3 install + decom + Go-Live ★PCR | 461351 |  |  | Install 31 sites + decom all 134 + Go-Live sign-off
B&M Ph3 IFR+IFC+As-Builts+Surveys+Staging+CSC ★PCR | 862577 |  |  | $23,850×31 sites + surveys $86K + staging $25.6K + CSC $264K
2027 EAC TOTAL | 2912405 |  |  | No 2027 budget approved yet — entire amount is unfunded
★ FULL PROJECT EAC (ALL PHASES, ALL YEARS)
FULL PROJECT EAC (2024+2025+2026+2027) | 12125858 | 12125858 |  | Phases 1+2+3 complete
APPROVED BUDGET TO DATE | 6600000 | 6600000 | 6600000 | 2024 $750K + 2025 $3.25M + 2026 $2.6M — NO 2027 budget
★★★ URB ASK = $5,525,858 (GAP) + $350,000 contingency = $5,875,858 ★★★ Full project needs $12,125,858 ¦ Approved $6,600,000 ¦ Delta = $5,525,858 RECOMMEND: Ask URB for $5,875,858 in additional funding to complete all 3 phases
WHY ARE WE OVER BUDGET? (explain to URB)
1. PAR scope — not in original estimate | 582000 | Phase Angle Regulator circuit migration discovered during Ph2 surveys. Was $30-40K placeholder in original budget. Actual cost = $582K confirmed Vic May 18.
2. Phase 3 design acceleration | 360000 | 31-site MPLS design pulled from 2027 into 2026 to prevent 5-month schedule slip. Recovery from PAR discovery impact.
3. Phase 3 scope (31 sites, unfunded) | 2912405 | No 2027 budget approved. All Phase 3 work (Nokia $963K, Hawkeye, B&M, cables) = unfunded.
4. Cables & connectors — missed in original | 414151 | Ph2 $222K + Ph3 $192K. Based on Graybar Ph1 actuals ($241K/39 sites = $6,181/site). Not separately budgeted in original estimate.
5. Scope growth — original was 109 sites, now 134 |  | Original scope was smaller. Surveys revealed additional sites and shelters. No cost impact per site (per SOW), but more sites = more work.