## Financial Summary v7
PRJ13797 — JMUX REPLACEMENT ¦ FINANCIAL SUMMARY v7 ¦ Ph1=31 ¦ Ph2=36 ¦ Ph3=31 = 98 sites ¦ May 21 2026
SOURCES: B&M Ph1 SOW $306,300 (Feb 27 2024) ¦ B&M Ph2 SOW $1,370,040 (Aug 13 2025, RITM3364011) — App D: $16,695 IFR / $5,963 IFC / $1,192 As-Built per site ¦ Hawkeye Ph2 SOW $400,680 (Mar 27 2026) ¦ Hawkeye Ph1 PO 7000002054 $402,793 (inc Addendum 1) ¦ Graybar Ph1: 4 POs actual $241,073 — NO Ph2/Ph3 PO ¦ Chad Workbook actuals ¦ Vic May 18 2026 confirmed call ¦ ★PCR = items pending PCR approval
# | CONTRACTOR | STEP / DELIVERABLE | P1 | P2 | P3 | 2025 ACTUAL | 2026 FORECAST | 2027 FORECAST | TOTAL EAC | SOURCE / NOTE
★ ACTUALS TO DATE (Chad Workbook): 2024 = $741,206 ¦ 2025 = $3,130,120 ¦ Jan–Apr 2026 = $2,037,496 ¦ TOTAL SPENT = $5,908,822
1 ─ MATERIALS — Nokia Equipment
1 | Nokia / Presidio | Nokia SAR-8 MPLS Nodes + SFPs + CSM cards + licenses Ph1: 31 sites COMPLETE ✅ ($1,412,400 actual per POs) Ph2: 36 sites — $733,293 per Chad forecast Ph3: 31 sites — estimated at same scale as Ph1 | ✓ | ✓ | ✓ | 1412400 | 733293 | 1412400 | 3558093 | Ph1: POs 7000001857 + 7000001175 + 7000001748 (actual paid) Ph2: Chad workbook forecast Ph3: Estimate = Ph1 rate per site × 31
2 | Presidio | CWDM Cards — per IFC requirements (mux/demux per site) Ph2/Ph3: ongoing as IFCs issued |  | ✓ | ✓ |  | 25000 | 20000 | 45000 | Chad workbook forecast — no separate PO issued yet
MATERIALS SUBTOTAL | [5 empty] | 1412400 | 758293 | 1432400 | 3603093
2 ─ CABLES & CONNECTORS ★ IMPORTANT: Graybar used Ph1 ONLY — Ph2/Ph3 vendor TBD
3 | Graybar Electric | Phase 1 — Cables, Connectors, Fiber Jumpers — 31 sites COMPLETE ✅ 2× SM fiber patch cords, CAT6, serial (RJ45→DB25), 4-wire VF, conduit, fittings. 4 POs: 7000001767 ($24,759) + 7000001811 ($115,004) + 7000001841 ($55,287) + 7000002119 ($46,023) ACTUAL TOTAL: $241,073 | ✓ |  |  | 241073 |  |  | 241073 | ACTUAL — 4 Graybar POs confirmed from PO/Invoice Summary spreadsheet (all Reconciled)
4 | Vendor TBD | Phase 2 — Cables, Connectors, Fiber Jumpers — 36 sites ★ GRAYBAR NOT BEING USED FOR PHASE 2 Same cable types per Hawkeye Ph2 SOW scope (Sec 1.2 v-vi): 2× SM fiber, CAT6, serial, 4-wire VF, conduit. Estimate held: $7,777/site × 36 = $279,956 — VENDOR AND PO TBD |  | ✓ |  |  | 279956 |  | 279956 | ★ ESTIMATE ONLY — no PO, no SOW for Ph2 cables Rate derived from Graybar Ph1 actual ÷ 31 sites Vendor NOT confirmed — Jay to advise who is supplying
5 | Vendor TBD | Phase 3 — Cables, Connectors, Fiber Jumpers — 31 sites ★PCR ★ GRAYBAR NOT BEING USED FOR PHASE 3 Estimate: $7,777/site × 31 = $241,073 — VENDOR AND PO TBD |  |  | ✓ |  |  | 241073 | 241073 | ★ ESTIMATE ONLY — no PO, no SOW for Ph3 cables Vendor NOT confirmed — Jay to advise ★PCR
CABLES & CONNECTORS SUBTOTAL | [5 empty] | 241073 | 279956 | 241073 | 762102
3 ─ BURNS & McDONNELL (B&M) — Ph1 SOW $306,300 ¦ Ph2 SOW $1,370,040 (RITM3364011)
6 | B&M — Alex Lenox | Step 1: Project Management — $5,500/month Ph1 Sep 2024–Jan 2026 (17 mo): $93,500 Ph2 Feb–Sep 2026 (8 mo): $44,000 Ph3 2027 (4 mo est.): $22,000 Weekly status, meeting minutes, schedule, PSEG PDLC compliance | ✓ | ✓ | ✓ | 66000 | 44000 | 22000 | 132000 | SOURCE: B&M Ph1 SOW M4 (PM Services) + B&M Ph2 SOW (RITM3364011) PO 7000001429 PO Invoice Summary: PO 7000001429 — $5,500/invoice confirmed (reconciled invoices)
7 | B&M — Alex Lenox / Ethan Koch | Step 2: Phase 1 Systems Integrator — COMPLETE ✅ ($152,300) M1 Network Equipment Specs $36,250 + M2 RFP/Vendor Recommendation $16,250 + M3 Site Surveys $99,800 | ✓ |  |  | 152300 |  |  | 152300 | SOURCE: B&M Ph1 SOW (Feb 27 2024) Section 1.5 CPS Milestones M1=$36,250 (due 6/11/2024) + M2=$16,250 (due 9/4/2024) + M3=$99,800 (due 6/14/2024) Total Ph1 SOW = $306,300. Balance = M4 PM $154,000. Paid via PO 7000001415
8 | B&M — Ethan Koch PE | Step 3a: Substation Site Surveys Ph2 — COMPLETE ✅ ($86,040) Visual inspection 36 sites. Digital photos + video. Feeds IFR design. Paid Feb 27 2026. |  | ✓ |  |  | 86040 |  | 86040 | SOURCE: B&M Ph2 SOW (RITM3364011) Section 1.5 CPS Milestone 3 = $86,040 Due date 2/27/2026. Paid via PO 7000002099
9 | B&M — Ethan Koch PE | Step 3b: Site Surveys Ph3 — ★PCR (31 sites, ~$86,000) Same visual inspection scope as Ph2. Starts Aug 2026. |  |  | ✓ |  |  | 86000 | 86000 | SOURCE: Estimate = Ph2 SOW CPS M3 rate ($86,040) applied to 31 sites ★PCR No SOW executed yet for Ph3 surveys
10 | B&M — Ethan Koch PE | Step 4a: Staging Support Ph1 — COMPLETE ✅ ($57,300) Card slotting + SFP plan, fiber connectivity matrix, chassis labeling. Full staging test plan: firmware, IGP, BGP, BFD, SyncE, NMS, VPRN/Epipe/Cpipe, failure tests. | ✓ |  |  | 57300 |  |  | 57300 | SOURCE: B&M Ph2 SOW (RITM3364011) Section 1.5 CPS Milestone 1 = $57,300 Due date 8/22/2025. Paid via PO 7000002099
11 | B&M — Ethan Koch PE | Step 4b: Staging Support Ph2 (~$57,300 est.) Same test plan scope. 36 nodes. Jul–Aug 2026. |  | ✓ |  |  | 57300 |  | 57300 | SOURCE: B&M Ph2 SOW CPS M1 rate ($57,300) — Ph2 staging same scope Estimate = Ph1 staging cost (no separate milestone defined in Ph2 SOW for Ph2 staging)
12 | B&M — Ethan Koch PE | Step 4c: Staging Support Ph3 — ★PCR (~$57,300 est.) Same scope. 31 nodes. |  |  | ✓ |  |  | 57300 | 57300 | SOURCE: Estimate = Ph1/Ph2 staging rate ★PCR No SOW executed
13 | B&M — Nick Cianciolo PE | Step 5a: MPLS Node Design IFR Ph1 — COMPLETE ✅ $16,695/site × 31 sites = $517,545 Per site deliverables: floor plan (AutoCAD), rack elevation (Visio), power one-line (Visio), cable schedule (Excel), BOM (Excel), site scope of work (Word). | ✓ |  |  | 517545 |  |  | 517545 | SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D — Site List and Cost Breakdown IFR Cost = $16,695.00 per site × 31 Ph1 sites = $517,545 Every site in App D listed at $16,695 IFR / $5,963 IFC / $1,192 As-Built = $23,850 total/site
14 | B&M — Nick Cianciolo PE | Step 5b: MPLS Node Design IFR Ph2 (rolling Feb–Jun 29 2026) $16,695/site × 36 sites = $601,020 Same deliverable package per site. Final IFR deadline Jun 29 2026. |  | ✓ |  |  | 601020 |  | 601020 | SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D — IFR Cost = $16,695/site × 36 Ph2 sites Covered under CPS Milestone 4 ($858,600 total for IFR+IFC) via PO 7000002099
15 | B&M — Nick Cianciolo PE | Step 5c: MPLS Node Design IFC Ph2 (final Jul 13 2026) $5,963/site × 36 sites = $214,668 PE-sealed. Issued for Construction. Triggers Hawkeye cable orders + construction. |  | ✓ |  |  | 214668 |  | 214668 | SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D — IFC Cost = $5,963/site × 36 Ph2 sites Part of CPS Milestone 4 total ($858,600)
16 | B&M — Nick Cianciolo PE | Step 5d: MPLS Node Design IFR + IFC Ph3 — ★PCR (31 sites) IFR: $16,695 × 31 = $517,545 IFC: $5,963 × 31 = $184,853 Ph3 design accelerated into Ph2 window per schedule recovery plan. |  |  | ✓ |  |  | 702398 | 702398 | SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D rates applied to 31 Ph3 sites ★PCR No Ph3 SOW executed yet. PCR required.
↓ AS-BUILT DRAWINGS — ALL 3 PHASES CONSOLIDATED IN PHASE 3 (2027) per Jay direction May 21 2026
17 | B&M — Nick Cianciolo PE | Step 6: AS-BUILT Drawings — ALL PHASES in Ph3 (2027) Ph1 As-Builts: $1,192 × 31 sites = $36,952 Ph2 As-Builts: $1,192 × 36 sites = $42,912 Ph3 As-Builts: $1,192 × 31 sites = $36,952 TOTAL ALL PHASES: $116,816 — billed in Phase 3 (2027) Red-line record drawings. Issued 1 month after construction complete. | ✓ | ✓ | ✓ |  |  | 116816 | 116816 | SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D — As-Built Cost = $1,192/site Ph1 (31×$1,192=$36,952) + Ph2 (36×$1,192=$42,912) + Ph3 (31×$1,192=$36,952) = $116,816 ★ Per Jay instruction 5/21/2026: ALL as-builts paid in Ph3 regardless of phase. IFRs/IFCs stay in their phase.
18 | B&M — Ethan Koch PE | Step 7a: Construction Support Coordinator Ph1 — COMPLETE ✅ ($368,100) On-site daily. $61,350/mo × 6 mo (Aug 2025–Jan 2026). Field coordination, daily reports, RFI log, cutover/commissioning support. | ✓ |  |  | 368100 |  |  | 368100 | SOURCE: B&M Ph2 SOW (RITM3364011) Section 1.5 CPS Milestone 2 = $368,100 total / $61,350 invoiced monthly PO Invoice Summary: PO 7000002099 — multiple $61,350 invoices reconciled
19 | B&M — Ethan Koch PE | Step 7b: Construction Support Coordinator Ph2 $61,350/mo × 6 mo (Aug–Jan 2027) = $368,100 Pre-construction planning, on-site coordination, RFI log, daily field reports, cutover support. |  | ✓ |  |  | 368100 |  | 368100 | SOURCE: B&M Ph2 SOW (RITM3364011) Section 1.5 CPS Milestone 2 rate $61,350/month × 6 months. Same scope as Ph1 Milestone 2.
20 | B&M — Ethan Koch PE | Step 7c: Construction Support Coordinator Ph3 — ★PCR ~$245,400 est. (~4 months × $61,350) |  |  | ✓ |  |  | 245400 | 245400 | SOURCE: Estimate = B&M Ph2 SOW M2 rate ($61,350/mo) × 4 months ★PCR No Ph3 SOW yet
B&M SUBTOTAL | [5 empty] | 1161245 | 1428428 | 1229914 | 3819587
4 ─ HAWKEYE (Elecnor Hawkeye LLC) — Ph1 PO 7000002054 $402,793 (inc Addendum 1) ¦ Ph2 SOW $400,680 (Mar 27 2026)
21 | Hawkeye — Vinny Montano | Step 1: Pre-Construction Survey (per site, after IFC issued) Ph1 complete ✅. Ph2: Vinny visits each substation, measures cable runs, confirms rack location per IFC. Ph2 SOW Milestone Phase 0 = $100,170 | ✓ | ✓ |  |  | 100170 |  | 100170 | SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone Phase 0 = $100,170 25% of $400,680 SOW value. Due: TBD (after IFCs issued)
22 | Hawkeye | Step 2a: Staging Ph1 — COMPLETE ✅ ($100,170) Rack + slot 31 Nokia SAR-8 nodes per B&M card plan, install SFPs, power-on, test. | ✓ |  |  | 100170 |  |  | 100170 | SOURCE: Hawkeye Ph1 PO 7000002054 — $402,792.76 total (includes Addendum 1 WDs #1-5,9) Ph1 SOW original $333,900 + Addendum 1 $68,892.76 = $402,792.76 Staging portion confirmed from PO Invoice Summary
23 | Hawkeye | Step 2b: Staging Ph2 (Jul–Aug 2026) Same scope. 36 nodes. Per Ph2 SOW Milestone 1 = $100,170 |  | ✓ |  |  | 100170 |  | 100170 | SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone 1 = $100,170 25% of $400,680 SOW value
24 | Hawkeye | Step 2c: Staging Ph3 — ★PCR (~$100,170 est.) Same scope. 31 nodes. |  |  | ✓ |  |  | 100170 | 100170 | SOURCE: Estimate = Hawkeye Ph2 SOW M1 rate ★PCR No Ph3 SOW yet
25 | Hawkeye — 3 visits | Step 3a: Substation Installation Ph1 — COMPLETE ✅ ($302,623) Visit 1: deliver, rack SAR-8, conduit, pull cables, Eltek PSU Visit 2: terminate fiber, CWDM, RS-232 patch panel, CAT6, 4-wire VF Visit 3: energize node, checklist, notify B&M CSC + relay team Hawkeye SOW Sec 1.2 items (i–xi): furnish/install SM fiber, CAT6, serial, 4-wire VF, ground bar, conduit | ✓ |  |  | 302623 |  |  | 302623 | SOURCE: Hawkeye Ph1 PO 7000002054 — $402,792.76 total Installation portion $302,623 from PO Invoice Summary (invoices 77148 + 78832 + 255072 = $197,517 invoiced, balance accrued) Addendum 1 covers WDs 1-5,9 for staging upgrades, inner duct at 9 sites
26 | Hawkeye — 3 visits | Step 3b: Substation Installation Ph2 (Aug 5–Sep 28 2026) Ph2 SOW M2 = $80,136. Same 3-visit scope. 36 sites. Hawkeye furnishes/installs: SM fiber, CAT6, serial, 4-wire VF, ground bar, conduit, inner duct. Checkout checklist + record docs per site. |  | ✓ |  |  | 80136 |  | 80136 | SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone 2 = $80,136 20% of $400,680 SOW value
27 | Hawkeye — 3 visits | Step 3c: Substation Installation Ph3 — ★PCR (31 sites, ~$402,793 est.) Same 3-visit scope. |  |  | ✓ |  |  | 402793 | 402793 | SOURCE: Estimate = Hawkeye Ph1 PO rate ($12,993/site × 31 sites) ★PCR No Ph3 SOW yet. Rate = Ph1 PO total $402,793 ÷ 31 sites
28 | Hawkeye | Step 4a: Go-Live Sign-Off Ph2 (Ph2 SOW M4 = $80,136) After relay team completes RTU cutover: confirm all Nokia circuits live, no JMUX traffic, acceptance. |  | ✓ |  |  | 80136 |  | 80136 | SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone 4 = $80,136 20% of $400,680 SOW value
29 | Hawkeye | Step 4b: Go-Live Sign-Off Ph3 — ★PCR (~$100,000 est.) |  |  | ✓ |  |  | 100000 | 100000 | SOURCE: Estimate — no Ph3 SOW yet ★PCR
30 | Hawkeye | Step 5: Decommissioning — ALL Phases in Ph3 (Ph2 SOW M6 = $40,068 + Ph1/Ph3 est.) Cannot start until Nokia LIVE on all 3 phases. De-rack JMUX, palletize, ship to PSEG warehouse. 98 sites total (31+36+31). $141,351 est. |  |  | ✓ |  |  | 141351 | 141351 | SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone 6 = $40,068 (10% of SOW) Ph1 decommission + Ph3 decommission estimated at same rate Total $141,351 across all phases, all executed in Ph3
31 | Hawkeye | WD#8 Fiber Testing — Elwood to Northport + 7 patch panels | ✓ |  |  |  | 8229 |  | 8229 | SOURCE: PO 7000009182 = $8,229 (separate work directive)
HAWKEYE SUBTOTAL | [5 empty] | 402793 | 368841 | 744314 | 1515948
5 ─ PAR (Phase Angle Regulator) ★ NEW SCOPE — PCR REQUIRED ¦ 6 sites: Northport, 5HK, Melville, 7Z, 2H, 2R
a | Nokia / Presidio | Iniven RC-30 Equipment — 6 units × $8,750 = $52,500 Serial→C37.94 protocol converter. PO placed. 8-week lead. Target delivery Jun 2026. |  | ✓ |  |  | 52500 |  | 52500 | SOURCE: PO 7000002695 — $52,500 confirmed ★PCR CONFIRMED: Vic call May 18 2026
b | Chak's Team (Relay Eng) | Relay Engineering Design — 200 hrs × 6 sites × $200/hr = $240,000 Review PAR scheme, design C37.94 interface, relay settings, MOP, NERC-CIP compliance. |  | ✓ |  |  | 240000 |  | 240000 | SOURCE: CONFIRMED Vic May 18 2026 call $200/hr = external relay/protection engineering billing rate No SOW executed yet — ★PCR required
c | Steven Bradley (Relay) | Relay Install, Configure & Cutover — ~1,298 hrs × $200/hr = $259,500 Install RC-30, wire to PAR relay contacts, configure C37.94, end-to-end test, NERC-CIP commissioning. ★ Call Steven before Mon May 25 — need names + hours by month |  | ✓ |  |  | 259500 |  | 259500 | SOURCE: CONFIRMED Vic May 18 2026 call ★ ZERO SAP actuals to date — unverified in system No SOW executed yet — ★PCR required
d | Various | PAR Materials — $30,000 Custom serial cables, C37.94 connectors, rack hardware across 6 sites. |  | ✓ |  |  | 30000 |  | 30000 | SOURCE: CONFIRMED Vic May 18 2026 call No PO yet — ★PCR required
PAR SUBTOTAL ★PCR★ ($52.5K RC-30 + $240K Eng + $259.5K Install + $30K Materials) | [5 empty] | 0 | 582000 | 0 | 582000
6 ─ PM / CONTROLS / SCHEDULER
32 | Hermitage — Jay G | PM — Dhananjaya Gunaratne | ✓ | ✓ | ✓ |  | 174000 | 58000 | 232000 | SOURCE: Chad workbook forecast No SOW reference — internal Hermitage contract
33 | Hermitage — Ahsan | PM — Ahsan Khawaja |  | ✓ |  |  | 257619 |  | 257619 | SOURCE: PO 7000001734 — $257,619
34 | ComTec — Chad | Controller — Chad Boyett $8,400/month | ✓ | ✓ | ✓ | 67200 | 100800 | 33600 | 201600 | SOURCE: Chad workbook forecast — $8,400/month rate No PO reference provided
35 | ComTec — Umair | Scheduler — Umair Mohammed $5,416/month | ✓ | ✓ | ✓ | 54160 | 67040 | 13400 | 134600 | SOURCE: POs 7000001145 + 7000002363
36 | ComTec — Farouk | Scheduler — Farouk Adelekan |  | ✓ | ✓ |  | 20000 | 6600 | 26600 | SOURCE: PO 5000046818
37 | Hermitage — Ed S | O/S Sr. Engineer — Edward Schwartz $2,512/month | ✓ | ✓ | ✓ |  | 30000 | 5000 | 35000 | SOURCE: PO 7000001998
PM / CONTROLS SUBTOTAL | [5 empty] | 121360 | 649459 | 116600 | 887419
7 ─ INTERNAL LABOR (PSEG + Cognizant)
38 | PSEG — Multiple | PSEG Internal Labor (Rahiq, Brianna, Chok, Lok, Sameer et al.) Martin Gately: DEPARTED — $0 2026+ | ✓ | ✓ | ✓ | 82421 | 154989 | 60000 | 297410 | SOURCE: Chad workbook forecast ★ Martin Gately departed PSEG — removed from all 2026+ forecasts 2025 actuals ($133,886) already in SAP as sunk cost
39 | Cognizant — Lee | Lee Blackman — Sr. Network Architect $7,200/month | ✓ | ✓ |  |  | 86400 |  | 86400 | SOURCE: PO 7000002490 — $7,200/month rate
40 | PSEG — Steven B | Relay Team — Steven Bradley ★ ZERO SAP actuals charged to date. $195K forecast. ★ CALL STEVEN BEFORE MON MAY 25 — need names, hours by month, WBS codes | ✓ | ✓ | ✓ |  | 195000 | 30000 | 225000 | SOURCE: Chad workbook forecast — UNVERIFIED No SAP actuals. No invoices. Must collect resource names + hrs from Steven before May 25 ★ Separate from PAR relay cost (PAR relay = $259,500 external, Steven Bradley internal above)
INTERNAL LABOR SUBTOTAL | [5 empty] | 82421 | 436389 | 90000 | 608810
8 ─ PQA / ASSESSMENTS / NERC-CIP
41 | Cognizant / EPMO | PQA Audit — Margaret Tanner Glover | ✓ | ✓ | ✓ | 56330 | 40000 | 10000 | 106330 | SOURCE: Chad workbook forecast
42 | PSEG | Assessments (PSEG IT overhead) | ✓ | ✓ | ✓ | 19172 | 72737 | 20000 | 111909 | SOURCE: Chad workbook forecast
43 | TRC — Raju K | Raju Khedkar — Cyber Security / NERC-CIP | ✓ | ✓ | ✓ | 3726 | 30000 | 5000 | 38726 | SOURCE: POs 7000001237 + 7000002343
PQA / ASSESSMENTS SUBTOTAL | [5 empty] | 79228 | 142737 | 35000 | 256965
★ GRAND TOTAL — ALL PHASES (Ph1=31 ¦ Ph2=36 ¦ Ph3=31 = 98 sites) | [5 empty] | 3500520 | 4646103 | 3889301 | 12035924
APPROVED CP BUDGET (Chad WB): 2025 $3.25M + 2026 $2.6M = $5.85M approved ¦ FULL EAC incl 2024 actuals ($741,206): $12,777,130 ¦ FUNDING GAP ~$6.5M ¦ URB ASK (incl $400K contingency) ~$6.9M
COLOR KEY: Green = SOW/PO actual ¦ Blue = SOW milestone (not yet paid) ¦ Yellow = Estimate / Chad forecast (no SOW) ¦ Red = ★FLAG: Graybar removed Ph2/Ph3, As-Builts moved to Ph3, Steven Bradley unverified

## URB Ask
PRJ13797 JMUX — URB FUNDING REQUEST v7
Item | Amount | Note
Total EAC (all phases) | $12,777,130 | Incl 2024 actuals $741,206
Already Spent (2024+2025+Jan-Apr2026) | $5,908,822 | Chad workbook actuals
Approved Budget (2025+2026) | $5,850,000 | Chad WB approved CP
FUNDING GAP | $6,927,130 | EAC minus approved budget
Contingency | $400,000 | 10% buffer
URB ASK | $7,327,130 | Gap + contingency