# PRJ13797 — JMUX REPLACEMENT

## Financial Summary v7 — Source Traceability Document

Date: May 21, 2026  |  Prepared by: Daminie AI Agent  |  Requested by: Dhananjaya (Jay) Gunaratne

This document provides the source reference for every line item in the Financial Summary v7 spreadsheet. For each row it states: what document or call the number came from, what section/page, and whether it is an ACTUAL (paid/PO), SOW MILESTONE (contracted but unpaid), or ESTIMATE (no contract — subject to change).

LEGEND:

✅ GREEN = ACTUAL — confirmed PO or paid invoice

📊 YELLOW = ESTIMATE — derived from Chad workbook forecast or rate extrapolation. No PO or SOW backing.

BLUE = SOW MILESTONE — contracted amount in a signed SOW, not yet invoiced

⚠ RED = FLAG — no source document. Needs vendor confirmation or PCR.

## SECTION 1 — MATERIALS (Nokia Equipment)

Row Row 1  |  Nokia / Presidio  |  Nokia SAR-8 MPLS Nodes + licenses + SFPs + CSM cards  |  Ph1 $1,412,400 actual | Ph2 $733,293 forecast | Ph3 $1,412,400 estimate

Source Type: ACTUAL (Ph1) + ESTIMATE (Ph2/Ph3)

Detail: Ph1: PO 7000001857 (Nokia) + PO 7000001175 (Nokia $190,575 paid in full) + PO 7000001748 (Presidio $40,955 paid in full). All confirmed from PO/Invoice Summary spreadsheet. Ph2 $733,293: Chad workbook forecast — no PO yet. Ph3 $1,412,400: estimate at same per-site rate as Ph1 (no PO, no SOW).

Row Row 2  |  Presidio  |  CWDM Cards (mux/demux per site)  |  Ph2 $25,000 | Ph3 $20,000

Source Type: ESTIMATE

Detail: Chad workbook forecast only. No separate PO issued yet. Will be ordered as IFCs are issued per site.

## SECTION 2 — CABLES & CONNECTORS

⚠ MAJOR CORRECTION FROM v6: Graybar Electric is NOT being used for Phase 2 or Phase 3. Phase 1 Graybar cost is ACTUAL (4 POs). Phase 2 and Phase 3 cable vendor is TBD. Cost estimate is held pending vendor confirmation from Jay.

Row Row 3  |  Graybar Electric  |  Phase 1 — Cables, Connectors, Fiber Jumpers — 31 sites COMPLETE  |  $241,073 ACTUAL

Source Type: ACTUAL — 4 confirmed POs (all Reconciled in PO/Invoice Summary)

Detail: PO 7000001767: $24,758.84 (Reconciled, paid in full)
PO 7000001811: $115,004.10 (Reconciled, paid in full)
PO 7000001841: $55,286.98 (Reconciled, paid in full)
PO 7000002119: $46,023 (4th Graybar PO per Chad WB)
Total actual: $241,073. Hawkeye Ph2 SOW Sec 1.2 items v-vi confirms cable types: 2× SM fiber patch cords, CAT6, serial, 4-wire VF, conduit, inner duct.

Row Row 4  |  Vendor TBD (NOT Graybar)  |  Phase 2 — Cables, Connectors, Fiber Jumpers — 36 sites  |  $279,956 ESTIMATE — VENDOR NOT CONFIRMED

Source Type: ESTIMATE ONLY — NO SOW, NO PO

Detail: Rate derived from Graybar Ph1 actual: $241,073 ÷ 31 sites = $7,777/site × 36 sites = $279,956. Jay confirmed May 21 2026: Graybar NOT used for Ph2 or Ph3. Vendor TBD. Amount held as placeholder. Jay to advise replacement vendor.

⚠ Ph2 cable vendor is NOT confirmed. This $279,956 must be updated once vendor is selected.

Row Row 5  |  Vendor TBD (NOT Graybar)  |  Phase 3 — Cables, Connectors, Fiber Jumpers — 31 sites  |  $241,073 ESTIMATE — VENDOR NOT CONFIRMED ★PCR

Source Type: ESTIMATE ONLY — NO SOW, NO PO

Detail: Rate: $7,777/site × 31 sites = $241,073. Same derivation as Row 4. Ph3 vendor TBD. ★PCR required.

⚠ Ph3 cable vendor is NOT confirmed. PCR required.

## SECTION 3 — BURNS & McDONNELL (B&M)

Two SOWs on file:

✅ B&M Ph1 SOW: Feb 27 2024, Total $306,300 — 3 milestones (M1 $36,250 + M2 $16,250 + M3 $99,800) + M4 PM $154,000. PO 7000001415.

✅ B&M Ph2 SOW: Aug 13 2025, RITM3364011, Total $1,370,040 — M1 Staging $57,300 + M2 Construction $368,100 + M3 Surveys $86,040 + M4 Design $858,600. PO 7000002099.

Appendix D of Ph2 SOW is the rate card: $16,695 IFR / $5,963 IFC / $1,192 As-Built = $23,850/site total.

Row Row 6  |  B&M — Alex Lenox  |  Step 1: Project Management — $5,500/month  |  2025 $66,000 | 2026 $44,000 | 2027 $22,000

Source Type: PO ACTUAL + SOW MILESTONE

Detail: SOURCE: B&M Ph1 SOW Section 1.5 M4 (PM Services). B&M Ph2 SOW PO 7000001429 confirmed at $5,500/invoice. PO Invoice Summary shows multiple $5,500 reconciled invoices from PO 7000001429 (Inv 170554-5, -6, -8, -10, -21). Ph3 $22,000: estimate at 4 months × $5,500.

Row Row 7  |  B&M — Alex Lenox / Ethan Koch  |  Step 2: Ph1 Systems Integrator — COMPLETE  |  $152,300 ACTUAL

Source Type: ACTUAL — B&M Ph1 SOW milestones 1-3

Detail: SOURCE: B&M Ph1 SOW (Feb 27 2024) Section 1.5 CPS Milestones:
M1 Network Equipment Specs = $36,250 (due 6/11/2024)
M2 RFP/Vendor Recommendation = $16,250 (due 9/4/2024)
M3 Site Surveys = $99,800 (due 6/14/2024)
Total = $152,300. Paid via PO 7000001415.

Row Row 8  |  B&M — Ethan Koch PE  |  Step 3a: Site Surveys Ph2 — COMPLETE  |  $86,040 ACTUAL

Source Type: ACTUAL — B&M Ph2 SOW CPS Milestone 3

Detail: SOURCE: B&M Ph2 SOW (RITM3364011) Section 1.5 CPS Milestone 3 = $86,040. Due date 2/27/2026. Paid via PO 7000002099. Scope: visual inspection 36 sites, digital photos + video, feeds IFR design.

Row Row 9  |  B&M — Ethan Koch PE  |  Step 3b: Site Surveys Ph3 — ★PCR  |  $86,000 ESTIMATE

Source Type: ESTIMATE — no Ph3 SOW

Detail: SOURCE: Estimate = Ph2 SOW CPS M3 rate ($86,040) applied to same scope for 31 sites. No Ph3 SOW executed. ★PCR required.

Row Row 10  |  B&M — Ethan Koch PE  |  Step 4a: Staging Support Ph1 — COMPLETE  |  $57,300 ACTUAL

Source Type: ACTUAL — B&M Ph2 SOW CPS Milestone 1

Detail: SOURCE: B&M Ph2 SOW (RITM3364011) Section 1.5 CPS Milestone 1 = $57,300 (due 8/22/2025). Scope: card slotting plan, SFP plan, fiber connectivity matrix, chassis labeling, full staging test plan (firmware, IGP, BGP, BFD, SyncE, NMS, VPRN/Epipe/Cpipe, failure tests). Paid via PO 7000002099.

Row Row 11  |  B&M — Ethan Koch PE  |  Step 4b: Staging Support Ph2  |  $57,300 ESTIMATE

Source Type: ESTIMATE — Ph2 SOW does not define a separate Ph2 staging milestone

Detail: SOURCE: Ph2 SOW CPS M1 rate applied to Ph2. Same scope, 36 nodes. No separate milestone value stated in Ph2 SOW for Ph2 staging — estimate held at Ph1 M1 rate.

Row Row 12  |  B&M — Ethan Koch PE  |  Step 4c: Staging Support Ph3 — ★PCR  |  $57,300 ESTIMATE

Source Type: ESTIMATE — no Ph3 SOW

Detail: SOURCE: Estimate = Ph1/Ph2 staging rate. No Ph3 SOW. ★PCR required.

Row Row 13  |  B&M — Nick Cianciolo PE  |  Step 5a: IFR Ph1 — COMPLETE  |  $517,545 ACTUAL

Source Type: ACTUAL — B&M Ph2 SOW Appendix D

Detail: SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D — Site List and Cost Breakdown.
Every Ph1 site listed at IFR Cost = $16,695.00 per site × 31 sites = $517,545.
Appendix D lists all 36 Ph2 sites individually, each at $23,850 total ($16,695 IFR + $5,963 IFC + $1,192 As-Built).
Ph1 IFR used same rate applied to 31 sites. Paid via PO 7000002099.

Row Row 14  |  B&M — Nick Cianciolo PE  |  Step 5b: IFR Ph2  |  $601,020 SOW MILESTONE

Source Type: SOW MILESTONE — B&M Ph2 SOW Appendix D

Detail: SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D — IFR Cost = $16,695/site × 36 Ph2 sites = $601,020.
Part of CPS Milestone 4 total = $858,600 (IFR+IFC combined for all 36 sites).
PO 7000002099 ordered $1,370,040. Invoice 170554-20 = $147,330 (partial, reconciled).

Row Row 15  |  B&M — Nick Cianciolo PE  |  Step 5c: IFC Ph2  |  $214,668 SOW MILESTONE

Source Type: SOW MILESTONE — B&M Ph2 SOW Appendix D

Detail: SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D — IFC Cost = $5,963/site × 36 Ph2 sites = $214,668.
Part of CPS Milestone 4 total. PE-sealed drawings issued for construction.

Row Row 16  |  B&M — Nick Cianciolo PE  |  Step 5d: IFR + IFC Ph3 — ★PCR  |  $702,398 ESTIMATE

Source Type: ESTIMATE — B&M Ph2 SOW App D rates applied to Ph3

Detail: SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D rates × 31 Ph3 sites:
IFR: $16,695 × 31 = $517,545
IFC: $5,963 × 31 = $184,853
Total: $702,398
No Ph3 SOW executed. ★PCR required.

## STEP 6 — AS-BUILT DRAWINGS: MAJOR CHANGE FROM v6

⚠ Per Jay Gunaratne instruction May 21 2026: ALL As-Built drawings (Ph1 + Ph2 + Ph3) are to be consolidated and billed in Phase 3 only. IFRs and IFCs remain in their respective phases.

Row Row 17  |  B&M — Nick Cianciolo PE  |  Step 6: AS-BUILT Drawings — ALL 3 PHASES in Ph3 (2027)  |  $116,816 TOTAL — ALL IN 2027

Source Type: SOW MILESTONE — B&M Ph2 SOW Appendix D (rate) + Jay direction

Detail: SOURCE: B&M Ph2 SOW (RITM3364011) Appendix D — As-Built Cost = $1,192.00/site.
Ph1: $1,192 × 31 = $36,952
Ph2: $1,192 × 36 = $42,912
Ph3: $1,192 × 31 = $36,952
TOTAL ALL PHASES: $116,816 — booked entirely in 2027/Phase 3.
v6 ERROR: Ph1 as-builts ($36,952) was in 2025 column and Ph2 ($42,912) was in 2026 column — both WRONG. Now corrected per Jay instruction.

⚠ v6 had as-builts split across phases — now all $116,816 moved to Ph3/2027 only.

Row Row 18  |  B&M — Ethan Koch PE  |  Step 7a: Construction Support Ph1 — COMPLETE  |  $368,100 ACTUAL

Source Type: ACTUAL — B&M Ph2 SOW CPS Milestone 2

Detail: SOURCE: B&M Ph2 SOW (RITM3364011) Section 1.5 CPS Milestone 2 = $368,100 total, $61,350/month.
Engaged Aug 2025 through Jan 2026 (6 months). On-site daily during construction + cutover.
PO Invoice Summary: PO 7000002099 — multiple $61,350 invoices reconciled.

Row Row 19  |  B&M — Ethan Koch PE  |  Step 7b: Construction Support Ph2  |  $368,100 SOW MILESTONE

Source Type: SOW MILESTONE — B&M Ph2 SOW CPS Milestone 2 rate

Detail: SOURCE: B&M Ph2 SOW CPS Milestone 2 rate: $61,350/month × 6 months = $368,100.
Construction window Aug–Jan 2027. Same scope as Ph1 M2.

Row Row 20  |  B&M — Ethan Koch PE  |  Step 7c: Construction Support Ph3 — ★PCR  |  $245,400 ESTIMATE

Source Type: ESTIMATE — no Ph3 SOW

Detail: SOURCE: Estimate = $61,350/month × 4 months. Rate from B&M Ph2 SOW M2. ★PCR required.

## SECTION 4 — HAWKEYE (Elecnor Hawkeye LLC)

Two Hawkeye contracts on file:

✅ Hawkeye Ph1 SOW: Aug 5 2025, original $333,900 + Addendum 1 ($68,892.76 for WDs 1-5,9) = $402,792.76 total. PO 7000002054.

✅ Hawkeye Ph2 SOW: Mar 27 2026, Total $400,680. Milestones: Ph0 $100,170 + M1 $100,170 + M2 $80,136 + M4 $80,136 + M6 $40,068.

Hawkeye SOW Sec 1.2 defines what Hawkeye furnishes per site: Nokia SAR-8, CWDM, Eltek PSU, RS-232 patch panel, SM fiber, CAT6, serial, 4-wire VF, ground bar, conduit, inner duct.

Row Row 21  |  Hawkeye  |  Step 1: Pre-Construction Survey Ph2  |  $100,170 SOW MILESTONE

Source Type: SOW MILESTONE — Hawkeye Ph2 SOW CPS Milestone Phase 0

Detail: SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone Phase 0 = $100,170 (25% of $400,680).
Scope: on-site assessment survey per site, review IFC documents, prepare inventory/BOM.

Row Row 22  |  Hawkeye  |  Step 2a: Staging Ph1 — COMPLETE  |  $100,170 ACTUAL

Source Type: ACTUAL — Hawkeye Ph1 PO 7000002054

Detail: SOURCE: Hawkeye Ph1 PO 7000002054 — $402,792.76 total (inc Addendum 1).
PO Invoice Summary: invoices 77148 ($133,560), 78832 ($44,425), 255072 ($19,532) = $197,517 invoiced. Balance accrued.
Addendum 1 covered WDs 1-5,9: racks, antenna mast, subpanel, fiber jumpers, inner duct at 9 sites.

Row Row 23  |  Hawkeye  |  Step 2b: Staging Ph2  |  $100,170 SOW MILESTONE

Source Type: SOW MILESTONE — Hawkeye Ph2 SOW CPS Milestone 1

Detail: SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone 1 = $100,170 (25% of $400,680).

Row Row 24  |  Hawkeye  |  Step 2c: Staging Ph3 — ★PCR  |  $100,170 ESTIMATE

Source Type: ESTIMATE — no Ph3 SOW

Detail: SOURCE: Estimate = Hawkeye Ph2 SOW M1 rate. ★PCR required.

Row Row 25  |  Hawkeye — 3 visits  |  Step 3a: Substation Installation Ph1 — COMPLETE  |  $302,623 ACTUAL

Source Type: ACTUAL — Hawkeye Ph1 PO 7000002054

Detail: SOURCE: Hawkeye Ph1 PO 7000002054 total $402,792.76.
Installation scope per Hawkeye SOW Sec 1.2: rack Nokia SAR-8, CWDM, Eltek PSU, RS-232 patch panel,
2× SM fiber patch cords, CAT6, serial, 4-wire VF, ground bar, conduit, inner duct.
3 mobilizations per site: survey, install/energize, decommission.

Row Row 26  |  Hawkeye — 3 visits  |  Step 3b: Substation Installation Ph2  |  $80,136 SOW MILESTONE

Source Type: SOW MILESTONE — Hawkeye Ph2 SOW CPS Milestone 2

Detail: SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone 2 = $80,136 (20% of $400,680).
Same 3-visit scope as Ph1. 36 sites. Construction window: Aug 5–Sep 28 2026.

Row Row 27  |  Hawkeye — 3 visits  |  Step 3c: Substation Installation Ph3 — ★PCR  |  $402,793 ESTIMATE

Source Type: ESTIMATE — no Ph3 SOW

Detail: SOURCE: Estimate = Ph1 PO rate per site: $402,793 ÷ 31 sites = $12,993/site × 31 sites = $402,793. ★PCR.

Row Row 28  |  Hawkeye  |  Step 4a: Go-Live Sign-Off Ph2  |  $80,136 SOW MILESTONE

Source Type: SOW MILESTONE — Hawkeye Ph2 SOW CPS Milestone 4

Detail: SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone 4 = $80,136 (20% of $400,680).
After relay team RTU cutover: confirm Nokia circuits live, no JMUX traffic, PSEG formal acceptance.

Row Row 29  |  Hawkeye  |  Step 4b: Go-Live Sign-Off Ph3 — ★PCR  |  $100,000 ESTIMATE

Source Type: ESTIMATE — no Ph3 SOW

Detail: SOURCE: Estimate only. ★PCR required.

Row Row 30  |  Hawkeye  |  Step 5: Decommissioning — ALL phases in Ph3  |  $141,351 ESTIMATE

Source Type: PARTIAL SOW + ESTIMATE

Detail: SOURCE: Hawkeye Ph2 SOW (Mar 27 2026) Section 1.5 CPS Milestone 6 = $40,068 (10% of $400,680).
Ph1 and Ph3 decommission estimated at same rate.
Cannot start until Nokia LIVE on all 3 phases. De-rack JMUX, palletize, ship to PSEG warehouse. 98 sites.

Row Row 31  |  Hawkeye  |  WD#8 Fiber Testing  |  $8,229 ACTUAL

Source Type: ACTUAL — PO 7000009182

Detail: SOURCE: PO 7000009182 = $8,229 (Elwood to Northport fiber test + 7 patch panels).

## SECTION 5 — PAR (Phase Angle Regulator) — ★PCR REQUIRED

⚠ PAR is entirely NEW scope not in original project budget. Full PCR required. $582,000 total.

Row Row a  |  Nokia / Presidio  |  Iniven RC-30 Equipment  |  $52,500

Source Type: PO CONFIRMED

Detail: SOURCE: PO 7000002695 = $52,500. 6 units × $8,750 each. CONFIRMED: Vic call May 18 2026.
Sites: Northport, 5HK Hicksville, Melville, 7Z Lindenhurst, 2H Far Rockaway, 2R Hewlett.

Row Row b  |  Chak's Team  |  Relay Engineering Design  |  $240,000

Source Type: CONFIRMED VERBAL — no SOW yet

Detail: SOURCE: CONFIRMED Vic call May 18 2026. 200 hrs × 6 sites × $200/hr = $240,000.
$200/hr is the EXTERNAL relay/protection engineering billing rate. No SOW executed yet.

Row Row c  |  Steven Bradley (Relay)  |  Relay Install, Configure & Cutover  |  $259,500

Source Type: CONFIRMED VERBAL — no SOW yet. ZERO SAP actuals.

Detail: SOURCE: CONFIRMED Vic call May 18 2026. ~1,298 hrs × $200/hr = $259,500.
★ ZERO SAP actuals charged to date — completely unverified in system.
★ ACTION: Call Steven Bradley before Mon May 25 — get names, hours by month, WBS codes.

⚠ Steven Bradley relay costs have ZERO SAP actuals. Must be verified before including in URB ask.

Row Row d  |  Various  |  PAR Materials  |  $30,000

Source Type: CONFIRMED VERBAL — no PO yet

Detail: SOURCE: CONFIRMED Vic call May 18 2026. Custom serial cables, C37.94 connectors, rack hardware.

## SECTION 6 — PM / CONTROLS / SCHEDULER

Row Row 32  |  Hermitage — Jay G  |  PM — Dhananjaya Gunaratne  |  2026 $174,000 | 2027 $58,000

Source Type: ESTIMATE — Chad workbook

Detail: SOURCE: Chad workbook forecast only. No separate SOW reference available.

Row Row 33  |  Hermitage — Ahsan  |  PM — Ahsan Khawaja  |  $257,619

Source Type: ACTUAL — PO 7000001734

Detail: SOURCE: PO 7000001734 = $257,619.

Row Row 34  |  ComTec — Chad  |  Controller — Chad Boyett  |  $8,400/month — 2025 $67,200 | 2026 $100,800 | 2027 $33,600

Source Type: ESTIMATE — Chad workbook

Detail: SOURCE: Chad workbook forecast at $8,400/month. No PO reference provided in documents received.

Row Row 35  |  ComTec — Umair  |  Scheduler — Umair Mohammed  |  $5,416/month

Source Type: ACTUAL — POs 7000001145 + 7000002363

Detail: SOURCE: POs 7000001145 + 7000002363.

Row Row 36  |  ComTec — Farouk  |  Scheduler — Farouk Adelekan  |  2026 $20,000 | 2027 $6,600

Source Type: ACTUAL — PO 5000046818

Detail: SOURCE: PO 5000046818.

Row Row 37  |  Hermitage — Ed S  |  Sr. Engineer — Edward Schwartz  |  2026 $30,000 | 2027 $5,000

Source Type: ACTUAL — PO 7000001998

Detail: SOURCE: PO 7000001998 = $2,512/month.

## SECTION 7 — INTERNAL LABOR

Row Row 38  |  PSEG Internal  |  PSEG Internal Labor (Rahiq, Brianna, Chok, Lok, Sameer)  |  2025 $82,421 | 2026 $154,989 | 2027 $60,000

Source Type: ESTIMATE — Chad workbook

Detail: SOURCE: Chad workbook forecast. Martin Gately DEPARTED — $0 in 2026+. His 2025 actuals ($133,886) already sunk in SAP. Removed from all future projections.

Row Row 39  |  Cognizant — Lee Blackman  |  Sr. Network Architect — $7,200/month  |  2026 $86,400

Source Type: ACTUAL — PO 7000002490

Detail: SOURCE: PO 7000002490 = $7,200/month.

Row Row 40  |  PSEG — Steven Bradley  |  Relay Team internal labor (separate from PAR external relay cost)  |  2026 $195,000 | 2027 $30,000

Source Type: ESTIMATE — Chad workbook — ZERO SAP ACTUALS

Detail: SOURCE: Chad workbook forecast only. ZERO SAP actuals charged to date. Completely unverified.
★ This is SEPARATE from the PAR relay cost (Row c = $259,500 external billing rate).
★ ACTION: Call Steven Bradley before Mon May 25 — need resource names, hours by month, WBS codes.

⚠ ZERO SAP actuals. Must collect actual charge data from Steven before finalizing.

## SECTION 8 — PQA / ASSESSMENTS / NERC-CIP

Row Row 41  |  Cognizant / EPMO  |  PQA Audit — Margaret Tanner Glover  |  2025 $56,330 | 2026 $40,000 | 2027 $10,000

Source Type: ESTIMATE — Chad workbook

Detail: SOURCE: Chad workbook forecast only.

Row Row 42  |  PSEG  |  Assessments (PSEG IT overhead)  |  2025 $19,172 | 2026 $72,737 | 2027 $20,000

Source Type: ESTIMATE — Chad workbook

Detail: SOURCE: Chad workbook forecast only.

Row Row 43  |  TRC — Raju Khedkar  |  Cyber Security / NERC-CIP  |  2025 $3,726 | 2026 $30,000 | 2027 $5,000

Source Type: ACTUAL — POs 7000001237 + 7000002343

Detail: SOURCE: POs 7000001237 + 7000002343.

## OPEN ITEMS / ACTIONS REQUIRED FROM JAY

⚠ ACTION 1: Ph2 + Ph3 cable vendor — Graybar is OUT. Who is supplying cables/connectors for Ph2 and Ph3? Need vendor name + PO or SOW to replace Row 4 ($279,956) and Row 5 ($241,073) estimates.

⚠ ACTION 2: Call Steven Bradley before Mon May 25 — confirm names of relay team resources, hours charged by month, and WBS codes. Both his internal labor ($195K, Row 40) and PAR relay work ($259,500, Row c) need verification.

⚠ ACTION 3: PAR PCR — submit PCR for $582,000 PAR scope and $800K Phase 3 acceleration. Total PCR ask ~$1.33M.

✅ CONFIRMED: All As-Builts (Ph1+Ph2+Ph3 = $116,816) now consolidated in Phase 3 / 2027 per Jay instruction May 21 2026.