## Slide 1: JMUX Replacement
Progress Current Period (past 2 weeks)- Milestones/Key Deliverables with Dates
CAT6 cable run completed by Hawkeye 03/04/2026
OTDR bad filter replaced; wavelength tested – green link light confirmed at Hicksville-Syosset 03/13/2026
BGP design for corporate connectivity completed by Lee Blackman 03/10/2026
Fiber termination to the NSP completed by Hawkeye 03/13/2026
New batch of IFRs received from Burns & McDonnell 03/13/2026
First batch of 3 IFRs converted to IFC and uploaded to shared drive 03/09/2026
IFR received for 6S Kings Hwy 03/13/2026
IFR received for 7BH Bohemia 03/13/2026
 | Status* | Trends*
Schedule Health | Yellow | 
Financial Health | Green | 
Scope Health | Green | 
Risk Health | Green | 
Resource Health | Green | 
Status Date: 03/13/2026
IT/Cyber: IT
Director: Irving Landesbaum
GPM: Vikas Vohra
Program Manager Jay Gunaratne
Time Management
Proj Plan (Baseline) Start 03-01-2024
Proj Actual Start 04-18-2024
Go-Live/In Service/Next Sprint Release 01-01-2024
Proj Plan (Baseline) End 04-08-2027
Proj Actual Target End 07-08-2027
Project Financials / Budget
WBS Code: I.39424.1.x
LIPA approved total project budget: $6,600,000.00
URB approved funding to date: $6,600,000.00
Spend to date: $4,548,505.00
Estimate to complete: $2,051,495.00
Estimate at completion: $6,600,000.00
Over (+) / Under (-) LIPA approved budget: +/- $00.00
Benefit
Due to GE announcing End of Life for the GE Jungle Mux system as of EOY 2025, the benefits for project is to allow the Systems Integrator to select the most appropriate ‘Equipment Vendor’ via the RFP process to replace the GE JMUX equipment.
Scope (95%-Complete)
The purpose of this project is to install new Multiprotocol Label Switching (MPLS) nodes, remove existing GE Jungle MUX (JMUX) equipment, and design new circuits from the existing substation .
Major Steps (next 2 weeks): Milestones/Key Deliverables with Dates
ILO Connection at Melville and Hicksville for remote server access (Brianna) 03/16/2026
BGP Corporate team approval and complete remote router configuration 03/20/2026
Northport DC fuse/relay issue resolution by Hawkeye and relay tech 03/20/2026
Nokia NSP remote access setup upon ILO and BGP completion 03/27/2026
Phase 2 IFR to IFC conversions – next batch submission to Burns & McDonnell 03/27/2026
Risk Management- Top 3 (in descending order of possible impact)
Vendor installation delays – inclement weather
Legacy JMUX equipment old and need to be very careful when doing cutovers.
Other projects and work being done at the substation simultaneously
Issue Management- Top 3 (in descending order of actual impact)
Accelerating phase 2 site surveys by getting them completed in Phase 1.
Working closely with vendors and tracking installation.
Equipment procurement and delays in SCM.
Scope/Change Management (most recent approved)
Adding 7 additional nodes to the original 25 Phase 1 nodes. The additional 7 nodes completes both ring 1 and ring 2 in this Phase 1 effort.
PRJ (ServiceNow): PRJ13797
Repository Link : JMUX Repository
Lifecycle Phase:
Execution
Current Period (past 2 weeks) Status Narrative:
CAT6 cable run completed at Hicksville on 03/04.
OTDR bad filter replaced; wavelength tested – confirmed green link light at Hicksville-Syosset on 03/13.
Fiber termination to the NSP completed by Hawkeye on 03/13.
BGP design for corporate connectivity completed by Lee Blackman on 03/10; awaiting Corporate approval.
First batch of 3 IFRs converted to IFC and uploaded to shared drive on 03/09.
New batch of IFRs received from Burns & McDonnell on 03/13.
Hawkeye engaged relay tech to resolve DC fuse tripping issue at Northport – in progress.
IFR received for 6S Kings Hwy on 03/13.
IFR received for 7BH Bohemia on 03/13.
Remediation (For Non-Green Statuses)
Schedule (Yellow): 3-week delay. Recovery: BGP Corporate approval + remote router configuration to restore Green.
Project Description
The Systems Integrator will create, facilitate, and execute the process for generating an RFP to select an ‘Equipment Vendor’ to replace the existing Private Network vendor – GE Jungle MUX. In parallel, the Systems Integrator will conduct ‘high-level’ design activities for the MPLS Private Network, including site surveys at 88 COMPANY substations to assess specific structural and infrastructure modifications required for the new equipment.
Dependency Management |  | 
Project | Deliverable | Date
NA |  | 
Overall Health This Period Last Period
Version 3.0