Our focus is on 2026.  As of today, we’ve spent $851,055 of the $2.6M.  We’re projecting to go over this year by $796,783 and that’s without anything new regarding phase 2.  If we had any idea of how much more is coming it would help a lot.  Are we talking about another $100K? $200K?  More?  That should be our focus.

I am not sure what work we’re moving from 2027 to 2026.  I only have our budget, current forecast, actuals, and projected variance.  The main reason for our overage this year was NOKIA where we just recently added a $753K forecast in March for PO 7000001857.  We also recently added “WD #8 Fiber Testing Elwood to Northport and add 7 Patch Panels” for an additional $68,893.  Let me know if you want me to review this with you prior to our meeting.

| JMUX Replacement | Total Capital | 2026 Capital |
| --- | --- | --- |
| CP Budget | $ 6,600,000 | $ 2,600,000 |
| Spend to Date | $ 4,722,381 | $ 851,055 |
| Remaining Budget | $ 1,877,619 | $ 1,748,945 |
| ETC | $ 2,545,728 | $ 2,545,728 |
| Projected Variance $ | $ (668,109) | $ (796,783) |
| Projected Variance % | -10.1% | -31% |
| EAC | $ 7,268,109 | $ 3,396,783 |